PAGE  
13


INDEX

S.No.
Particulars of Documents
Page No.

  

1.
Instructions to Executive Engineer
 
2
2.
Press Tender Notice
   3
3.
Notice Inviting E-Tendering (PWD-6)
   5 


4.
Form PWD-8
  11

5.
Specification & Conditins

57


6.
Schedule of Department issue of materials

79


7.
Sketch of Typical Cement Godown at site of work.
   80
8.
Clause of works agreement for settlement of disputes
   86
9.
Schedule of Quantities

88
Certified that this N.I.T. Contains Pages 1 to 89 (ONE TO EIGHTY NINE)  
A.E.(P)




Executive Engineer (P)/CC-11,NZ
INSTRUCTIONS TO EXECUTIVE ENGINEER

The Executive Engineer may kindly attend to the following points before inviting tender.

1. Executive Engineer before preparation of copies of tender documents for sale, shall go through the NIT and in case any discrepancy is noticed, the same should be got corrected from this office immediately.

2. The detailed Structural & Architectural Drawings should be made available to the contractor at the time of issue of NIT.

3. Condition at S.No.2(a) of PWD-6 regarding availability of site has been provided which Executive Engineer should confirm.

4. Press Notification given at Page- 3  is to be filled up by Executive Engineer before issue of NIT.

5. Date and Time and other details are to be filled by Executive Engineer in PWD-6 and press Tender Notice.

6. Services plans such as water supply, severage, strong water drains etc. are to be got approved from MCD by Executive Engineer Before taking of the work.
7. Executive Engineer should ensure that the A/A and E/S is available for the project or the permission to take up the work in anticipation of A/A and E/S has been given by competent Authority before call the tender.
8. The N.I.T has been approved, subject to the above remarks, for Rs. 85,80,402/-
9. The Executive Engineer/ND-9 should go through the NIT and in case any discrepancy noticed should be got corrected from this office immediately. 
10. One Page 79-81 of N.I.T. the materials unit and stores to be issued to the contractor are given.  These should be verified by EE before issue of the N.I.T. before issue of the N.I.T. after ascertaining the same from EE (Stores) availability of all materials stipulated shall be verified before tenders are called for.

Note:
This page contains Instructions to Executive Engineer, hence should not form part of tender document/Agreement.

AE (P)


            EE (P)

 
          SE/CC-11/NZ/DDA
                         
DELHI DEVELOPMENT AUITHORITY
E-TENDER PRESS NOTICE 

Press Notice / NIT No.13/SE/CC-11/DDA/2009-10


NIT No. 14/EE/ND-9/DDA/2009-10

Online Sealed Item Rate tenders are invited through E-Tendering mode for the following work by the Ex. Engineer/ ND-9/ DDA on behalf of the DDA upto 3.00 P.M. on (mentioned below) from the approved contractors of appropriate class of the DDA, CPWD, MES, P&T (Civil Wing) & Railway which shall be opened on the same day at 3.30 P.M. through e-tendering mode. 

The Tender documents can be obtained/downloaded on the e-tendering portal i.e. www.tenderwizard.com/dda on payment of cost of tender (non-refundable) with the CAU, North Zone and processing fees (non-refundable) of Rs.5678/-.  Sale of tender forms will be stopped four days (including the date of opening) before the date fixed for the opening of tender documents.

The manner of submission of tender, opening of the same shall  be only through e-tendering mode.

The tender shall be accompanied with earnest money Treasury Challan / Deposit at Call Receipt of a Schedule Bank/Fixed Deposit Receipt of a Scheduled Bank/Demand Draft of a Scheduled Bank issued in favour of Sr. AO(CAU)NZ, DDA.  50% of the Earnest money or Rs.20 (Twenty) lacs, whicheve is less, shall be in the form prescribed above and balance can be accepted in the form of Bank Guarantee issued by a schedule bank.

The earnest money receipt/challan/DD may be scanned and kept a copy with agency and the same may upload in the DDA e-tendering portal www.tenderwizard.com/dda while submitting the tender through online.

It shall be ensured that Demand Draft/Fixed Deposit Receipt is valid for a period of six months or more after the last date of receipt of tender and the same shall be in favour of Sr. Accounts Officer, CAU (NZ).  No interest shall be paid on Earnest money as deposited with DDA.

	S.

No.
	Name of Work
	Estimated Cost/ Earnest Money
	Last date of Sale/Date of Opening
	Cost of Tender
	Tender

Processing

 Fee
	Time 

Allowed

	1.
	Peripheral Development of integrated freight complex (IFC) at Narela including Bulk Services.

SH :  Construction of boundary wall along Railway Line from 100mt. R/W Road to Railway Freight Terminal and raising of boundary wall along Village Bhoregarh to Alipur Road.

 
	85,80,402/-

1,71,608/-
	19.12.09

23.12.09
	1,000/- + 4% DVAT = 1040/-
	5678/-
	6 Months


Further informations can be had from the website www.dda.org or www.tenderswizard.com/DDA
DDA will not be responsible for not getting internet connection / power supply while downloading the Electronic Bid Sheets/ Documents or while uploading their officers.

For obtaining the User ID and Passowrd and regarding downloading and uploading of e-tender documents the following persons may be contacted.

E-Tendering help desk

01122488721

Mr. M.K. Ghosh


09350893669

Mr. Sanjay Kumar 

08010367038

Mr. Mritunjay Jha

09717786058

Mr. Manish Kumar

09312064776

Any clarifications regarding the scope of work and technical features of the project can be had from the undersigned during office hours.

EXECUTIVE ENGINEER 

Division : ND-9
PWD -6

DELHI DEVELOPMENT AUTHORITY 

NOTICE INVITING E-TENDERS

DIVISION : ND-9







Sub Division - 
Online item rate tenders in the prescribed form and hereby invited on behalf of the Delhi Development for the work :- 

Name of work
: Peripheral Development of integrated freight complex (IFC) at Narela including Bulk Services.

SH   :   Construction of boundary wall along Railway Line from 100mt. R/W Road to Railway Freight Terminal and raising of boundary wall along Village Bhoregarh to Alipur Road.

1.
Estimated Cost
 :- 
Rs.85,80,402.00
2.
Contract document consisting of the detailed plans, complete specifications, the schedule of quantities of the various items of work to be done and a set of conditions of contract can be seen / purchased/ downloaded from the e-tendering website : www.tenderwizard.com/DDA or www.dda.org.in
(a)
The site of the work is available.
3(a)
The Time allowed for carrying out the work will be Six months after the date of written orders to commerce the work or from the first day of handing over of the site, whichever is later, in accordance with the phasing, if any, indicated in the tender documents. 

3(b)
The tenders shall be accepted only by e-tendering process and all details are available on the website : www.tenderwizard.com/DDA and www.dda.org.in These tenders should be opened only through online process.

3(c)
These tenders shall be opened by the concerned Executive Engineer, ND-9, in his office on the date fixed at 3.30 PM through e-tendering process only. Intending Tenders can see their bids after log in into the e tendering website www.tenderwizard.com/DDA or one of their authorized representatives (having proper Authority on letter head of the Contractor) will be allowed to enter into the premises where tenders shall be opened.

4(a)
Tender documents consisting of plans, Specifications, the schedule of quantities of the various classes of work to be done and the set of terms and conditions of necessary documents can be downloaded from the e-tendering website www.tenderwizard.com/DDA Tender documents will be issued only through e tendering website www.tenderwizard.com/DDA after the payment of Rs.1040/- (Including 4% VAT) as cost of Tender (non refundable) in the form of Cash to the office of the CAU, North Zone, Ashok Vihar DDA office and tender processing fee of Rs.5,678/- (non refundable) should be deposited in the form of demand draft
(b) Earnest Money of Rs.1,71,608.00 in cash/ receipt Trasury Challan/ Deposit at Call receipt of a schedule bank / Fixed Deposit receipt of a schedule bank/ Demand draft of a schedule bank issued in favou of AO/CAU/ North Zone/DDA.  When amount of earnest money is more than Rs.5 lac part of earnest money is acceptable in the form of bank guarantee also in such cases minimum 50% of earnest money (but not less than Rs.5 lac) shall be deposited in the shape as described above and for balance amount of earnest money bank guarantee will be also be acceptable in favour of AO/CAU/North Zone, DDA.
Note : Demand draft/ Bank Guarantee / Cash receipt should be scanned and uploaded in to the e-tendering site while submitting the tenders. The original Earnest money has to be submitted physically to the office of the Executive Engineer, ND-9, DDA on before the last date and time of the tender submission as mentioned in the table.
5. The contractors should quote in figures in a blue color cells as well as in words in rate and amount tendered by them. The amount for each item should be worked out and the requisite total by given.

6.
Tender must be submitted through e-tendering process only. The tender and the proof / receipt of deposited Earnest Money shall be placed in separate sealed envelope, each marked ‘Tender’ and ‘Earnest Money’ respectively. In case where Earnest money in cash is acceptable the same shall be deposited with the cashier, CAU, North Zone, Ashok Vihar,DDA.

7.
The Contractor, whose tender is accepted, shall execute an Agreement on Rs.50/- non judicial stamp paper reiterating his acceptance of the execution of the work on the rates, terms and conditions set in the Contract document.

a).
The Contractor, whose tender is accepted, shall be required to furnish by way of Performance Guarantee / Security Deposit for due fulfillment of his Contract at the following rate :- 

b)
Performance Guarantee of 5% (five percent) of the tendered amount for the proper performance of the Contract Agreement within fifteen days of issue of letter of intent. This period can be further extended by the Engineer-in Charge up to a maximum period of seven days on written request of the Contractor. This guarantee shall be in the form of Govt. Security or Fixed Deposit Receipt or Guarantee Bond of any Scheduled Bank or the State Bank of India in accordance with the form annexed hereto.

c)
Security Deposit @ 5% (five percent) of the tendered value of the work by way of deduction from the running bills of the Contractor @ 10% (ten percent) of gross amount of each running bill till the sum along with the sum already deposited as Earnest Money will amount to 5% of the tendered value of the work.

8.
The acceptance of tender will rest with the CE/NZ/ DDA,  who does not bind himself to accept the lowest tender and reserve to himself the Authority to reject any or all the tenders received without assigning any reason. All tenders in which any of the prescribed condition not fulfilled or incomplete in any respect are liable to be rejected.

9.
Canvassing in connection with tenders is strictly prohibited and the tender submitted by the Contractor who resort to canvassing shall be liable to rejection.

10.
All rates shall be quoted on the proper schedule of the Tender.

11.
Item rate tender containing percentage below/ above will be summarily rejected.

11(a)
It may please be carefully noted that no condition, whatsoever, shall be accepted by the Department and the Contractor is not prepared to execute the work at the terms and conditions contained in the tender document, he is requested not to tender for this work. It may be noted that if any Contractor chooses to submit conditional tender in spite of clear direction given above his tender shall be liable to summarily rejected and his full Earnest money shall stand forfeited. He will also be liable for being debarred from tendering in DDA for a period of six months.

 11(b)
Monthly payment to the Contractor will be made when gross amount o the work done during the previous months is not less than.


Amount of Contract 



Gross Value of work since previous








Bill should exceed


Over Rs.10 lacs Value



Rs.25000/-


Over Rs.2 Lacs up to Rs.10 lacs


Rs.10000/-


Over Rs.50000 upto Rs.2 lacs


Rs.5000/-


Over Rs.50000/-



Rs.2500/-

12. On acceptance of the tender the name of the authorized representative of the contractor, who would be responsible for taking instruction from the Engineer-in-Charge, shall be communicated to the Engineer-in-charge.
13. Special care should be taken while quoting the rates that the rates should invariably by in two decimal places.
14. Delhi Development Authority does not bind itself to accept the lower any tender and reserves to itself for accepting the whole or any part of the tender and the tenderer shall be bound to perform the same at the rate quoted.
15. Sales Tax / VAT or any other Tax on materials in respect of this Contract shall be payable by the Contractor and DDA will not entertain any claim whatsoever in this respect.

16(a)
Contractor must produce valid certificate of Registration with works Contract Cell of Sales Tax Department of GNCTD. The Tenderer shall submit the Tax Clearance Certificate in Form 11 (under Rule 8(2) of the Delhi Sales Tax of works Contract Rule (Latest) ) issued by the said cell before the tender paper can be sold to him. 

17.
A Contractor shall not be permitted to tender for works in the DDA Zone (responsible for award and execution of Contract) in which any of his near relative is posted as Divisional Accountant or as an Officer in any capacity between the grades of CE and JE (both inclusive) in the DDA. He shall intimate the name of his near relatives, if any, (both inclusive) in the DDA. He shall also intimate the name of his near relatives. If any, who are working as group A, B, or C officer in DDA. He shall also intimate the name of the persons who are working with him in any capacity or who are subsequently employed by him and who are near relatives, if any Groups A,B, or C Officer in the DDA. Any breach of this condition by the Contractor would render him liable to action under Clause 3 of the Agreement. In addition, he would also be liable to be debarred from tendering in future.

18.
The Contractor shall also give a list of Non gazetted DDA employees related to him.

19.
No Engineer of Gazetted rank or other Gazetted officer employed in Engineering or Administrative duties in any Engineering Deptt. of the Govt. of India/ Delhi Development Authority is allowed to work as contractor for a period of one year of his retirement from Govt. Service/ Delhi Development Authority. The contract is liable to be cancelled, if either the Contractor or any of his employees are found at any time to be such a person who had not obtained the permission from the Govt. of India/ Delhi Development Authority as aforesaid, before the submission of the tender or engagement in the contractors service.


The Engineering Depts. of India includes the Engineering Depts. of CPWD, MES, P&T, DDA .

20.
The tender for work shall remain open for acceptance, for a period of 60 (sixty) days from the date of opening of tenders. If any, tenderer withdraws his tender before the said period or makes any modifications in terms and conditions of the tender which are not in acceptance to the department, then the DDA shall, without prejudice to any other right or remedy, be at liberty to forfeit the entire amount of the said Earnest Money absolutely.

21.
The tender for the work shall not be witnessed by a Contractor or Contractors who himself/ themselves has/ have tendered for the same work. Failure to observe this condition would render the tender of tenderers as well as witnessing the tender is liable to summarily rejection.

22.
Approved and eligible contractors of DDA, CPWD, and those on the appropriate list of P&T, MES and Railways are also eligible to tenders.

23.
The tender for the Composite work includes the Building portion, Sanitary, water supply, drainage works.

24.
The tenderer  apart from being a class I B&R Contraoctor must associate himself with agencies of the appropriate class which are eligible to tender for sanitary& Water supply installation.
25.
The Contractor shall submit the list of works which are in hand (progress) in the performa given below :- 

	Name of work 
	Name and particulars of Division where the work is being executed 
	Amount of work
	Position of work 
	Work in Progress
	Remarks


The facility of exemption from depositing the earnest money by virtue of executing the bond was withdrawn w.e.f. 20.12.89 and the bond stand cancelled from this date.  Each intending tenderer has to deposit the required earnest money with individual tenderin para 8.
26 The tenderer shall inspect and study the drawings referred in the Tender documents in the office of the Executive Engineer before and for the purpose of submitting the tender.
27 It has further been observed by CTE that in particular tender the contractor did not quote rate for a particular item.  However, as per tender condition, tender in which any of the prescribed conditions are not fulfilled or incomplete in any respect, such tender are liable to be rejected.  Instad of rejecting such incomplete tender or adopting ‘Nil” rate where contractor did not quote, justified rate observed to have been paid to the contractor, thus extending undue benefit to the contractor.

Therefore, it is enjoined upon all concerned that the tender in which any of the prescribed conditions are not fulfilled and/or the tender which is incomplete in any respect, shall be rejected.  Wherever the contractor has not mentioned any rate against any item(s), the rates agains such item(s) shall be treated as ‘Nil’ for evaluation/ execution purpose. 

28 ADDITIONAL CLAUSE

Case of withdrawal of offer                         Action to be Taken


	i).
	If the contractor modifies/ withdraw their offer within 60 days of quoting the rates.

	The earnest money deposited by the contractor shall be forfeited 50%

	ii)
	If the contractor withdraw his offer immediately after the award of work
	The earnest money deposited by the contractor shall be forfeited absolutely 



	(iii)

(iv)
	If the contractor /agency withdraw his offer after award of the work and taking over possession of site.

The work/ supply shall remain open for a peiroe of 60 days from the date of opening of quotation.  The DDA shall without prejudice to any other right or remedy, be at liberty to forfeit 50% of the earnest money, if any quotationer withdraws this quotation before the said period or makes any modification in the terms and condition of the offer which are not acceptable to the department and to forfeit the whole of the earnest money if the quotationer whose quotation is accepted fails to commence the work/ supply specify in the NIT along with changes in the scope if any) in the prescribed time or abandons the work/ supply before its completion.
	It is deemed that the Contractor has entered into contract and the action under clause 2&3 of he agreement i.e. taking up work at the risk and cost of the contractor and to penalize the contractor for not completing the work within the stipulated period will be taken against the contractor if he abandons the site after taking over the possession of the site  from the Engineer-in-charge. For taking action under Clause 2&3, the only documentary proof required will be the document showing signature of the Contractor or his authorized representative for taking over the possession of site. It is further clarified that action under Clause 2 & 3 of the Agreement attracted even through the Contractor fails to sign the Agreement on Rs.50/- non judicial stamp paper but do not start work from the tenth day after the date on which the order to commence the work is issued to the Contractor. The date of start of the work will be considered as date of taking over the possession of site. In case of tender for supply of material the documentary proof for start will be submission of samples of approval of Engineer-in-Charge i.e. in case the supply order is given to the Contractor and he fails to supply the materials or submit the samples to Engineer-in –charge then the action to be taken against the contractor is only the forfeiture of earnest money and if he submits the samples for supply and there after abandons the work or fails to supply the materials then action under Clause 2 & 3 is attracted

Signature of _____________________Divisional Officer

For and behalf of _____________________ D.D.A.

Dt. New Delhi ________200 _______











Executive Engineer (P)









CC-11/DDA

PWD-8

DELHI DEVELOPMENT AUTHORITY

Item Rate Tender For work

I/We hereby tender for the execution of the work for the Delhi Development Authority of the work specified in underwritten memorandum within the time specified in such memorandum at an amount of Rs._______________ (Rupees ______________________________________) the item rate tender entered in the schedule attached and in accordance with all aspects with the specifications, design, drawings and instructions in writing, referred to rule 1 hereof in clause-11 of the conditions of contract, and with such materials as are provided for, by and in all other respects in accordance with, such conditions so far as applicable.
Memorandum

(a)
General Description

Name of work
: Peripheral Development of integrated freight complex (IFC) at Narela including Bulk Services.

SH   :   Construction of boundary wall along Railway Line from 100mt. R/W Road to Railway Freight Terminal and raising of boundary wall along Village Bhoregarh to Alipur Road.

(b)
Estimated Cost
:- Rs.85,80,402.00

(c )
Earnest Money
:
Rs.1,71,608/-
(d)
Security Deposit
:
As per Clause 1 & 1(a) 

(e)
Time allowed for the work from the 10th day after the date of written order to commence
: Six months


Should this tender be accepted, in whole or in part, I/We hereby agree:

(i)
To abide by and fulfill all Terms and Provisions of the said Conditions annexed hereto and all the Terms and provisions contained in the Notice Inviting Tender so far as applicable and/or in default thereof to forfeit and pay to the DDA or their successors the sum of money mentioned in the said conditions.

(ii)
To execute all the works referred to in the tender documents on the Terms & Conditions contained or referred to therein and to carry out such deviations as may be ordered up to maximum of 20% and hereafter called the Deviation Limit of tender, at the rates quoted in tender documents and those in excess of this limit at the rates to be determined in accordance with the provisions contained in clause 12-A of the tender form.


A sum of Rs. 171,608/- has been deposited in Cash/Receipt Treasury Challan/Deposits at Call Receipt of a Scheduled Bank/Fixed Deposit Receipt of a Scheduled Bank /Demand Draft of a Scheduled Bank/Bank Guarantee as earnest money as per provisions laid down in para 4 above of the NIT (PWD6) in favour of Sr.AO/CAU/North Zone/DDA.  If I/We fail to furnish the prescribed Performance Guarantee within the prescribed period,  I/we agree that the said DDA or his successors in office shall without prejudice to any other right or remedy, be at liberty to forfeit the said earnest money absolutely.  Further if, I/We fail to commence work as specified, I/We agree that Chairman, DDA or his successors in office shall without prejudice to any other right or remedy available in law, be at liberty to forfeit the said earnest money & the Performance Guarantee absolutely, otherwise the said earnest money shall be retained by him towards Security Deposit to execute all the works referred to in the tender documents upon the terms & conditions contained or referred to therein & to carry out such deviations as may be ordered up to maximum of the percentage mentioned elsewhere in the tender documents & those in excess of that limit at the rates to be determined in the accordance with the provisions contained in clause 12 & 12 A of the tender form.  I/We hereby declare that I/We shall treat the tender documents, drawings & other records connected with the work as secret/confidential documents & shall not communicate information derived there from to any person other than the person to whom I am/We are authorized to communicate the same or use the information in any manner prejudicial to the safety of the state.

REBATE CONDITIONS


It may please be carefully noted that no conditions whatsoever (beyond the tender documents placed below) shall be accepted by the Dept. and the contractors are strictly prohibited from giving conditional tenders.  If any contractor is not prepared to execute the work at the terms and conditions contained in the tender documents, he is requested not to tender for this work.  It may be noted that if any contractor chooses to submit conditional tender, inspite of clear directions given above, his tender shall be liable to be rejected summarily and his full earnest money shall stand forfeited.  He will also be liable for being debarred from tendering in DDA for a period of six months. 

Dated the ……………….day of …………………..200

Name and Signature Contractor before Submission of Tender

Signature of Witness



Signature of Contractor 

Name of witness.




Postal Address

Address ……………………………… 

……………………………………

………………………………………..         

 ……………………………………

Occupation……………………………

The above tender for the sum of Rs.__________________ (Rupees___________________________________) only  is hereby accepted by me ________________ Engineer _____________ Division _________________ on behalf of the DDA.





Signature of ______________Engineer
DELHI DEVELOPMENT AUTHORITY

General Rules and Directions


The liability of exemption for depositing the earnest money by virtue of exempting the bonds stand withdrawn w.e.f.26.12.89 and all the bonds stand cancelled fom.  This date ends intending tenderer has to deposit the required earnest money with individual tender and mentioned in para 8 of PWD-6.  
1.
All works proposed for execution by contractor will be notified in a form of invitation to tender posted in public place signed by the Divisional Officer. This form will state the work to be carried out as well as the date for submitting and opening tenders and the time allowed for carrying out the work also, the amount of earnest money to be deposited with the tender and the percentage at which the security deposit shall be deducted from the bills of the successful tenderer.  Copies of the specifications, design and drawings and schedule of quantities and of rates of the various descriptions of work and any other document required in connection with the work assigned for the purpose of identification by the Divisional Officer shall also be open for inspection by the contractor at the office of Divisional Officer during office hours.

2.
In the event of tender being submitted by a firm, it must be signed separately by each partner thereof, or in the event of the absence of any partner, it must be signed on his behalf by a person holding a power of attorney authorizing him to do so.  Such power of attorney to be produced with the tender and, it must disclose that the firm is duly registered under the Indian Partnership Act.

3.
Receipt for payments made on account of work, when executed by a firm must also be signed by the several partners except where the contractors are described in their tender as a firm, in which case the receipts must be signed in the name of the firm by one of the partners or by some other person having authority to give effectual receipt for the firm.

4.
Any person who submits the tender shall fill up the usual printed form, stating at what rate he is willing to undertake each item of the work only one rate of percentage more or less at the estimated rates/ schedule rates shall be named.  Tender which proposes any alteration in the work specified in the said form of invitation to tender or in the time allowed for carrying out the work or which contains any other condition of any sort including conditional or unconditional rebates will be summarily rejected.  No single tender shall include more than one work, but contractors who wish to tender for two or more works shall submit a separate tender for each work. Tenders shall have the name and number of the work to which they refer written outside the envelope.


(a)
The rate(s) and amount(s) must be quoted in decimal coinage.  Amount must be quoted in full rupee ignoring fifty paisa and considering more than fifty paisa as Rupee one.       

5.  
The Divisional Officer or his duly authorized representative will open tenders in the presence of intending contractors who may be present at the time and will enter the amount of the several tenders in a comparative statement in a suitable form.  In the event of a tender being accepted, a receipt for the earnest money forwarded there with shall thereupon be given to the contractor who shall thereupon for the purpose of identification signed copies of the specifications and other documents mentioned in rule-1. In the event of a tender being rejected, the earnest money forwarded with such unaccepted tender shall thereupon be returned to the contractor remitting the same.

6.   
The officer inviting tenders shall have the right of rejecting all or any of the tender and will not be bound to accept the lowest tender.

7.
The receipt of an accountant or clerk for money paid by the Contractor will not be considered as acknowledgement of payment to the Divisional Officer and the Contractor shall be responsible for seeing that he procures a receipt signed by Divisional Officer or duly authorized cashier of CAU(NZ)DDA.

8.
The memorandum of work tendered, for the schedule of materials to be supplied by the DDA and their issue rates, shall be filled in and completed, in the office of the Divisional Officer before the tender form is issued.  If a form is issued to an intending tenderer without having been so filled in and completed, he shall request the office to have this done before he completes and delivers his tender.
9.
In the case of Item Rate Tenders, only rates quoted shall be considered. Any tender containing percentage below/above the rates quoted is liable to be rejected. Rates quoted by the contractor in item rate tender in figures and words shall be accurately filled in so that there is no discrepancy in the rates written in figures and words.  However, if a discrepancy is found, the rates which correspond with the amount worked out by the Contractor shall, unless otherwise proved, be taken as correct.  
9(a)
If the amount of an item is not worked out by the Contractor or it does not correspond with the rates written either in figures or words, then the rates quoted by the Contractor in words shall be taken as correct.  Where the rate quoted by the Contractor in figures or in words tally but the amount is not worked out correctly, the rates quoted by the Contractor will unless otherwise provided be taken as correct and not the amount.  In the event of no rate has been quoted for any items(s), leaving space both in figure(s), word(s), and amount blank, it will be presumed that the Contractor has loaded the cost of this/these item(s) in other item(s) and the rate for such item(s) will be considered as Zero and work will be required to be executed accordingly.

10.
If it is found that the tender is not submitted in proper manner or contains too many corrections or absurd rates or amount it would be open for the DDA to reject the same.

11.
The tenderer shall sign a declaration under the official secret Act for maintaining secrecy of the tender and shall return all the drawings or other records connected with the work given to them.  The unsuccessful tenderer shall return all the drawings given to them.

DECLARATION

I/We hereby declare that I/We shall treat the tender documents drawings and records connected with the work as secret confidential documents and shall not communicate information to any persons other than a person to whom I am/We are authorized to communicate the same or use the information in any manner prejudicial to the safety of state.

                                                                                                          Signature of the Contractor

















CONDITIONS OF CONTRACT

Definition:

1.
The Contract means the documents forming the tender and acceptance there of and formal agreement executed between the Executive Engineer, DDA and the Contractor together with the documents referred to therein including the conditions, specifications, design, drawing and instructions issued from time to time by the Engineer-in-Charge and all the documents taken together shall be deemed to form one contract and shall be complimentary to one another.

2.
In the contract, the following expressions shall thereof, unless the context otherwise requires, have the meaning hereby respectively assigned to them.

(a)
The expression Work shall, unless there be something either in the subject or context repugnant to such construction to  be constructed and taken to mean the work by or by virtue of the contract to be executed whether temporary or permanent and whether original, altered, substituted or additional.

(b)
The Site shall mean the land or other places or through which the work is to be executed under the contract or any adjacent land, path or street through which work is to be executed under the contract or any adjacent land path of street which may be allotted or used for the purpose of carrying out the contract.

(c) 
The Contractor shall mean the individual or firm or company whether incorporated or not, undertaking the works and shall include the legal personal representative or  such individual or the persons comprising such firm or company or the successors of such individual firms or company and the permitted assignees of such individual or firms or company.

              (d)         The Authority or DDA means the Delhi Development Authority.


(e)
The Engineer-in-Charge means the Divisional Officer who shall supervise and be in-charge of the work and who shall sign the Contract on behalf of the DDA.


(f)
The Chairman, Government or Government of India shall mean the V.C. DDA of Delhi.

g)  The terms Chief Engineer means concerned Zonal Chief Engineer, DDA.   Words imparting the singular number include the plural number and vice-versa.


(h)
The Chief Technical Examiner/Technical Examiner means the Chief Technical Examiner/Technical Examiner of Central Vigilance Commission of Govt. of India.

3.
The contractor shall be deemed to have satisfied himself before tendering as to the correctness and sufficiency of his tender for the works and of the rates and prices quoted in the Schedule of Quantities, which rates and the price shall, except as otherwise provided, cover all his obligations under the contract and all matters and things necessary for the proper completion and maintenance of the works.

4.
The several documents forming the contract are to be taken as mutually explanatory of one another, detailed drawings being followed in preference to small scale drawing and figured dimensions in preference to scale and special conditions in preference to General Conditions.

4.1
In the case of discrepancy between the Schedule of Quantities, the specifications and/or the drawings, the following order of preference shall be observed:

                a)           Description in Schedule of Quantities.


b)
Particular specifications and Special Conditions, if any.


c)
Drawings


d)
CPWD Specifications


e)
Indian Standard Specifications of BIS

4.2
If there are varying or conflicting provisions made in any one document forming part of the contract, the Accepting Authority shall be the deciding authority with regard to the intention of the documents and his decision shall be final and binding on the contractor.

4.3
Any error in description, quantity or rate in Schedule of Quantities or any omission there from shall not vitiate the contract or release the contractor from the execution of the whole or any part of the works comprised therein according to drawings and  specifications or from any of his obligations under  the contract.

CLAUSES OF CONTRACT

Clause 1: The person/persons whose tender(s) may be accepted (hereinafter called the contractor) shall permit DDA at the time of making any payment to him for work done and measured under the contract to deduct a sum at the rate of 10% of the gross amount of each running bill till the sum along with the sum already deposited as earnest money, will amount to security deposit of 5% of the tendered value of the work. Such deductions will be made and held by DDA by way of security deposit unless he has/they have deposited the amount of security at the rate mentioned above in cash or in the form of Govt. Securities or FDR (FDRs).  In case a FDR of any Bank is furnished by the Contractor to DDA as part of the Security Deposit and the Bank is unable to make payment against the said FDRs, the loss caused thereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the DDA to make good the deficit.

All compensations or the other sums of money payable by the contractor under the terms of this contract may be deducted from, or paid by the sale of a sufficient part of his security deposit or  from the interest arising therefrom, or from any sums which may be due to or may become due to the contractor by DDA on any account whatsoever and in the event of his security deposit being  reduced by reason of any such  deductions or sale as aforesaid, the contractor shall within 10 days make good in cash or FDR tendered by the State Bank of India(SBI) or by Scheduled Banks or Government securities (if deposited for more than 12 months) endorsed in favour of the Engineer-in-Charge, any sum or sums which may have been deducted  from or raised by sale of his security deposit or any part thereof.  The security deposit shall be collected from the running bills of the Contractor at the rates mentioned above and the earnest money, if deposited in cash at the time of tenders  will be treated a part of the security deposit.

NOTE:1.
Govt. papers tendered as security will be taken at  5% (five percent) below its market price or at its face value, whichever is less.  The market price of Govt. paper would be ascertained by the Divisional Officer at the time of collection of interest and the amount of interest to the extent of deficiency in value of the Govt. paper will be withheld, if necessary.


2. 
Govt. Securities will include all forms of securities mentioned in rule no.274 of the G.F. Rules except fidelity bond.  This will be subject to the observance of the conditions mentioned under the rule against each form of security.
Clause1(A):  Performance Guarantee

i)
The contractor shall submit an irrevocable PERFORMANCE GURANTEE  of 5% (five percent) of the tendered amount in addition  to other deposits mentioned elsewhere in the contract for his proper performance of the contract agreement, (notwithstanding and/or without prejudice to any other provisions in the contract) within 15 days of issue of the letter of intent.  This period can be further extended by the Engineer- in-Charge up to a maximum period of 7 days on written request of the contractor stating the reason for delays in procuring the Bank Guarantee, to the satisfaction of the Engineer -in- Charge.  This Guarantee shall be in the form of Govt.  Securities or FDRs or Guarantee bonds of any Scheduled Bank or the SBI in accordance with   the form annexed hereto (Annexure II).   In case FDR of any Bank is furnished by the contractor to the DDA as part of the Performance Guarantee and the bank is unable to make payment against the said FDR, the loss caused hereby shall fall on the contractor and the contractor shall forthwith on demand furnish additional security to the DDA to make good the deficit.

ii)
A letter of intent shall be issued in the first instance informing the successful tenderer by the competent Authority to accept his tender and the award letter shall be issued only after the Performance Guarantee in any of the prescribed form is received.  In case of failure by the contractor to furnish the Performance Guarantee within the specified period, D.D.A. shall without prejudice to any other right or remedy available in law, be at liberty to forfeit the earnest money absolutely.

iii)
The Performance Guarantee shall be initially valid up to the stipulated date of completion plus 60 days beyond that. In case the time for completion of works gets enlarged, the contractor shall get the validity of Performance Guarantee extended to cover such enlarged time for completion of work.  After  recording of the completion certificate for the work by the competent authority, the Performance Guarantee shall be returned to the contractor, without any interest.

iv)  
The Engineer-in-Charge shall not make a claim under the Performance Guarantee except for amounts to which the DDA is entitled under the contract (notwithstanding and/or without prejudice to any other provisions in the contract agreement) in the event of :-


a)     Failure by the contractor to extend the validity of the Performance Guarantee as described hereinabove, in which event the Engineer-in-Charge may claim the full amount of the Performance Guarantee.


b)

Failure by the contractor to pay DDA any amount due, either as agreed by the contractor or determined under any of the clauses/conditions of the agreement, within 30 days of the service of notice to this effect by Engineer- in-Charge.

v)

In the event of the contract being determined or rescinded under provision of any of the clause/condition of the agreement, the Performance Guarantee shall stand forfeited in full and shall be absolutely at the disposal of the DDA

NOTE: - Note 1 & 2 given under clause 1 shall be applicable for Clause 1(A) also.

Clause 2: If the contractor fails to maintain the required progress in terms of clause 5 or to complete the work and clear the site on or before the contract or extended date of completion, he shall, without prejudice to any other right or remedy available under the law to the DDA, on account of such breach, pay as agreed compensation the amount calculated at the rates stipulated below as the Superintending Engineer(whose decision in writing shall be final and binding) may decide on the amount of tendered value of the work for every completed day/month (as applicable) that the progress remains below that specified in Clause 5 or that the work remains incomplete.

This will also apply to Items or group of Items for which a separate period of completion has been specified.

Compensation for delay of work @ 1.5% per month of delay to be computed on per day basis.

Provided always that the total amount of compensation for delay to be paid under this condition shall not exceed 10% of the tendered value of work or of the tendered value of the item or group of items of work for which a separate period of completion is originally given.

The amount of compensation may be adjusted or set off against any sum payable to the contractor under this or any other contract with the DDA.  In case, the contractor does not achieve a particular milestone in Annexure-II or the reschedule  milestone(s) in terms of Clause 5.4, the amount shown against that milestone shall be withheld, to be adjusted against the compensation levied at the final grant of extension of time. Withholding of this amount on failure to achieve a milestone, shall be automatic without any notice to the contractor.  However, if the contractor catches up with the progress of work on the subsequent milestone(s), the withheld amount shall be released. In case the contractor fails to make up for the delay in the subsequent milestone(s), the amount mentioned against each milestone missed subsequently also shall be withheld.  However, no interest, whatsoever, shall be payable on such withheld amount.

Clause 3:  The Engineer-in-Charge may, without prejudice to his any other right or remedy against the contractor in respect of any delay, inferior workmanship, any claims for damages and/or in respect of any breaches of contract and without prejudice to any right or remedies under any of the provisions of this contract or otherwise, and whether the date for completion has or has not elapsed, by notice in writing absolutely determine the contract in any of the following cases:-
i)
If the contractor having been given by the Engineer-in-Charge a notice in writing to rectify, reconstruct or replace any defective work or that the work is being performed in an inefficient or otherwise improper or unworkman like manner shall omit to comply with the requirements of such notice for a period of seven days thereafter.

ii)       If the contractor being a company shall pass a resolution or the court shall make an order that the company shall be wound up or if a receiver or a manager on behalf of a creditor shall be appointed or if circumstances shall arise which entitle the court or the creditor to appoint a receiver or a manger or which entitle the court to make a winding up order.

iii)
Deleted

iv)
If the contractor has, without reasonable cause, suspended the progress of the work or has failed to proceed with the work with due diligence so that in the opinion of the Engineer-in-Charge (which shall be final and binding) he will be unable to secure completion of the work by the date for completion and continues to do so after a notice in writing of seven days from the Engineer-in-Charge.

v)
If the contractor fails to complete the work within the stipulated  date or items of work with individual date of completion, if any stipulated, on or before such date(s) of completion and does not complete them within the period specified in a notice given in writing in that behalf by the Engineer-in-charge

vi)
If the contractor persistently neglects to carry out his obligations under the contract and/or commits default in complying with any of the terms and conditions of the contract and does not remedy it or take effective steps to remedy it within 7 days after a notice in writing is given to him in that behalf by the Engineer-in-Charge.

vii)
If the contractor commits any acts mentioned in Clause 21 hereof.

viii)
If the work is not started by the contractor within 1/8th of stipulated time. When the contractor has made himself liable for action under any of the cases aforesaid, the Engineer-in-Charge on behalf of the DDA shall have powers:

a)
To determine or rescind the contract as aforesaid (of which termination or rescission notice in writing to the contractor under the hand of Engineer-in-Charge shall be conclusive evidence). Upon such determination or rescission, the earnest money deposit, security deposit already recovered and Performance Guarantee under contract shall be liable to be forfeited and shall be absolutely at the disposal of the DDA.

b)
Deleted

c)       
After giving notice to the contractor to measure the work of the contractor and to take such whole, or the balance or part thereof, as shall be unexecuted out of his hands and to give it to another contractor to complete the work. The contractor, whose contract is determined or rescinded as above, shall not be allowed to participate in the tendering process for the balance work.
In the event of above courses being adopted by the Engineer-in-Charge, the contractor shall have no claim to compensation for any loss sustained by him by reasons of his having purchased or procured any materials or entered into any engagements or made any advances on account or with a view to the execution of the work or the performance of the contract.  And in case action is taken under any of the provision aforesaid, the contractor shall not be entitled to recover or be paid any sum for any work thereof or actually performed under this contract unless and until the Engineer-in-Charge has certified in writing the performance of such work and the value payable in respect thereof and he shall only be entitled to be paid the value so certified.

Clauses 3A: In case, the work cannot be started due to reasons not within the control of the contractor within 1/8th of the stipulated time for completion of work, either party may close the contract.  In such eventuality, the earnest money deposit and the Performance Guarantee of the contractor shall be refunded, but no payment on account of interest, loss of profit or damages etc. shall be payable at all.

Clause 4: In any case in which any of the powers conferred upon the Engineer-in-Charge by Clause 3 thereof, shall have become exercisable and the same are not exercised, the non-exercise thereof shall not constitute a waiver of any of the conditions hereof and such power shall notwithstanding be exercisable in the event of any future case of default by the contractor and the liability of the contractor for the compensation shall remain unaffected.  In the event of the Engineer-in-Charge putting in force all or any of  the powers vested in him under the preceding clause he may,  if he so desires after giving a notice in writing to the contractor take possession of (or at the sole desecration  of Engineer-in-Charge which shall be final and binding on the contractor)   use as on hire (the amount of the hire money being also in the final determination of the Engineer-in-Charge) all or any tools, plants, materials and stores in or upon the works or the site thereof, belonging to the contractor, or  procured by the contractor and intended to be used for the execution of the work/or any part thereof, paying or allowing for the same in account  at the contract rates or in the case of these not being applicable at current market rates to be certified by the Engineer-in-Charge whose certificate thereof shall be final and binding on the contractor, otherwise the Engineer-in-Charge by giving this in writing may order the contractor, or his clerk of the  works, foreman or other authorized agent to remove such tools, plants, materials or stores from the premises (within a time to be specified in such notice)  in the event of the contractor failing to comply with  any such requisition, the Engineer-in-Charge may remove them at the contractor’s expense or sell them by auction or private sale on account of the contractor and at his risk in all respects and the certificate of the Engineer-in-Charge as to the expenses of any such removal and the amount of the proceeds and expenses of any such  sale shall be final and conclusive against the contractor.

Clause 5: The time allowed for execution of the work as specified in the Annexure-II of the extended time in accordance with these conditions shall be the essence of the contract.  The execution of the works shall commence from the 15th day or such time period as mentioned in letter of award after the date on which the Engineer-in-Charge issues written orders to commence the work or from the date of handing over of the site whichever is later.  If the contractor commits default in commencing the execution of the work as aforesaid DDA shall without prejudice to any other right or remedy available in law, be at liberty to forfeit the Earnest Money & Performance Guarantee absolutely.

5.1
As soon as possible after the contract is concluded, the contractor shall submit a Time & Progress Chart for each milestone and get it approved by the department.  The chart shall be prepared in direct relation to the time stated in the contract documents for completion of items of the works.  It shall indicate the forecast of the dates of commencement and completion of various trades of sections of the work and may be amended as necessary by agreement between the Engineer-in-Charge and the contractor  within the limitations of time imposed in the contract documents and further to ensure good progress during the execution of the work, the contractor shall in all cases in which the time allowed for any work, exceeds one month (save for special jobs for which a separate programme has been agreed upon) complete the work as per milestones given in Annexure-II.
5.2 If  the work (s) be delayed by :


i)
Force majeure, or   


ii)
Abnormally bad weather, or 


iii)
Serious loss or damage by fire, or             


iv)
civil commotion, local commotion of workmen, strike or lockout, affecting any of the trades employed on the works, or 


v)
delay on the part of other contractors or tradesmen  engaged by Engineer- in-Charge in executing work not forming part of the contract, or


vi)
non availability of stores, which are the responsibility of  Govt./DDA to supply, or


vii)
non availability or break down of tools and Plant to be supplied by Govt./DDA, or 


viii)
any other cause which, in the absolute discretion  of the  authority  mentioned in Annexure-II is beyond the contractor’s control. 


then upon the happening of any such event causing delay, the contractor shall immediately give notice thereof in writing to the Engineer-in-Charge but shall  nevertheless use constantly his best endeavors to prevent or make good the delay and shall do all that may be reasonably required to the satisfaction of the Engineer-in- Charge to proceed with the works.

5.3
Request for rescheduling of mile stones and extension of time, to be eligible for consideration, shall be made by the contractor in writing within fourteen days of the happening of the event causing delay on the prescribed form.  The contractor may also, if practicable, indicate in such a request the period for which extension is desired.

5.4
In any such case the authority mentioned in Annexure-II may give a fair and reasonable extension of time and reschedule the milestone for completion of work.  Such extension shall be communicated to the contractor by the Engineer-in-charge in writing within 3 months of the date of receipt of such request.  Non application by the contractor for extension of time shall not be a bar for giving a fair and reasonable extension by the Engineer-in-Charge and this shall be binding on the contractor.

Clause-6: Within 10 days of the completion of the work the contractor shall give notice of such completion to the Engineer-in-Charge and within 10 days of the receipt of the such notice the Engineer-in -charge shall inspect the work and if there is no defect in the work, he shall furnish the contractor with a certificate of completion otherwise a provisional certificate indicating defects (a) to be rectified by the contractor, and/or  (b) for which payment will be made at reduced rates, be issued but no certificate of  completion, provisional or otherwise,  shall be issued, nor  shall the work be considered to be completed until the contractor shall have removed from the premises on which the work shall be executed all scaffolding surplus materials, rubbish and all huts and sanitary arrangement required for his work people on the site in connection with the execution of the work, which shall have been erected or constructed by the contractor and cleaned of the dirt from all wood work, doors, windows, walls floors or other parts of any building in, upon or about which work is to be executed or of which he may have had possession for the purpose of the execution thereof, and not until the work shall have been measured by the Engineer-in-Charge.  If the contractor fails to comply with the requirements of this clause as to removal of scaffolding, surplus materials and rubbish and all huts and sanitary arrangement as aforesaid and cleaning of dirt on or before the date fixed for the completion of the work, the Engineer-in-Charge may at the expense of the contractor remove such scaffolding, surplus materials and rubbish etc.  and dispose of same as he thinks fit and clean of such dirt as aforesaid and the contractor shall have no claim in respect of any such scaffolding or surplus materials as aforesaid accept for any sum actually released by the sale thereof.

Clause 6A : When the annual repairs and maintenance work is carried out, the splashes and dropping from white washing colour washing, painting etc. on walls, doors, roofs, windows etc. shall be removed and the surface cleaned simultaneously with completion of these items of works in the individual rooms, quarters or premises etc. where the work is done without waiting for the actual completion of the other items of the work in contract.  In case the contractor fails to comply with the requirements of this clause, the Engineer-in-Charge shall have the right to get this work done at the risk and cost of the contractor either departmentally or through another agency.  Before taking such action the Engineer-in-Charge shall give two days notice in writing to the contractor.

Clause 6 B: The contractor shall submit the completion plan required vide general specification for Electric works (Part 1 Internal 2005) and (Part 2 Ext. 1994) as applicable within 30 days of the completion of work.  In case the contractor fails to submit the completion plan as aforesaid he shall be liable to pay a sum equivalent to 1.0 % of the tendered cost of the work subject to a ceiling to Rs.25,000/-(Twenty Five Thousand only) as may be fixed by the Superintending Engineer (SE) concerned and in this respect the decision of the SE shall be final and binding on the contractor.

Clause 6 C :  The contractor of the work shall have to enter into a supplementary agreement with Executive Engineer immediately after the actual date of completion of work for items contained in Schedule ‘A’ of the contract.  The security deposit for the work of schedule A & B shall be deducted in accordance with the para of clause 6-C.

Clause 7: No payment shall be made for a work estimated to cost Rupees five thousand or less till after the whole of the work shall have been completed and certificate of completion given.  But in the case of work estimated to cost more than Rs. Five thousand the contractor shall on submitting the bill be entitled to receive a monthly payment proportionate to the part of work executed to the satisfaction of the Engineer-in-Charge whose certificate of the sum so payable shall be final or conclusive against the contractor.  

All such intermediate payments shall be regarded as payment by way of advanced against the final payment only and not as payment for work actually done and completed and shall not   preclude the requiring of bad, unsound and imperfect or unskilled work to be rejected, removed, taken away and reconstructed or  recreated or be considered as an admission of the due performance of the contract on any part thereof, in any respect or the acquiring of any claims, nor shall it conclude, determine or affect in any way the powers of the Engineer-in-Charge under this conditions or any of them as to the final settlement and adjustments of the accounts or otherwise or in any other way vary or affect the contract.  The final bill shall be submitted by the contractor within one month of the date fixed for completion of the work or of the date of the certificate of completion furnished by the Engineer-in-Charge and payment shall be made within three months, when amount of the contract plus that of additional items is up to Rs. 2 lacs and within six months, if the same exceeds Rs. 2 lacs, of the submission of such bill.  If there shall be any dispute about any item of the work than the undisputed item or items only shall be paid within the said period of three months or 6 months or as the case may be.  The contractor shall submit a list of the disputed items within thirty days from the disallowances thereof and if he fails to do this, his claim shall be deemed to have been fully waived and absolutely extinguished.


Whenever there is likely to be delay in recording detailed measurement for making running payment in the case of residential building, advance payment without detailed  measurement for works done (other than foundation and finishing items) up to (a) lintel level (including sunshade etc.) and (b) slab level for each floor, worked out at 75% of the assessed value may be made in running accounts bill by the Engineer-in-Charge in his discretion of the basis of certificate from the Assistant Engineer to the effect that the work has been completed up to the level in question.  The advance payment so allowed shall be adjusted in the subsequent running bill by taking detailed measurement there of final payment shall be made only on basis of detailed measurement.

Clause 8: A bill shall be submitted by the  contractor each month on or before the date fixed by the Engineer-in-Charge for all work executed in the previous month and the Engineer-in-Charge shall take or cause to be taken the requisite measurement for the purpose of having the same verified, and the claim as far as admissible adjusted as far as possible before the expiry of ten days from the presentation of the bill, if the contractor does not submit the bill within the time fixed as aforesaid, the Engineer-in-Charge may depute, with in seven days of the date fixed, as aforesaid, his subordinate to measure the said work in presence of the contractor whose counter signature to measurement list will be sufficient warrant and the Engineer-in-Charge may prepare a bill from such list.

Clause 8 A:  Before taking any measurements of any work as has been referred to in Clause 6, 7 & 8 thereof the Engineer-in-Charge or a subordinate deputed by him shall give reasonable notice to the contractor.  If the contractor fails to attend the measurement, after such notice or fails to countersign or to record the difference with in a week from the date of measurement in the manner required by the Engineer-in-Charge then in any such event the measurement taken by the Engineer-in-Charge or by a  subordinate deputed by him as the case may be shall be final and binding on the contractor and the contractor shall have no right to dispute the same.

Clause 9: The contractor shall submit all bills on the printed forms to be had on application from the office of the Engineer-in-Charge and the charges in the bills shall always be entered at rates specified in the tender or in the case of any extra work, ordered in pursuance of these conditions and not mentioned or provided for in the tendered, at the rates here in after provided for such work.

Clause 9 A: Payments due to the contractor may if so desired by him be made to his bank instead of direct to him provided that the contractor furnishes to Engineer-in-Charge (i) An authorization in the form of a legally valid documents such as a power of attorney conferring authority on the Bank, to receive payment and (ii) his own acceptance of the correctness of amount made out as being due to him by DDA or his signature on the bill or other claim preferred against DDA, before settlement by the Engineer-in-Charge of the account or claim by payment to the bank.  While the receipt given by such bank shall constitute a full and sufficient discharge for the payment, the contractor should whenever possible present his bill duly receipted and discharged through his bankers.  Nothing herein contained shall operate to create in favour of the bank, any right or equities vis-a-vis the authority.

Clause 10: Stores to be supplied by Delhi Development Authority.

If the specification or schedule of items provides for the use of any special description of materials to be supplied from Engineer-in-Charge stores or if it is required that the contractor shall use certain stores to be provided by the Engineer-in-Charge as shown in the schedule of materials here to annexed the contractor shall be bound to procure and shall be supplied such materials and stores, as are from time to time required to be used by him for the purpose of the contract only, and the value of the full quantity of materials and stores so supplied at the rates specified in the said schedule of materials may be set off or deducted from any sums then due, or there after to become due to contractor under the contract, or otherwise or against or from the security deposit, or the proceeds of the sale there of if the same is held in Govt. Securities, the same of sufficient portion thereof being in this cases sold for the purposes.  The contractor shall bear the cost of getting the material issued, loading, transporting to site, unloading storing as required cutting, assembly and joining the several parts together as necessary.  Not withstanding any thing to the contrary contained.  If in any other clause of the contract and (or the CPWD Code, all stores / Materials so supplied to the contractor or procured with the assistance of the Delhi Development Authority, shall remain the absolute property of Delhi Development Authority and the contractor shall be trustee of the store / materials and the said store / materials shall not be removed / disposed off from the site of the work on any account and shall be at all times open to the inspection by the Engineer-In-Charge, any such stores / materials remaining unused shall be returned to the Engineer-in-Charge at a place directed by him if by a notice he shall so require, but in case it is decided not to take back the stores / materials the contractor shall have no claim for compensation on any account of such stores / materials so supplied to him as aforesaid and not used by him or for any wastage in or damage to in such stores / materials.


On being required to return the stores / materials the contractor shall hand over the stores / materials on being paid or credited such price as the Engineer-in-Charge shall determine, having due regard to the condition of the stores / materials.  The price allowed to the contractor, however shall not exceed the amount charged to him excluding the storage charge if any. The decision of the Engineer-In-Charge shall be final and conclusive.  In the event of breach of the aforesaid condition the contractor shall in addition to throwing himself to open to account of contravention of the terms of the licences or permit and / or criminal breach of trust be liable to Delhi Development Authority for all advantages of profits resulting or which in the usual course would having resulting or which in the usual course would having resulted to him by reason of such breach.  Provided that the contractor shall in no case be entitled to any compensation or damage on the account of the delay in supply or non-supply there of all or any such materials and stores.  Provided further that the contractor shall be bound to execute the entire work if the materials are supplied by the DDA with in the schedule time for the completion of the work plus 50% there of (Schedule time plus 6 months if the time of the completion exceed 12 months) but if a part only of the materials has been supplied with in the aforesaid period then the contractor shall be bound to do so much of the work as may be possible with the materials and the stores supplied in the aforesaid period for the completion of the rest of the work contractor shall be entitled to such extension of the times as may be determined by the Engineer-in-Charge whose decision in this regard shall be final.

Clause 10 A: The Engineer-in-Charge shall have full powers to require the removal from the premises of all materials which in his opinion are not in accordance with the specifications and in case of default, the Engineer-in-Charge shall be at liberty to employ at the expense of the contractor, other persons to remove the same without being answerable or accountable for any loss or damage that may happen or arise to such materials.  The Engineer-in-Charge shall also have full power to require other proper material to be substituted there of and in case of default the Engineer-in-Charge may cause the same to be supplied and all costs which may arise due to such removal and substitution shall be borne by the contractor

Clause 10 B (i) :
The contractor on signing an indenture in the form to be specified by the Engineer-in-Charge shall be entitled to be paid during the progress of the execution the work up to 75% of estimated value of any materials which are in opinion of the Engineer-in-Charge non-perishable, non-fragile and non-combustible  and are in accordance with the contract and which have been brought on the site in connection, therewith and are adequately stored and protected against damage by weather or other causes but which have not at the time of advance been incorporated in the works. When materials on account of which an advance has been made under this sub clause   are incorporated in the work, the amount of such advance shall be deducted from the next payment made under any of the clause or clauses of this contract. Such secured advance shall also be payable on other items of perishable nature, fragile and combustible with the approval of the Engineer-in-Charge provided the contractor provides a comprehensive insurance cover for the full cost of such materials.  The decision of the Engineer-in-Charge shall be final and binding on the contractor in this matter.  No secure advance shall however, be paid on high risk materials such as ordinary glass, sand, petrol, diesel etc.

Clause 10 B(ii) : Mobilization advance not exceeding 10% of the tendered value or estimated cost put to tender or Rs.1.00 crore which ever is less may be given, if requested by the contractor in writing within one month of the order to commence the work.  In such a case, the contractor shall execute a bank guarantee bond from a scheduled nationalized bank as specified by the Engineer-in-Charge for the full amount of such advance before it is released.  Such advance shall be in two or more installments to be determined by the Engineer-in-Charge in his absolute discretion.  The first installment of such advance shall be released by the Engineer-in-Charge to the contractor on a request made by the contractor to the Engineer-in-Charge in this behalf. The second and subsequent instalment shall be released by the Engineer-in-Charge only after the contractor furnishes a proof of the satisfactory utilization of the earlier instalments to the entire satisfaction of the Engineer-in-Charge. Mobilization advance shall be admissible only for works where estimated cost put to tender is Rupees Two Crores and above.

Clause 10 B (iii) : An advance for Plant and Machinery required for the work and brought to site by the Contractor may be given if requested by the Contractor in writing within one month of bringing such Plant and Machinery to site.  Such advance shall be given on such Plant and Machinery, which in the opinion of the Engineer-in-Charge will add to the expeditious execution of work and improve the quality of the work. The amount of advance shall be restricted to 5% of tendered value.  In the case of new Plant and equipment to be purchased for the work, the advance shall be restricted to 90% of the price of such new Plant and equipment paid by the contractor for which the contractor shall produce evidence satisfactory to the Engineer-in-Charge.  No such advance shall be paid on any Plant and equipment of perishable nature and on any Plant and equipment of a value less than Rs.50,000/-.  Seventy five percent of such amount of advance shall be paid after the Plant and equipment is brought to site and balance twenty five percent on successfully commissioning of the same.

This advance shall further be subject to the conditions that such Plant and equipment (a) Are considered by the Engineer-in-Charge to be necessary for the work. (b)
and are in  and  are maintained in working order (c) hypothecated to the DDA as specified by the Engineer-in-Charge  before the payment of advance is released.  The Contractor shall not be permitted to remove from the site such hypothecated Plant and equipment without the prior written permission of the Engineer-in-Charge.  The Contractor shall be responsible for maintaining such Plant and equipment in good working order during the entire period of hypothecation failing which such advance shall be entirely recovered in lump sum. 


The Contractor shall insure the Plant and Machinery for which mobilization advance is sought and given, for a sum sufficient to provide for their replacement at site.  Any amount not recovered from the insurer will be borne by the Contractor.

Clause 10 B (iv) : The mobilization advance and Plant and Machinery advance in (ii) and (iii)  above bear simple interest at the rate of 10% per annum and shall be calculated from the date of payment to the date of recovery, both days inclusive, on the outstanding amount of advance.  Recovery of such sums advanced shall be made by the deduction from the Contractor’s bill commencing after first ten per cent of the gross value of the work is executed and paid, on pro rata percentage basis to the gross value of the work billed beyond 10% in such a way that the entire advance is recovered by the time 80% of the gross value of the Contract is executed and paid, together with interest due on the entire outstanding amount up to the date of recovery of the instalment.

Clause 10B(v) : If the circumstance are considered reasonable by the Engineer-in-Charge the period mentioned in (ii) and (iii) on request by the Contractor in writing for grant of mobilization advance and Plant and equipment advance may be extended in the discretion of the Engineer-in-Charge.

Clause 19B(vi)  :  The said bank guarantee for advances shall initially be made for the full amount and valid for the Contract period, and be kept renewed from time to time to cover the balance amount and likely period of complete recovery together with interest.





Clause 10 C: Deleted  

Clause 10 CA: Deleted

Clause 10 CC : Deleted
Clause 10 D :  The Contractor shall treat all materials obtained during dismantling of a structure, excavation of the site for a work etc. as DDA’s property and such materials shall be disposed off to the best advantage of DDA according to the instructions in writing issued by the Engineer-in-Charge

Clause 10 E : Cement shall be supplied by the department in HDPE or Guny bags containing of 50 Kg. of cement in each bags and shall be available in multiple of 50 Kg. bags.  The recovery rate of cement is inclusive of cost of Jute or paper bags or HDPE bags.

Clause 10 F :  In case, the empty cemen bags are required by DDA or bonafied use in work, the executive Engineer-in-charge of work shall have the power to collect the bags himself and the contractor shall have to return desired number of empty jute poly bags in sereviceable condition to him on the same condition and as per prevailing rates of DGS & D for bag collecting agents.

Clause 11: Work to be executed in accordance with Specifications, Drawings, Orders etc.

The Contractor shall execute the whole and every part of the work in the most substantial and workman like manner and both as regards materials and otherwise in every respect in strict accordance with the Specifications. The Contractor shall also conform exactly, fully and faithfully to the designs, drawings and instructions in writing in respect of the work signed by the Engineer-in-Charge and the Contractor shall be furnished free of charge one copy of the Contract documents together  with Specifications and of all such design drawing and instructions as are not included in the Central Public Works Department compilation entitled CPWD Specification for work at Delhi 1996 volume 1 to VI with upto dte correction slips with any and revised CPWD specifications 2002 for cement mortar, cement concrete & R.C.C. works other printed publication on general Specification referred to else where in the contract or (CPWD General specification to Electrical works Part-I (Int). 2005 and Part-II (Ext.) 1994 with uptodate correction slips). 
Clause 12: Alteration on Specification and Drawing.

The Engineer-in-Charge shall have power to make any alteration in, omission from, addition to or substitution for the original specifications drawings and instructions that may appear to him to be necessary or advisable during the progress of the work and omit a part of the work in case of non availability of a portion of the site or for any other reason and the  Contractor shall be bound to carry out the work in accordance with any instruction which may be given to him in writing signed by the Engineer-in-Charge and such alterations, omission, additions or substitutions shall not invalidate the Contract and any altered, additional, substituted work, which the Contractors may be directed to do in the manner above specified, as part of the work, shall be carried out by the Contractor on the same conditions in all respects on which he agreed to do the main work. The time for the completion of the work shall be extended in the proportion that the altered, additional or substituted work bears to the original Contracts work and certified by the Engineer-in-Charge shall be conclusive as to such proportion. Over and above this, a further period to the extent of 25% of such extension so extended shall be allowed to the Contractor. The rates for such additional, altered or substituted work under this Clause shall be worked out in accordance with the following provisions in their respective order:-  

(i) If the rates for additional, altered or substituted work are specified in the Contract for the Work, the Contractor is bound to carry out the additional, altered or substituted work at the same rates as are specified in the Contract for the work.

(ii) If the rates for the altered, additional or substituted work are not specifically provided in the Contract for the work. The rates will be derived from the rates for a similar class of work as are specified in the Contract for the work.

(iii) If the rates for altered, additional or substituted work includes any work for which no rate is specified in the Contract or the rate can not be derived from the similar class of work in the Contract, then such work shall be carried out at the rates entered in the current CPWD Schedule of Rates for Delhi 2007 with Correction Slips up to the date of receipt of tender plus/ minus percentage which the total tendered amount bears to the Estimated Cost of the entire work put to tender or CPWD Schedule of rates Pt. I (Int) 2005 and Part-II(ext.) 1995 electrical works with upto date correction slips.

(iv) If the rates for the altered, additional or substituted work cannot be determined in the manner specified in sub-clause (i), (ii) & (iii) above then rates for such shall be worked out on the basis of the current C.P.W.D. Schedule of Rates for Delhi 2007 with upto date correction slips up to the date of receipt of tenders plus/ minus percentage which the total tendered amount bears to the Estimated Cost of the entire work put to tender.  Provided always that if the rate for a particular part or parts of the items is not in the schedule of rates for such parts or part will be determined by the Engineer-in-Charge on the basis of prevailing market rates when the work was done. 


(v)
If the rates for any altered, additional or substituted item of work cannot be determined in the manner specified in Sub-clause (i) to (iv) above, then the Contractor shall, within seven days from the date  of receipt of the order to carry out the said work, inform   the Engineer-in-Charge of the rate which he proposed to claim for such item  of work, supported by the 
analysis of the rate claimed, and the Engineer-in-Charge shall within three months thereafter, after giving due consideration to the rates claimed by the Contractor, determine the rate on the basis of prevailing market rates and pay the Contractor accordingly.  However, the Engineer-in-Charge by giving notice in writing will be at liberty to cancel his order to carry out such class of work and arrange to carry it out in such manner as he may consider advisable, but under no circumstances the Contractor shall suspend the work on the plea of non-settlement of rate of items falling under the clause.

(vi)
Except in case of items relating to foundations, provisions contained in sub-clause (i) to (v) above shall not apply to Contract or substituted items as individually exceed the percentage set out in the tender 
documents (referred to herein below as deviation limit) subject to the following restrictions: 

(a) The deviation limit referred to above is the net effect (algebraic sum) of all additions and deduction ordered.

(b) In no case shall the addition/deductions (arithmetical Sum) exceed twice the deviation limit.

(c) The deviation ordered on items of any individual trade included in the Contract shall not exceed plus/minus 50% of the value of that trade in the Contract as a whole or half the deviation limit: whichever is less.

(d) The value of additional items, of any individual trade not already included in the Contract, shall not exceed 10% of the deviation limit.

vii)
For the purpose of operation of clause 12 (vi) the following work shall be treated as work relating to foundations.

(a) For building Plinth level or 1.2 meters above ground level whichever is lower excluding items of flooring and DPC but including base concrete below the floor.

(b) For abutment, piers, retaining walls or culverts and bridges, walls of water reservoirs: The bed of floors level

(c) For retaining walls where floor level is not determinate: 1.2 meters above the average ground level or bed level.

(d) For roads: All items of excavations and filling including treatment of sub base and soling work.

(e) For water supply lines, sewer lines, underground storm water drains and similar works: All items of work below ground level except items of pipe work and masonry work.

(f) For open storm water drains: All items of work below ground level except item of pipe work except lining of drains. 


Note : Individual trade means the trade sections into which schedule of quantities annexed to the Agreement has been divided or in the absence of any such divisions the individual sections of the CPWD.  Schedule of Rates specified above such as earthwork concrete work, woodwork etc. The rates of any such work except the items relating to foundation which is in excess of the deviations limits shall be determined in accordance with the provisions contained in clause 12 A.

Clause 12 A: In the case of Contract items, substituted items or additional items which result in exceeding the limits laid down in sub-clause (vi) of clause 12 except the items relating to foundation work which the Contractor is required to do under clause 12 above the Contractor shall within 7 days from the receipt of order claim revision of the rates supported by proper analysis in respect of such items for quantities in excess of the deviation limit notwithstanding the fact that the rates for such items exist in the tender for the main work or can be derived in accordance with the provisions of clause 12 and Engineer-in-Charge may revise their rates having regard to the prevailing market rates and the Contractor shall be paid in accordance with the rates so fixed. The Engineer-in-Charge shall however, be at liberty to cancel his order to carry out such increased quantities of work by giving notice in writing to the Contractor and arrange to carry it out in such a manner as he may consider advisable but under no circumstance the Contractor shall suspend the work on the plea of non-settlement of rates of items falling under this clause. 

All the provisions of the preceding paragraph shall equally apply to the decrease in the rates of items or quantities in excess of the deviation limit notwithstanding the fact that the rates for such items exist in the tender for the main work or can be derived in accordance with the provisions of the preceding Clause 12, and the Engineer-in-Charge may revise such rates having regards to the prevailing market rates.

Clause 13:

If at any time after the commencement of the work the Authority shall for any reason whatsoever not require the whole work or part of work thereof, as specified in the tender, to be carried  out, the Engineer-in-Charge shall give notice in writing of the fact to the Contractor who shall have no claim to any payment to compensation   whatsoever on account of any profit or advantage which he might have derived from the execution of the work in full but which he did not derive in consequence of the full amount of the work not having been carried out neither shall he have any claim for compensation by reason of any alteration having been made in the Original Specifications, drawings, designs and instructions which shall involve any curtailment of the work as originally contemplated. Provided that the Contractor shall be paid the charges on the cartage only of materials actually and bonafiedly brought to the site of the work and had rendered surplus as a result of the abandonment or curtailment of the work or  any portion thereof and then taken back by the Contractor. Provided, however, that the Engineer-in-Charge shall have in all such cases, the option of taking over all or any such material at their purchase price or at local current rates, whichever may be less.   In the case of such stores having been issued from DDA Stores and returned by  the Contractor to DDA Stores, credit shall be given to him by the Engineer-in-Charge at the rates not exceeding those at which they where originally issued to him after taking into consideration and deduction for claim on account of any deterioration or damage while in the custody of the Contractor and in this respect the decision of the Engineer-in-Charge shall be final.

Clause 14: If it shall appear to the Engineer-in-Charge or his authorized subordinate-in-charge of the work, Chief-Engineer, Superintending Engineer, Chief Technical Examiner/Technical Examiner of Central Vigilance commission & Chief Engineer Quality / Assurance Cell DDA or by an Officer of the vigilance of the Authority, that any work has been executed with unsound, imperfect or unskillful workmanship or with materials of any inferior description or that any materials or articles provided by him for the execution for the work are unsound or of quality inferior to that contracted for, otherwise or not in accordance with the contract, the contractor shall on demand in writing, which shall be made within six months of the completion of the work, from the Engineer-in-Charge specifying the work, materials or articles complained of, notwithstanding that the same may have been passed, certified and paid for, will rectify or remove and reconstruct the work so specified in whole or in part as the case may require or as the case may be, remove the material or article so specified and provide other proper suitable material or articles at his own  charge and   cost and in the event of his failing to do so within a period to be specified by the Engineer-in-Charge in  his demand aforesaid, then the Contractor shall be liable to pay compensation at the rate of one percent on the estimated amount put to tender for every day not exceeding ten days while his failure to do shall continue and in the case of any such failure, the Engineer-in-Charge may rectify or remove and re-execute the work or remove and replace with others, the materials, or articles complained, as  the case may be at the risk and expense in all respects of the Contractor. 

Clause 15: All work under or in course of execution or pursuance of the Contract shall at all times be open to the inspection and supervision of the Engineer-in-Charge and his authorized subordinates and the Central Vigilance Commission or by the Chief Engineer Quality Assurance Cell/ DDA or his authorized subordinate officer, and the Contractor shall at all times during the usual working hours and at all others times for which reasonable notice of the intention of the Engineer-in-Charge or authorized representative to visit the works has been given,  the Contractor either himself be present to receive the orders and instructions or have a responsible agent duly accredited in writing present for that purpose. Orders given to the Contractor’s agent shall be considered to have the same force as if they had been given to the Contractor himself.  The work during its progress can also be inspected by the Chief Technical Examiner / Technical Examiner of the Central Vigilance Commission or by Chief Engineer (QAC) DDA or by an officer of the Vigilance Cell of the Authority on behalf of the Engineer-in-Charge or any official of higher level, commissioner  or any officer of higher cell.

Clause 16: Contractor shall give not less than seven days’ notice, in writing to Engineer-in-Charge or his authorized subordinate in charge of the work, before covering up or otherwise placing beyond the reach of measurement any work in order that the same may be measured and correct dimension there of be taken before the same is so covered up or placed beyond the reach of measurement and shall not cover up any work without the consent in writing of the Engineer-in-Charge or his authorized subordinate in charge of the work.  The Engineer-in-Charge or his authorized subordinate- in-charge of work shall within the aforesaid period of seven days inspect the work, and if any work shall be covered or placed beyond the reach of measurement without such notice having been given to the Engineer-in-Charge, consent being obtained the same shall be uncovered at the Contractor’s expense or in default there of no payment or allowance shall be made for such work or the materials with which the same was executed. 

Clause 17: Contractor liable for Damages done and for imperfections noticed during maintenance period.

If the Contractor or his working people or servants shall break, deface injure or destroy any part of building in which they may be working or any building, road, road kerb, fence, enclosure, water pipe, cables, drains, Electric or Telephone post or wires, trees, grass or grassland, or cultivated ground contiguous to the premises on which the work or any part of it is being executed, or if any damage shall happen to the work while in progress from any cause whatever or if any defect, shrinkage or other faults appear in the work within 12 months (6 months in case of any work other than road work costing Rs.10,00,000/- and below) after a certificate final or otherwise of its completion shall have been given by the Engineer-in-Charge as aforesaid arising out of defective or improper materials or workmanship the Contractor shall upon receipt of a notice in the writing on that behalf make the same good at his own expense or in default, the Engineer-in-Charge cause the same to be made good by other workmen and deduct the expense from any sums that may be due or at any time thereafter may become due to the Contractor,  or from his Security Deposit (except for the portion pertaining to asphaltic work which is governed by sub-para(iii) of clause 35) or the proceeds of sale thereof  of a sufficient portion thereof. The Security Deposit of the Contractor (except the portion pertaining to asphaltic work which is governed by sub-para (iii) of clause 35) shall not be refunded before the expiry of twelve months (Six months in case of any work other then road work costing Rs.10 Lac and below) after the issue of the certificate final or otherwise, of completion of work or after the final bill has been prepared and passed whichever is later. 
Clause 17 A:  Provided that in the case of road work if in the opinion of the Engineer-in-Charge, half of the Security Deposit is sufficient to meet all the liabilities of contractor under this contract, half of the Security Deposit will be refundable after six months and the remaining half after twelve months of the issue of the said certificate of completion or after the Final bill has been prepared and passed whichever is later.

Clause 17B:  Provided further that for defects relating to leakage from the roof, the Contractor shall be responsible for rectification of the same within a period of one year or two rainy seasons (ending October) whichever is later, after the physical date of completion of the work as a whole to be recorded by the Department and 10% of the Security Deposit of the Contractor will be refunded after expiry of the above period.  

Clause 18:  The Contractor shall provide at his own cost all materials (except such materials, if any as may in accordance with the Contract be supplied from the Engineer-in-Charge stores) Plant, tools, appliances, implements, ladders, cordage, tackle, scaffolding and temporary works required for the proper execution of the work, whether original, altered or substituted and whether included in the specification or other documents forming part of the Contract or referred to in these conditions or not, or which may be necessary for the purpose of satisfying or complying with the requirements of the Engineer-in-Charge as to any matter as to which under these conditions he is entitled to be satisfied or which is entitled to require together with carriage thereof to and from the work. The Contractor shall also supply without charge the requisite number of persons with the means and materials necessary for the purpose of setting out work and counting, weighing and assisting the measurement for examination at any time and from time to time of the work or materials. Failing his so doing the same may be provided by the Engineer-in-Charge at the expenses of the Contractor and expanses may be deducted from any money due to the Contractor or otherwise and/or from his Security Deposit or the proceeds of sale thereof of a sufficient portion thereof.

Clause 18 A:  In every case in which by virtue of the provisions of section 12 sub-section (i) of the workman’s compensation Act 1923 DDA is obliged to pay compensation to a workman employed by the Contractor, in  execution of the works, DDA will recover from the Contractor the amount of the compensation so paid, and without prejudice to the rights of DDA under section 12 sub-section (ii) of the said Act DDA shall be at liberty to recover such amount or any part thereof, by deducting it from the Security Deposit or from any sum due by DDA to the Contractor whether under this Contract or otherwise. DDA shall not be bound to contest any claim made against it under section 12 sub-section (i) of the said Act, except on the written request of the Contractor and upon his giving to DDA full security for all cost for which DDA might become liable in consequence of contesting such claim. 

Clause 18 B:  In every case which by virtue of the provisions of the Contract labour (Regulation & Abolition) Act, 1970 and of the Contract Labour (Regulation & Abolition) Central Rules 1971, DDA is obliged to pay any amounts of wages to a workman employed by the Contractor in the execution of the works, or to incur any expenditure in providing welfare and health amenities required to be provided under the above said Act and the rules under clause 19-H or under the DDA Contractor’s Labour Regulations, or under the rules framed by the government from time to time for protection of health and sanitary arrangements for workers employed by DDA Contractors, DDA will recover from the Contractor the amount of wages so paid or the amount of expenditure so incurred and without prejudice to the rights of the DDA under section 20. Sub-section (2) and Section (21), Sub-section (4) of the Contract Labour (Regulation &Abolition) Act, 1970, DDA shall be at liberty to recover such amount or any part thereof by deducting it from the Security Deposit or from any sum due by DDA to the Contractor, whether under this Contract or otherwise, DDA shall not be bound to contest any claim made against it under section 20, sub-section (i) and Section 21, Sub Section (4) of the said act, except on the written request of the contractor and upon his giving to the DDA full security for all cost for which DDA right become liable in contesting such claim.
Clause 19: The Contractor shall obtain license under the Contract Labour (R&A), Act 1970, and the Contract Labour (Regulation & Abolition) Central Rules 1971, before the commencement of the work and continue to have a valid license until the completion of the work any failure of fulfil his requirement shall attract the Penal provision of this contract arising out of the retirement non executive of the work.
Clause 19 A: No Labour below the age of Eighteen Years shall be employed on the work 

Clause 19 B: Payment of wages to labour 

(a) The Contractor shall pay not less than fair wages to labourers engaged by him on the work.

Explanation: “Fair Wages” means wages, whether for time or piece work, notified at the time of inviting tenders for the work, where such wages have not been so notified the wages prescribed by the D.D.A. for the district in which the work is done it will be notified/prescribed by D.D.A. in consultation with the officers of the Industrial Relation Machinery located in the respective areas and will not be less than the minimum rates of the wages fixed by the Govt. of N.C.T.  Delhi for that class of employee engaged on the same type of the work in the same area. 

(b) The Contractor shall, notwithstanding the provisions of any Contract to the contrary, cause to be paid fair Wages to labourers indirectly engaged on the work, including any labour engaged by his sub-Contractors in connection with said work, as if the labourer had been immediately employed by him.

(c) In respect of all labour directly or indirectly employed in the works for performance of the Contractor’s part of this Contract, the Contractor shall comply with or cause to be complied with the D.D.A. Contractor’s labour regulations made by the Govt. of N.C.T.  Delhi  from time to time  payment of wages, period of deductions from wages, recovery of wages not paid and deductions unauthorized made, maintenance of wage books or wage slip, publication of scale of wages and other items of employment inspection 
and submission of periodical returns and all other matters of the like nature or as per the provisions of the Contract labour (Regulation and Abolition) Act 1970 and Contract labour (Regulation & Abolition) central rules, 1971, whichever is applicable. 

(d) The Engineer-in-Charge concerned shall have right to deduct from the money due to the Contractor any sum required or estimated to be required for making good the loss suffered by a worker or workers by reason of non-fulfillment of the conditions of the Contract for the benefit of the workers, non-payment of wages or of deductions made from his / their wages which are not justified by the terms of the Contract or non-observance of the Regulations.

(e) Under the provision of the Minimum Wages Act 1948 and the Minimum Wages (Central) Rule 1950, the Contractor is bound to allow or cause to be allowed to the labourers directly employed in the works one day rest for six days continuous work and pay wages at the same rate as for duty. In the event of default the Engineer-in-Charge shall have the right to deduct the sum or sums not paid on account of wages for weekly holidays to any labourers and pay the same to the persons entitled thereto from any money due to the Contractor by the Engineer-in-Charge concerned, in the case of the N.C.T. of Delhi, however as the all inclusive minimum daily wages fixed under Delhi Government Notification.   And plus uptoate variation and wages allowance applicable for minimum wages for cost index circulated by GNCTD from time to time.
(f) Vis-à-vis the DDA and the Contractor shall be primarily liable to all payment to be made under and for the observance of the Regulation aforesaid without prejudice to his right to claim indemnity from sub contractors. 
(g) The regulation aforesaid shall be deemed to be a part of this Contract and any breach thereof shall be deemed to be a breach of this Contract. 

Clause 19 C: In respect of all labour directly or indirectly employed in the work for the performance of the Contractor’s part of this Contract, the Contractor shall at his own  expense arrange for the safety provision as per Safety Code framed from time to time and shall at his own expense provide for all facilities in connection therewith.  In case the Contractor fails to make arrangement and does not provide necessary facilities as aforesaid he shall be liable to pay a penalty of Rs.200/- for each default and in addition the Engineer-in-Charge shall be at liberty to make arrangement and provide facilities as aforesaid and recover the costs, incurred in that on behalf of the Contractor.

Clause 19 D: The Contractor shall by the 4th and 19th of every month, submit to the Engineer-in-Charge, a true Statement showing, in respect of the second half of the preceding month and the first of the current month respectively:- 

1. The number of labourers employed by him on the work,

2. Their working hours, 

3. The wages paid to them,

4. The accidents that occurred during the said fortnight showing the circumstances under which they happened and the extent of damage and injury caused by them and.

5. The number of female workers who have been allowed Maternity Benefit according to clause – 19F and the amount paid to them failing which the Contractor shall be liable to pay to D.D.A. sum not exceeding Rs. 50/- for each default or materially incorrect statement. The decision of the Divisional Officer shall be final in deducting from any bill due to the Contractor and the amount levied as fine shall be binding on the Contractor.

Clause 19 E: In respect of all labourers directly or indirectly employed in the works for the performance of the Contractor’s part of this Agreement, the Contractor shall comply with or cause to be complied with all rules by Government from time to time, for the protection of health and sanitary arrangement for workers employed by the DDA and its Contractors.

Clause 19 F: 
Leave and pay during leave shall be regulated as follows:  

1. Leave
    
(i) 
In the case of delivery, maternity leave not exceeding 8 weeks, 4 weeks up to 
and including the day of delivery and four weeks following that day
   
(ii)   
In case of miscarriage –up to three weeks from the date of miscarriage.

2.
Pay 

    
(i) 
In case of delivery – leave pay during maternity leave will be at the rate of the women’s average daily earnings, calculated on total wages earned on the days when full time work was done during a period of three months immediately preceding the date on which she given notice that she expects to 
be confined or, at the rate of rupee one only per day whichever is greater. 

 
(ii)
In case of miscarriage - leave pay at the rate of average daily earning calculated on the total wages earned on the days when full time work was done (during a period of 3 months immediately preceding the date of such miscarriage.

3.
Conditions for the grant of maternity leave: No maternity leave benefit shall be admissible to a woman unless she has been employed for a total period of not less than Six months immediately preceding the date on which she proceeds on leave. 

4.
The Contractor shall maintain a register of maternity (benefit) in the prescribed form as shown below and the same shall be kept at the place of work.

Register of Maternity Benefit
Name and address of the Contractor(s) 

Name and location of work,

Name of      Father’s/ Husband’s         Nature of            Period of Actual    Date on which notice 


Employee
Name                   Employment           Appointment        of Confinement given

(1)                            (2)


(3)
   ( 4)


(5)

Date on which maternity leave commenced and ended

Date of Delivery/   In case of Delivery
    In case of miscarriage
       

    Miscarriage          Commenced    Ended
    Commenced    Ended         

        (6)
(7)             (8)                 (9)                (10)

Leave pay paid to the Employee


In case of Delivery                              In case of Miscarriage 


Rate of leave pay    Amount paid     Rate of leave pay    Amount paid   

        
      (11)
           (12)                      (13)                         (14)               )
Specimen form of the Register regarding maternity benefit 

admissible to Contractor’s labour in DDA work.

1. Name of the work .............................. Name of Contractor ..................................... 

2. Name of the woman and her husband’s name ..................................... ................

3. Designation .......................... .4.  Date of appointment................ ........................

5.
Date with Month & Year in which she is employed ................
.......................... ....

6.
Date of discharge/dismissal, if any ..................... ..................................... ..............

7.
Date of production of certificate in respect of pregnancy.......................... ......... ...

8.
Date on which woman informs about expected delivery....... .......................... .......

9.
Date of delivery/miscarriage/death .................... ..................................... .............

10.
Date of production of certificate in respect of
delivery/miscarriage.......................

11.
Date with the amount of maternity/death, death benefit, if paid in advance of expected 
delivery..................................... ...............................

12.
Date with the amount of subsequent payment of maternity benefit...................... ...

13.
The name of the person nominated by the women to receive the payment of the 
maternity 
benefit after her death .......................... ............................. .....................

14.
If woman dies, the date of her death, the person to whom Maternity benefit amount was paid, the 
month thereof and the date of payment. .......................... .... 


15.
Signature of the Contractor authenticating entries in the register .......................... .

16.
Remarks column for the use of inspecting officer .......................... .....................

Clause 19G: MODEL RULES 

In the event of the Contractor(s) committing a default or breach of any of the Provisions of the DDA Contractor’s labour Regulation and Model Rules for Protection of Health and sanitary arrangements for workers as amended form time to time or furnishing any information or submitting or filing any statement under the provisions of the above Regulations and Rules which is materially incorrect, he/they shall without prejudice to any other liability, pay to the Delhi Development. Authority a sum not exceeding Rs.50/-per day for each day, default, breach or furnishing, making, submitting, filing such material incorrect statements and in the event of the Contractor(s) defaulting continuously in this respect, the penalty may be enhanced to Rs.50/- per day for each day of default subject to a maximum of five percent of the Estimated Cost of the work put to Tender. The decision of the Engineer-in-Charge shall be final and binding on the parties. 

Should it appear to the Engineer-in-Charge that the Contractor is not properly observing and complying with the provisions of DDA. Contractor’s Labour Regulations and model rules and the provisions of the Contract (Labour Regulation & Abolition) Act 1970, and the Contract labour (Regulation & abolition) Central Rules 1971, for the protection of health and sanitary arrangements for work people employed by the Contractor, hereinafter referred a “The said Rules”, the Engineer-in-Charge shall have power to give notice in writing to the Contractor (s) requiring that the said rules be complied with and the amenities prescribed therein be provided to the work people within a reasonable time, to be specified in the notice. If the Contractor(s) fail within the period specified in the notice to comply with and/observe the said rules and to provides the amenities to work people as aforesaid, the Engineer-in-Charge shall have the power to provide the amenities herein before mentioned at the cost of the Contractors(s).  The Contractor (s) shall construct, make and maintain at his/their own expenses and according to approved standards all necessary huts and sanitary arrangement required at for his/their work people on the site in connection with the execution of the works, and if the same shall not have been erected or constructed according to approved standards, the Engineer-in-Charge shall have powers to give notice in writing to the Contractor’s requiring that the said huts and sanitary arrangements be remodeled and/or reconstructed according to approved standards, and if the Contractors  fails to remodel or reconstruct such huts and sanitary arrangement according to approved standards within the  period specified in the notice, the Engineer-in-Charge shall have the power to remodel such huts and sanitary arrangements, according to approved standards at the cost of the Contractor(s).

Construction of labour huts near work sites shall be avoided as far as possible. Whenever labour huts are constructed the Engineer-in-Charge will prepare a plan of the area to be occupied by the labour of the construction agency reflecting thereupon the huts to be constructed. The Engineer-in-Charge shall obtain an undertaking from the Contractor that the site of the labour huts shall be cleared of the labour huts after the work has completed in the following Performa.

I/We hereby undertake that.

1. Full site free from any encroachment has been handed over to me/ us on....................
2. The labour huts.................... in nos. constructed by me/us at site as shown on the site plan and duly signed by me/us, belong to me/us. These shall be removed from the site before the completion of the work. In case of failure to do so the Department can get the same removed at my risk and cost.  The Contract bill shall not be finalized till the Engineer-in-Charge gives a certificate that the area occupied by the labour of the Contractor has been cleared/vacated by the contractor.
Clause 19H:  The Contractor (s) shall at his/their own cost provide his/their labour with a sufficient number of huts (herein after referred to as the camp) of the following specifications on a suitable plot of land to be approved by the Engineer-in-Charge.

1
(a)
The minimum height of each hut shall be 2.10 m and the floor area to be provided  @.2.7sqm for each member of the worker’s family staying with labourer.
(b) The Contractor(s) shall in addition construct suitable cooking place having minimum area of (1.8m x1.5m) or (6 feet x 5 feet) adjacent to the hut for each family.

(c) The Contractor(s) shall also construct temporary Latrines and Urinals for the use of the labour each at the scale of not less than four pan for each one hundred of the total strength. Separate latrines and Urinals shall be provided for women.
(d) The Contractor(s) shall also construct sufficient number of bathing & washing places, one unit for every 25 persons residing in the camp. Theses bathing & washing places shall be suitable screened.
(e) The contractor shll provide hut with proper ventilation at door, windows and ventilators shall be provided with suitable levels for ecurity purpose.
2.
(a)
The floor of huts shall be in bricks and shall be at least 6 above the surrounding ground. The roof of the huts shall be of canvas cloth (water proof) as may be approved by the Engineer-in-Charge and the Contractor shall ensure that throughout the period of their occupation the huts remain water tight.


(b)
There shall be kept an open space of at least 8 yards (7.2m) between the rows of Tentgs which may be reduced to 20 ft. (6m) according to the availability of site with the approval of the Engineer-in-Charge. Back to back construction will be allowed.   The contractor shall provide ventilation window for ventilation with lock and key for security arrangement.
3.
Water Supply: 
The Contractor shall provide adequate supply of water for the use of labourers. Provisions shall not be less than two gallons of pure and wholesome water per head per day for drinking purpose and three gallons of clean water per head per day for bathing & washing purposes. Where piped water supply is available supply shall be at stand posts and where the supply is from wells or river, tanks, which may be of metal or masonry, shall be provided. The Contractor (s) shall also at his/their cost make arrangement for laying pipe lines for  supply to his/their labour camp from the existing mains wherever available and shall pay all fees and charges thereof.

4.
The site selected for the camp shall be on high ground, removed from jungle.

5.

Disposal of Excreta: 



The Contractor (s) shall make necessary arrangement for the disposal of excreta from latrines by trenching or incineration which shall be according to the requirements laid down by local Health Authority. If trenching or incineration is not allowed the Contractor(s) shall make arrangement for the removal of the excreta through the Municipal Committee/Authority and inform it, the number of labourers employed so that arrangements may made by such Committee / Authority for the removal of the excreta. All charge on this account shall, be borne by the Contractor and paid directly by him to the Municipality / Authority. The Contractor shall provide one sweeper for every 8 seats in case of dry system.

6.
Drainage: The Contractor shall provide efficient arrangement for draining away sullage water so as to keep the camp neat and tidy. 
7.
The Contractor shall make necessary arrangement for keeping the camp area sufficiently lighted to avoid accident to the workers.                                               

8.
Sanitation: 


The Contractor(s) shall make arrangement for conservancy and sanitation in the labour camps accordingly to the rule of the Local Public Health and Medical Authorities. 




9.
Wherever electric connection from NDPL/BSES is readily available the Contractor would provide sufficient street-lights for the labour camp as per directions of the Engineer-in-Charge. 

Clause 19 I: The Engineer–In-Charge may require the Contractor  to dismiss or remove from the site of the work any person or persons in the Contractor (s) employment on the work who may be incompetent or misconduct himself and the Contractor shall forth with comply with such requirements.  

Clause 19 J: It shall be the responsibility of the Contractor(s) to see that the building under construction is not occupied by any body unauthorizedly during construction, and is handed over to the Engineer-in-Charge with vacant possession of complete building. If such building, though completed is occupied illegally, then the Engineer-in-Charge will have the option to refuse to accept the said building/buildings in that position. Any delay in acceptance on this account will be treated as delay in completion and for such delay a levy up to 5% of the Estimated Cost put to tender may be imposed by the Superintending Engineer, whose decision shall be final both with regards to the justification and quantum and shall be binding on the Contractor. However, the Superintending Engineer may require the Contractor, through a notice, to remove the illegal occupation any time on or before reconstruction and delivery. 
.

Clause 20: The Contractor shall comply with all the provisions of the minimum wages Act 1948, and Contractor Labour (regulation & Abolition Act 1970), amended from time to time & rules framed thereunder & other labour laws affecting the Contract labour that may be brought into force from time to time.
Clause 21:  The Contract shall not be assigne or sublet without the written approval of the Engineer-in-charge.  And if the contractor shll assign or sublet the contract or attempt to do so advantage pecuniary or attempt to do so or if any bribe gratuity, gift, loan, perquisite reward or advantage pecuniary or attempt, shall eighter directly or indirectly, be given promised offered by the Contractor or any of his servants or agents or any public officer or persons in the employment of DDA in any way relating to his office or employment or if any such officer or person shall become in any way indirectly or directly interested in the Contract, the Engineer-in-Charge on behalf of the Authority shall have power to adopt any of the courses specified in clause 3, thereof as he may deem best suited to the interest of DDA and in the event of any these courses being adopted the consequence specified in the said clause 3 shall ensue payable.
Clause 22:  All sums payable by way of compensation under any of these conditions shall be considered as reasonable compensation to be applied to the use of DDA without reference to the actual loss or damage sustained and whether or not any damage shall have been sustained. 

The Contractor/ agency shall furnish a certificate that upto date return of D Vat have been filed under Delhi Value Added Tax on work contract Act, 2004, Rule 2005.  The copies of the return shall be enclosed with the tender documents. 
Clause 23: Where the Contractor is a partnership firm, the previous approval in writing of the Engineer-in-Charge shall be obtained before any change is made in the constitution of the firm. Where the Contractor is an individual or a Hindu undivided family business concern, such approval as aforesaid shall likewise be obtained before the Contractor enters into any partnership Agreement where under the partnership firm would have the right to carry out the works hereby undertaken by the Contractor. If previous approval as aforesaid is not obtained, the Contract shall be deemed to have been assigned in contravention of clause 21 hereof and the same action may taken, and same consequences shall ensure as provided in the said clause 21.

Clause 24: All works to be executed under the Contract shall be executed under the direction and subject to the approval in all respects of the Engineer-in-Charge who shall be entitled to direct at what point or points and in what manner they are to be commenced and time to time carried on.

Clause 25: The decision of the Superintending Engineer/Chief Engineer regarding the quantum of reduction as well as justification thereof in respects of rates for sub standard work below specification which may be decided to be accepted will be final and binding and will not be open to arbitration .

Clause 26:  The Contractor shall fully indemnify and keep indemnified the DDA against any action, claim or proceeding relating to infringement or use of any patent or design or any alleged patent or design rights and shall pay any royalties which may be payable in respect of any article or part thereof included in the Contract. In the event of any claims made under or action brought against DDA in respect of any such matters as aforesaid, the Contractor shall be immediately notified, thereof, and Contractor shall be at liberty, at his own expense, to settle any dispute or to conduct any litigation that may arise there from, provided that the Contractor  shall not be liable to indemnify the DDA if the infringement of the patent or design or any alleged patent or Design right is the direct result of an order passed by the Engineer-in-Charge, in this behalf.

Clause 27: Deleted

Clause 28:  In the case of any class of work for which there is no such Specifications as referred to in Clause 11, such work shall be carried out in accordance with the B.I.S./District Specifications. In case there is no B.I.S./District Specifications, then in such case the work shall be carried out as per manufacturers Specification.  In case, there are no such Specifications, as required above, the work shall be carried out in all respect in accordance with the instructions and requirements of the Engineer-in-Charge. 

Clause 29 (i)  Wherever any claims for payment of any sum / money arise out of or under Contract or against the Contractor, the Engineer-in-Charge or D.D.A. shall be entitled to withhold  and also have a lien to retain such sum or sums in whole or in part from security, if any deposited by the Contractor and for the purpose aforesaid, the Engineer-in-Charge or the D.D.A. shall be entitled to withhold the Security Deposit, if any, furnished as the case may be and also have a lien over the same pending finalization or adjudication of any such claim. In the event of the security being insufficient to cover the claimed amount or amounts or if no security has been taken from the Contractor, the Engineer-in-Charge or  D.D.A. shall be entitled to withhold and have lien to retain to the extent the such claimed amount or amounts referred to above, from any sum or sums found payable or which may at any time thereafter become payable to the Contractor under the same Contract or any other Contract with the Engineer-in-Charge or the D.D.A or any Contracting person through the Engineer-in-Charge pending finalization of adjudication of any such claim. 
It is an agreed term of the Contract that the sum or sums of money so withheld or retained under the lien referred to above by the Engineer-in-Charge or D.D.A. will be kept withheld or retained or retained as such by the Engineer-in-charge till the claim arising out of or or under the Contract is determined  or by the competent court, may be an that the contractor will have no claim for the interest or damage whatever or any account in respect of suh withholding or retention under the lien referred to above and duly notified as such to the contractor is a  partnership firm of a limited company the the Engineer-in-Charge or the D.D.A. shall be entitled to withhold and also have a lien to retain towards such claimed amount or amounts in whole or in part from any sum found payable to any partner/Limited company as the case may be, whether in his individual capacity or otherwise. 

Clause 29 (ii) :  DDA shall have right to cause an audit and technical examination of the works and the final bills of the Contractor, including all supporting voucher, abstract etc. to be made after payment of the final bill and if as a result of such audit and technical examination any sum is found to have been over paid in respect of any work done by the Contractor under the Contract or any work claimed to have been done by him under the Contract and found not to have been executed, the Contractor shall be liable to refund the amount of overpayment and it shall be lawful for  DDA to recover the same from him in the manner  prescribed in sub-clause (i) of this clause or in any other manner legally permissible, and if it is found that the Contractor was paid less than what was due to him under the Contract in respect of any work executed by him under it the amount of such under payment shall be duly paid by DDA to the Contractor, without any interest whatsoever. 
Provided that DDA shall not be entitled to recover any/some overpaid, nor the Contractor shall be entitled to payment of any sum paid short where payment has been  agreed upon between the Chief-Engineer or Executive Engineer on the one hand and the Contractor on the other hand under any term of the Contract permitting payment for work after assessment by the Chief-Engineer or the Executive Engineer             

Clause 30:  Any sum of money due and payable to the Contractor (including the Security Deposit refundable to him) under the Contract may be withheld or retained by way of lien by the Engineer–In-Charge or the DDA or any other Contracting persons or persons through Engineer-in-Charge against any claim.   The Engineer-in-Charge or DDA or such other person or persons in respect of payment of a sum of money arising out of or under any Contract made Contractor with the Engineer-in-Charge or the DDA with such other person or persons in respect of payment of sum of money arising out of or under any other contract made by the contractor made with the Engineer-in charge or DDA or with such other person or persons.

It is an agreed term of the Contract that sum of money so withheld or retained under this clause by Engineer-in-Charge or the DDA  will be kept withheld or retained as such by Engineer-In Charge or DDA or till his claim arising out of the same Contract or any other Contract is either mutually settled or by the competent Court, as the case may be and that the contractor shall have no claim for interest or damage whatsoever on his account or any other ground in respect of any sum of money withheld or retained under this clause and duly notified as such to the Contractor. 

Clause 31: The Contractor(s) shall make his/their own arrangement for unfiltered water required for the work and nothing extra will be paid for the same. This will subject to the following conditions:

(a)
That the water used by the Contractor shall be fit for construction purpose to the satisfaction of the Engineer-In Charge.  The cost of testing shall be paid by the Contractor. 

(b)
The Engineer-in-charge shall make alternative arrangement for supply of water at rink and ost of contractor for procurement of water in the opinion of the Engineer-in-charge are unsatisfactory.
Clause 32: (i)
The Contractor shall be allowed to construct temporary wells in DDA land for taking water for construction purposes only after he has got permission of the Engineer-in-Charge in writing. No charge shall be recovered from the Contractor on this account, but the Contractor shall 
be required to provide necessary safety arrangements to avoid any accidents or damage to adjacent building, roads and service lines. He shall be responsible for any accidents or damage caused due to construction and subsequent maintenance of the wells and shall restore the ground to its original condition after the wells are dismantled on completion of the work.

Clause 32: (ii)  Where there is no piped water supply arrangement and the water is to be taken by the Contractor from the wells or hand pumps constructed by the DDA no charge shall be recovered from the Contractor on that account. The Contractor shall, however, draw water at such hours of the day that it does not interfere with normal use for which the hand pumps and wells are intended. He shall also be responsible for all damage and abnormal repairs arising out of his use, the cost of which shall be recoverable from Contractor on this account. The Engineer-in-Charge shall be the final Authority to determine the cost recoverable from Contractor on this account and his decision shall to be binding on the Contractor.

Clause 33:  Notwithstanding any thing contained to the contrary in any or all of the clauses of this Contract, where any materials for the execution of the Contract are procured with the assistance of DDA either by issue from DDA stock or purchase made under order of permits or licenses issued by DDA, the Contractor  shall hold the said materials economically and solely for the purpose of the Contract and not dispose of them without the permission of the D.D.A. and return, if required by the Engineer-in-Charge all surplus materials or unserviceable materials that be left with him after the completion of the Contract or at its termination for any reason whatsoever on being paid or credited such price at the Engineer-in-Charge shall determine having due regard to the condition of the materials. The price allowed to the Contractor however shall not exceed the amount charged to him excluding the element of storage charges. The decision of the Engineer-in-Charge shall be final and conclusive. In the event of breach of the aforesaid condition the Contractor shall in addition throwing himself open to action for contravention of the term of the Licenses or permit and or for criminal breach of trust be liable to D.D.A. for all moneys, advantages or profit resulting or which in the usual course would have resulted to him by reason of such breach. 

Clause 34:  The plant and machinery as per annexure at page required of the work will be issued to the contractor on hire on conditions given below :-
(a)
Plant and machinery when supplied shall be made over and taken back at the departmental equipment/ shade the contractor shall arrange his programme of work according to the avaibility of the plant and no claim what so ever will be entertained from him for any delay in supply by Department.

(b)
The hire charges shall be recovered at the prescribed rates from and inclusive of the date the plant and machinery is made over and upto & inclusive of the date the plant and machinery is made over and upto and inclusive of the date of its return in good order even though the same may not have been working for any cuase except for major break down due to no fault of the contractor or faulty use requiring more than 3 working days continuously (i.e. excluding intervening holidays and Sundays) for bringing the plant in order.  The contractor shall immediately intimate in writing to the Engineer-in-Charge when any plant or machinery gets out of order requiring major repairs as aforesaid and binding on the contractor.

(c)
The Engineer-in-Charge shall record the date and time of receipt of such intimation in the log sheet of the plant or machinery.  Based on this if the break down occurs before lunch the period of major break down will be computed considering half a days break down on the day of complaint.  If the break occurs in the past break period, the period of major break down will be computed starting from the next working day.  In case of any dispute under this clause, the decision of the Superintending Engineer shall be final.
(d)
The hire charge shown above are for each day of 8 hours (inclusive of the one hour lunch break) or part there of in case of steam road roller the period of 8 hours will be inclusive of time required to make up the boiler pressure before start of work and to lower the boiler pressure at the close of the work.

(e)
Hire charges will include service of operating staff as required and supply of lubricating oil and stores for cleaning purposes Power fuel of approved type, for running the plant and machinery and also the full time Chowkidar for guarding the plant and machinery against any loss or damage shall be arranged by the Contractor who shall be fully responsible for the safeguard and security of plant and machinery.  The contractor shall on or before the supply of plant and machinery sign an agreement indemnifying the department against any loss or damage caused  to the plant and machinery either during transit or at the site of work.
(f)
Ordinarily the plant and machinery shall work for more than 8 hours a day inclusive of one hour lunch break.  In case of an urgent work, however, the Engineer-in-Charge may at his discretion, allow the plant and machinery to be worked for more than normal period of a 8 hours a day.  In that case the hourly hire charges for over time to be borne by the contractor shall be 50% more than the normal proportionate hourly charges (1/8 of the daily charges) subject to a minimum of half day’s normal charges son any particular day.  For working out hire charges for over time, a period of half an hour and above will be charges as one hour and a period of less than half hour will be ignored.
(g)
The contractor shall release the plant and machinery every 7th day for periodical servicing and/ or wash out which may take about three or four hours or more.  He shall also provide for any labour and water that may be required for wash out of steam rollers.  Hire charges for full day shall be recovered from the contractor for the day of servicing/ wash out irrespective of the period employed in servicing/ wash out.

(h)
The plant and machinery once issued to a contractor shall not be returned by him on account of lack of arrangements of labour and materials etc. on his part.  The same will be returned only when they require major repairs or when, in the opinion of the Engineer-in-Charge the work or a portion of work for which the same was issued is completed.

(i)
Log Book for recording the hours of daily work for each of the plant and machinery supply to the contractor will be maintained by the department and will be attested by the contractor for the authorized agent daily.  In case the contractor contests the correctness of the entries and/ or fails to sign the Log Book the decision to the Engineer-in-Charge shall be final and binding on him.  Hire charges will  be calculated according to the enties in the Log Book and will be binding on the contractor.  Recovery on account of hire charges for road rollers shlal be made for the minimum number of days worked out on the assumption that a roller  can consolidate per day and maximum quantity of materials or area of surfacing as noted against each in the annexed statement.
(j)
In the case of concrete mixers the contractor shall arrange to get the hopper cleaned and the drum washed at the close of the work each day of each occasion.

(k)
The contractor shall be responsible to return the plant and machinery in the same condition in which it was handed over to him and he shall be responsible for all damage caused to the said plant and machinery at the site of work or elsewhere when in operation or other wise or during transit including damages to or loss of parts and for all losses due to his failure to return the same soon after completion of work for which it was issued.  The Divisional Engineer shall be sole judge to determine the liability to the contractor and its, extent in this regard and his decision shall be final and binding on the contractor.
(l)
Hire of plant and machinery.


In case the road rollers for consolidations are employed by the contractor him self log book for such rollers shall be maintained in the same manner as is done in case of departmental rollers, maximum quantity of any items to be consolidated for each roller day shall be also same as in annexure to clause 34(i).  For less use of rollers, recovery for the less roller days shall be made at the market issue rate.
Clause 35: 
(i) 
The Contractor shall collect the total quantity of tar or bitumen required for the work as per standard formula before the process of painting is started and shall hypothecate it to the Engineer-in-Charge. If any bitumen or tar remains unused on completion of the work on account of less use of material in actual execution for reason other than Authorized changes of specification and abandonment of portion of work, a corresponding deduction equivalent to the cost of unused materials as determined by the Engineer-in-Charge shall be made and material returned to the Contractors. Although the material are hypothecated to D.D.A. the Contractors undertakes the responsibility for their proper watch, safe custody and protection against all risk. The material shall not be removed form site of work without the consent of the Engineer-in-Charge in writing.
(ii)
The Contractor shall be responsible for rectifying defects noticed within a year from the date of completion of the work. The Security Deposited relating to a asphaltic work shall refunded after expiry of this period. 
Clause 36: 
Contractor ‘Superintendence, Supervision Technical Staff & Employees.  

(i)
The Contractor shall provide all necessary superintendence during execution of the work and as long thereafter as may be necessary for proper fulfilling of the obligations under the Contract. 

The Contractor shall immediately after receiving letter of acceptance of the tender and before commencement of the work, intimate in writing to the Engineer-in-Charge the name, qualification, experience, age, address, and other particulars along with certificates of the Principal Technical representative to be in charge of the work. Such qualification and experience shall not be lower than specified in clause 36(iv). The Engineer-in-Charge shall within 15 days of receipts of such communication intimate in writing his approval or otherwise of such representative to the Contractor.  Any such approval may, at any time be withdrawn and in case of such withdrawal the Contractor shall appoint another such representative according to the provisions of this clause. Decision of the tender accepting Authority shall be final and binding on the Contractor in this respect.  Such Principal Technical Representative shall be appointed by the Contractor soon after receipt of the approval from Engineer-in-Charge and shall be available at site within fifteen days of start of work.

If the Contractor (or any partner in case of firm/company) who himself has such qualifications, it will not be necessary for the said Contractor to appoint such a principal technical representative but the Contractor shall designate and appoint a responsible agent to represent him and to be present at the work whenever the Contractor is not in a position to be so present.    All the provisions applicable to the principle technical representative under the clause will also be applicable in such a case to Contractor or his responsible agent. The principal technical representative and/or the Contractor shall on receiving   reasonable notice from the Engineer-in-Charge or his designated representative (s) in charge of the work in writing or in person or otherwise, present himself to the Engineer-in-Charge and/or at the site of work as required, to take instruction.  Instruction given to the principal technical representative or the responsible agent shall be deemed to have the same force as if these have been given to the Contractor. The principal technical representative and/or the Contractor or his responsible authorized agent shall be actually available at site at least on two working days every week, these days shall be determined in consultation with the Engineer-in-Charge as well as fully during important stage of execution of works, during recording of measurement of work and whenever so required by the Engineer-in-Charge by a notice as aforesaid and shall also note down instruction conveyed by the Engineer-in-Charge or his designated representative in the site order book and shall affix his signature in token of noting down the instructions and in token of acceptance of measurement. There shall be no objection if the representative/ agent looks after more than one work and not more than three work in same station provided these details are disclosed to the Engineer-in-Charge and he shall be satisfied that the provisions and the purpose of this clause are fulfilled satisfactorily.   If the Engineer-in-Charge, whose decision in this respect is final and binding on the Contractor, is convinced that no Technical representative or agent is effectively appointed or is effectively attending or fulfilling the provision of this clause, a recovery shall be effected from the Contractor as specified in clause 36 (iv) and the decision of the Engineer-in-Charge as recorded in the site order book and measurement recorded in Measurement book shall be final and binding on the Contractor. Further if the Contractor fails to appoint a suitable technical representative or responsible agent and if such appointed persons are not effectively present or do not discharge their responsibilities satisfactorily, the Engineer-in-Charge shall have full powers to suspend the execution of the work until such date a suitable agent appointed and the Contractor shall be held responsible for the delay so caused to the work.  The Contractor shall submit a certificate of employment of the technical representative/responsible agent along with every on account bill/Final bill and shall produce evidence, if at any time, so required by the Engineer-in-Charge.

(ii) The Contractor shall provide and employ on the site only such Technical Assistants as are skilled and experienced in their respective fields and such foremen and supervisors as are competent to give proper supervision to the work. 
The Contractor shall provide and employ skilled, semiskilled and unskilled labour as is necessary for proper and timely execution of the work.


The Engineer-in-Charge shall be at liberty to object to and require the Contractor to remove from the works any person who in his opinion misconducts himself, or is incompetent or negligent in the performance of his duties or whose employment is otherwise considered by the Engineer-in-Charge to be undesirable.  Such person shall not be employed again at work site without the written permission of the Engineer-in-Charge and the persons so removed shall be replaced as soon possible by competent substitutes.

Clause 36(i): 
Minimum qualification and experience required for principal technical representative 

(a)For works with Estimated Cost put to tender more than 

(i)
Rs.10 Lacs for Civil Work
Graduate or retired AE

(ii) 
Rs.5 Lacs for Elect /Mech. Works 
possessing recognized Diploma

(b)
For works with Estimated Cost put to tender. 

(i)
More than Rs.5 Lacs but less than 

Rs.10 Lacs for Civil Works 

(ii)
More Than Rs.1 Lakh but less then
Recognized Diploma Holder

Rs.5 Lacs for Elect./ Mech. Works

(c)  
Discipline for which the Principal

Technical Representative should belong 
Civil/Elect/Mech.

(d)
Minimum experience of works 



    10 years

(e)
Recovery to be effected form the 


Contractor in the event of not fulfilling the


 provisions of clause 36.(i)
i)
Rs.4,000/-pm for Graduate 


ii) Rs.2,000-pm for Diploma Holder
Clause 37 : The whole work may be split up between two or more contractors or accepted in part and not in entirely if considered expedient. 

Clause 38:  In pursuant to or under any law, notification or order any Royalty, Cess or the like become payable by the DDA and does not at any time becomes payable by the Contractor to the state Government/Local Authority in respect of any materials used by the Contractor, in the works then in such a case, it shall be lawful to the DDA and it will have the right and be entitled to recover the amount paid in the circumstances as aforesaid from dues of the Contractor.

1.
Sales tax/ VAT  or any other tax on material, in respect of this Contract shall be payable by the Contractor and DDA shall not entertain any claim whatsoever in this respect in case of any default the Engineer-in-charge shall effect recovery. 
2.
All Government Departments, Public Undertaking and other Government Bodies carrying out any building or other construction works which are covered under section 2(d) of the main Act shall in case the work is carried out through a contractor, deduct mandatory 1% of the amount of cost approved as per the tender notification from the bills at the time of making payment to the contractors. 
Clause 39:

Without prejudice to any of the rights or remedies under this contract if the contractor dies, Divisional Officer on behalf of the DDA shall have the option of terminating the Contract without compensation to the ‘heirs’ of the Contractor. 

Clause 40: 

The Contractor shall not be permitted to tender for works in D.D.A. Zone (responsible for award and execution of Contracts) in which any of his near  relatives is posted as divisional accountant or as officer in any capacity between grades of CE and J.E. (both inclusive) in  D.D.A. He shall intimate the names of his near relatives, if any who are working as group A, B or C officer or JE in D.D.A. He shall also intimate the names of these persons who are working with him in any capacity or are subsequently employed by him and who are near relatives of any group A, B or C officers in  D.D.A. or Ministry of Urban Development.   Any breach of this condition by the Contractor would render him liable to action under Clause-2 of the condition by the contractor would render agreement in addition, he would also liable to be debarred from tendering in future. 

Note: 
By the terms near relatives is meant wife, husband, parents and grand parents, children, brothers, sisters, uncles, aunts, cousin and their corresponding in-laws.

Clause 41:  No Engineer of Gazetted rank or other Gazetted officer employed in Engineering or Administrative duties in an Engineering Department of the DDA is allowed to work as a contractor or employee of a contractor for a period of one year after his retirement from Authority’s service without prior permission of DDA in writing. This contract is liable to be cancelled if either the Contractor or his employee is found at any time to be such a person who had not obtained the permission of the DDA as aforesaid, before submission of tender or engagement in the Contractor’s service as the case may be.

Clause 42: 

(i) 
The Contractor shall see that only required quantities of material are got issued. Any such materials remaining unused and in perfectly good condition at the time of completion or termination of the Contract shall be returned to the Engineer-in-Charge at a place where directed, directly by him by notice in writing under his hand if he shall so require, credit for such materials will be given at the prevailing market rate not exceeding the amount charged from him excluding the element of storage charge @ 2.5% levied at the time of issue of materials to him. The Contractor shall also not be entitled to cartage and incidental charges for returning the surplus material from and to the above said stores where these were issued.

(ii)
After completion of the work the theoretical quantity of cement to be used in work shall be calculated on the basis of statement showing quantity of cement to be used in different items of work provided in Delhi Schedule of Rate 2007 with Correction Slips issued up to the date of receipt of tender. In case any item is executed for which the standard constants for the consumption of cement are not available in the above mentioned statement or cannot be derived, the same shall be calculated on the basis of standard formula to be laid down by the Superintending Engineer of the circle concerned. Over this theoretical quantity of cement shall be allowed a variation up to 3% plus/minus for work up to the Estimated Cost of which put to tender is up to Rs.5 Lacs and 2%+/- for works the Estimated Cost of which put to tender is  more than Rs.5 Lacs. The difference of the quantity of the cement actually issued to the Contractor and theoretical quantity including authorized variation, if not returned by the Contractor, shall be recovered at twice the issue rate without prejudice to the provision of the relevant conditions regarding return of materials governing the Contracts.  In the event of it being discovered that the quantity of cement used is less than the quantity ascertained allowing variation on the minus side (as stipulated above), the cost of quantity of cement not so used shall be recovered from the Contractor on the basis of Stipulated Issue rates/ market rate and cartage to site.  

(iii)
The provisions of foregoing sub-clause shall apply mutatis-mutandis in the case of steel section, reinforcement or structural steel (each diameters/section or category shall be considered separately) except that theoretical quantity of the steel shall be taken as the quantity required as per design or as authorized by the Engineer-in-Charge including authorized lappages plus 3% wastage due to cutting into pieces. Over this theoretical quantity 2% plus/minus shall be allowed as variation due to wastage being more or less. 

(iv)
After the completion of the work the actual quantity of cables (other than underground cables)wire conduit/ GI, CI, SCI pipes, GI/MS sheets used in the various items of work shall be calculated on the basis of measurements recorded in the Measurement Books for purpose of payment and for assessing the consumption of materials used on works. Over this quantity a variation of 5% plus shall be allowed for wastage of materials during execution in case of cable, wire, conduit pipes/GI/CI/SCI pipes and 10% plus in case of GI/MS sheets. The difference in quantity recorded in the measurement book including authorized variation as states above, if not returned by the Contractors, shall be recovered at twice the issue rates plus cartage to site, with out prejudice to the provisions of the relevant condition regarding return of materials governing the Contract. 

(v)
After completion of the work the theoretical quantity of bitumen to be used on works shall be calculated on the basis of CPWD statement showing quantity of bitumen to be used in different items of work provided in the Delhi Schedule of Rates bitumen to be used in different items of the work provided in the Delhi Schedule of Rate 2007 with up to date Correction Slips in respect of agreement which do not provide for or authorized application of Delhi Schedule of rates 2007 with C.S.uptodate theoretical quantity of bitumen to be used in the work shall be calculated on the basis of standard formula laid down by Superintending Engineer of the concerned circle for items other then DSR items.  Over the said theoretical quantity of Bitumen a variation up to plus (excess) 2.5% shall be allowed. 


The agreement which provided for supply of bitumen actually issued to the contractor and the theoretical quantity including the above mentioned authorized variation if not returned by the contractor, shall be recovered at twice the issue rate of bitumen, without prejudice to the relevant conditions in the Agreement regarding return of materials governing the Contract. In the event of it being discovered that the quantity calculated in the manner aforesaid (no variation) is on the lower side, the cost of quantity of bitumen not so used shall be recovered by the Contractor on the basis of stipulated issued rate + cartage thereof up to site. 

(vi)
The provision made above are without prejudice to the rights of the DDA to take action against the Contractor under the condition of the Contract for not doing the work according to the prescribed specification. 

(vii)
The material shall be issued to the contractor at the place of delivery as mentioned in the schedule. If these are delivered at any other site, the difference due to cartage will adjusted accordingly. The contractor shall have to cart the materials at his own cost to the site of the work as soon as these are issued. The material shall be issued between the working hours and as per rules of the DDA‘s godown as framed from time to time.

(viii) 
The Contractor shall bear all incidental charges, storage and safe custody of materials.

(ix)
T.M.T. Round bars and Tor Steel shall be issued in lengths as available in the Stores.  No claim on this account shall be entertained.  

(x)
The Contractor shall construct suitable godowns at the site of work for storing the materials safe against damages from sun, rain, dampness, fire, theft etc. He shall also employ necessary watch and ward establishment for this purpose. 

(xi)
Cement bags shall be stored in separate godowns as per typical godown sketch attached, with pucca floor and weatherproof roof and walls. Each godown shall be provided with a single door with two locks. The keys of one lock shall remain with DDA Junior Engineer-in-Charge of work, and that of the other lock with the authorized agent of the Contractor at the site of work, and that the cement is removed from the godown according to the daily requirement with the knowledge of both the parties.  The cement bags shall be stacked on proper floor consisting of two layers of dry bricks laid on well consolidated earth, at a level of at least 30 cm above ground level. These stocks shall be in rows of 2 bags and 10 bags high with a minimum 60 cm clear space around. The bags should be placed horizontally continuous in each line as shown in the accompanying sketch. The day to day receipts and issue accounts of cement shall be maintained by the Junior Engineer-in-Charge and signed daily by the Contractor or his authorized agent (as per specimen of register attached)
Clause 43: DELETED  

Clause 44:  The work (whether fully constructed or not) and all materials, machine, tools and Plants, scaffolding, temporary building and other things connected therewith shall be at the risk of the Contractor until the work has been delivered to the Engineer-in-Charge, and a certificate from him to that effect  obtained.  In the event of the work, any materials properly brought to the site for incorporation in the work being damaged or destroyed in consequence of hostilities or war like operation, the Contractor shall, when ordered ( in writing) by the Engineer-in-Charge to remove any debris from the site, collect and properly stack and remove in store all serviceable materials salvaged from the damaged work and shall be paid at the Contract rates in accordance with provision of this Agreement for the work of clearing the site of debris, stacking or removal of serviceable materials and for the reconstruction of all works ordered by the Engineer-in-Charge, such payment being in addition to compensation up to the value of work originally executed before being damaged or destroyed and paid for for the compensation shall be assessed by the Divisional Officer 5 upto Rs.5,000/- and by the Chief Engineer for a higher amount. The Contractor shall be paid for the damages/destruction suffered and for restoring the material at the rate, based on the analysis of rates tendered for, in accordance with the provisions of this Agreement.  The certificate of the Engineer-in-Charge regarding the quantity of material and the purpose for which they were collected shall be final and binding on all parties to this Contract. 
Provided always that no compensation shall be payable for any loss in consequence of hostilities or war-like operations  Unless (a) the Contractor had taken all such precaution against air-raid deemed necessary by the A.R.P. Officer of the Engineer-in-Charge. (b) for materials etc. not on site of the work or for any tools and Plants, Machinery, scaffolding, temporary buildings and other things not intended for the work. 
In the event of the Contractor having to carry out reconstruction as aforesaid, he shall be allowed such extension of time for its completion as is considered reasonable by the Divisional Officer.

Clause 45:  The Contractor shall deposit royalty and obtain necessary permit for supply of red bajri, stone, kankar etc. from local Authority. 

Clause 46:  Security Deposit for the work shall not be refunded till clearance from the labour officer is obtained by the Contractor.

Clause 47: DELETED

Clause 48: The Contractor shall comply with the provisions of the Apprentice Act, 1961 and the rules and order issued there under from time to time. If he fails to do so, his failure will be a breach of the Contract and the Engineer-in-charge may in his discretion cancel the Contract. The Contractor shall be liable for any pecuniary liability arising on account of any violation by him of the provisions of the said Act. 
Clause 49: Anti Malaria Measures 

The Contractor shall at his expenses make necessary arrangement for undertaking anti-malaria measures including drainage at places as abandoned haudies, water tanks, and excavated sites etc where water is likely to stagnate and cause mosquito breeding. The Contractor shall comply with every reasonable directions of the Engineer-in Charge.

SAFETY CODE
1. Suitable scaffolds should be provided for workmen for all works that cannot be safely done from the ground or from solid construction except such short period works as can be done safely from ladders. When a ladder is used, an extra mazdoor shall be engaged for holding the ladder and if the ladder is used for carrying material as well, suitable foot-holds and hand-holds shall be provided on the ladder and ladder shall be given an inclination not steeper than ¼ to 1(1/4 horizontal and 1 vertical).

2. Scaffolding or staging more than 12feet above the ground or floor, swung   or suspended from an overhead support or erected with stationery support shall have a guard rail properly attached or  bolted, braced and otherwise secured at least 3 feet high above the floor or platform of such scaffolding or staging and extending along the entire length of the outside ends thereof with only such opening as may be necessary for the delivery of the materials. Such scaffolding or staging shall be so fastened as to prevent it from swaying from the building or structure. 

3. Working platforms, gangways and stairways should be so constructed that they should not sag unduly or unequally and if the height of the platform or the gangway or the stairway is more than 12 feet above ground level or floor level, they should be closely boarded and should have adequate width and should be suitable fastened as described in (2) above

4. Every opening in floor of a building or all working platforms shall be provided with suitable means to prevent the fall of persons or materials. The opening can be protected by providing suitable fencing or railing whose minimum height shall be 3’-0” (90cm).

5. Safe means of access shall be provided to all working platforms and other working places.  Every ladder shall be securely fixed.  No portable single ladder shall be over 30 feet ( 9 m) in length, while the width between side rails in hung ladder shall in no case less than (11½”) 29 cm, for ladder up to and including 3.05 m in length. For longer ladder this width should be increased at least 6mm for each additional 30 cm of length. Uniform step spacing shall not exceed 30cm. Adequate precautions shall be taken to prevent danger from Electrical equipment. The materials on any of the site of work shall not be so stacked or placed as to cause danger or inconvenience to any person or public.  The Contractor shall provide all necessary fencing and lights to protect the public from accident and shall be bound to bear the expenses to defend  every suit, action or other proceeding at law that may be brought by any person for injury sustained owing to neglect of the above precautions and to pay any damages and cost which may be awarded in any such suit, action or proceeding to any such person or which may, with the consent of the Contractor, be paid to compensate and claim by any such person.

6. Excavation and Trenching:-  All trenches four feet or more in depth shall at all times be provided with at least one ladder for each 30 m in length or fraction thereof. Ladder shall extend from bottom of the trench to at least 90 cm above the surface of the ground. The sides of the trenches with 1.5 m or more in depth shall be stepped back to give suitable slope or securely held by timber bracing so as to avoid the danger of sides to collapse.  Excavated materials shall not be placed within 1.5 m of the trench or half of the depth of the trench whichever is more. Cutting shall be done from top to bottom. Under no circumstances undermining or undercutting shall be done.

7.
Demolition: 
Before any demolition work is commenced and also during its progress following safety measures shall be taken.
(a) All roads and open areas adjacent to the work site shall either be closed or suitably protected.
(b) No Electric cable or apparatus which is liable to be a source of danger or a cable or apparatus used by the operator shall remain electrically charged.
(c) All practical steps shall be taken to prevent danger to persons employed from risk of fire or explosion or flooding.  No floor, roof or other parts of the building shall be so overloaded with debris or materials as to render it unsafe.

8.
All necessary personal safety equipments, as considered adequate by the Engineer-in-Charge, should be kept available for the use of the persons employed on the site and maintained in a condition suitable for immediate use and the Contractor should take adequate steps to ensure proper use of equipment by those concerned the following safety equipments shall invariably be provided.

(a) Workers employed on mixing asphaltic materials, cement and lime mortars shall be provided with protective footwear and protective goggles. 

(b) Those engaged in whitewashing and mixing or stacking of cement bags or any material which is injurious to the eyes shall be provided with protective goggles.

(c) Those engaged in welding works shall be provided with welder’s protective eyes shields. 

(d) Stone breakers shall be provided with protective goggles and protective clothing and seated at sufficiently safe intervals.

(e) When workers are employed in Sewers, Storm water piped drains and manholes, which are in active use, the Contractor shall ensure that the following safety measures are adhered to:-

(i) 
Entry for workers into the line shall not be allowed except under supervision of the JE or any other higher officers.
(ii)
At least 5 to 6 manholes at upstream and downstream should be kept open for at least 3 to 4 hours before any man is allowed to enter into the manhole for working inside.

(iii)
Before entry, presence of toxic gases should be tested by inserting wet lead acetate paper, which changes colour in the presence of such gases and gives indication of their presence. 

(iv)
Presence of oxygen should be verified by lowering a detector lamp into the manhole. In case, no oxygen is found inside the sewer line, workers should be sent only with oxygen kit. 

(v)
Safety belts with rope should be provided to the workers. While working inside the manhole, such rope should be handled by two men standing outside to enable him to be pulled out during emergency.

(vi)
The area should be barricaded or cordoned off by suitable means to avoid mishaps of any kind. Proper warning signs should be displayed for the safety of the public whenever cleaning works are undertaken during night or day.

(vii)
The malba obtained on account of cleaning of blocked manholes and sewer lines should be immediately removed to avoid accidents on account of slippery nature of the malba.

(viii) 
No smoking or open flames shall be allowed near the blocked manholes being cleaned.

(ix) 
Workers should not be allowed to work inside the manhole continuously. They should be given rest intermittently. The Engineer-in-Charge may decide the time up to which a worker may be allowed to work continuously inside the manhole.

(x)
Gas mask with oxygen cylinder should be kept at site for use in Emergency. 

(xi)
Gas masks with oxygen cylilnder should be kept or fresh air through manholes whenever called for.  Portable air blowers are recommended for ventilating the manholes.  The Motors for these shall be waterproof and of totally enclosed type. Non sparking gas engines also could be used but they should be placed at least 2 m away from the opening and on the leeward side protected from wind so that they will not be a source of friction on any inflammable gas that might be present. 

(xii)
The workers engaged for the cleaning the manholes and sewers should be properly trained before allowing to work in the manhole. 

(xiii)
The workers shall be provided with gumboots or non-sparking shoes, bump helmets and gloves, non-sparking tools, safety lights and gasmasks and portable air blowers (when necessary). They must be supplied with barrier cream for anointing the limbs before working inside the sewer lines. 

(xiv)
Workman descending a manhole shall try each ladder step or rung carefully before putting his full weight on it to guard against insecure fastening due to corrosion of the rung fixed to manhole wall.

(xv)
If a man has received a physical injury he should be brought out the sewer immediately and adequate medical aid should be provided to him.

(xvi)
The extent to which these precautions are be taken depend on individual situation, but the decision of the Engineer-in-Charge regarding the steps to be taken in this regard, in an individual case, will be final. 

9. The Contractor shall not employ men and women below the age of 18 years on the work of painting with products containing lead in any form. Wherever men above the age of 18 years are employed on the work of lead painting the following precautions should be taken. 
(i) No paint containing lead or lead products shall be used except in the form of paste or readymade paint. 





(ii) Suitable face masks should be supplied for use by the workmen when paint is applied in the form of spray or a surface having lead paint is dry rubbed and scrapped. 

(iii) Overalls, equipments (all safety equipments) shall be supplied by the Contractors to the Workmen when paint is applied in the form of spray on a surface having lead paint dry rubbed and scrapped. 
(iii)a.
Overall all the safety equipment shall be supplied by the contractor to the workmen and adequate facilities shall be provided to enable the working painters to wash during the execution of works.

(iv)
(a)
White lead, sulphate of lead, or product containing these pigments shall not be used in painting operation except in the form of pastes or paint ready for use. 

(b)
Precautionary measures shall be taken whenever required to prevent damage arising from the application of a paint in the form of pastes or paint ready for use, in the form of spray 

(c)
Precautionary measures shall be taken whenever required in order to prevent danger arising out from dust caused by dry rubbing down and scrapping. 

(v)
(a)
Adequate facilities shall be provided to enable working painters to wash during and on cessation of work.


(b)
Overalls shall be worn by working painters during the whole working period. 

(c)
Suitable arrangement shall be made to prevent clothing put on during working hours being spoiled by painting materials. 

(vi) 
(a)
Cases of lead poisoning and suspected lead poisoning shall be notified and subsequently verified by medical man appointed by the competent Authority of DDA 

(b)
The DDA may require necessary medical examination of the workers.

(c)
Instruction with regard to special hygienic precautions to be taken in the painting trade shall be distributed to working painters. 

(10) 
When the work is done near any place where there is risk of drowning, all necessary equipments should be provided and kept ready for use and all necessary steps to be taken for prompt rescue of any person in danger and adequate provision should be made for prompt first aid treatment of  all injuries likely to be sustained during the course of work. 

(11)
Use of hoisting machines and tools including their attachments, anchorage and supports shall conform to the following standards or conditions. 

(i)
(a)
These shall be of good mechanical construction, sound material and adequate strength and free from patent defect and shall kept repaired and in good working order. 


(b) 
Every rope used in hoisting or lowering materials or as a means of suspension shall be of durable quality and adequate strength and free from patent defects. 
(ii) Every crane driver or hoisting appliance operator shall be properly qualified and no person under the age of 21 years should be In-Charge of any hoisting machine including any scaffolding which gives signal to operator. 

(iii) 
In case of every hoisting machine and of every chain ring hook, shackle swivel and pulley block used in hoisting or as means of suspension, the safe working load shall be plainly marked with the safe working load.  In case  of a   hoisting machine having  a variable safe working load, each safe working load and the conditions under which it is applicable shall be clearly indiated.  No part of any machines or any gear referred to above in this paragraph shall be loaded beyond the safe working load except for the purpose of testing.

In case of Departmental machines, the safe working load shall be notified by the Electrical Engineer-in-Charge. As regards Contractor’s machines the Contractor  shall notify the safe working load of the machine to the Engineer-in-Charge whenever he brings any Machinery to site of work and get it verified by the Electrical Engineer concerned. 

(12) 
Motors, gearing, transmission, electric wiring and other dangerous parts of hoisting appliances should be provided with efficient safeguard. Hoisting appliance should be provided with such means as will reduce to the minimum risk of accidental descent of the load. Adequate precautions should be taken to reduce to the minimum risk of any part of a suspended load becoming accidentally displaced. When workers employed on electrical installation which are already energized, insulating mask, wearing apparel, such as gloves, sleeves and boots as may be necessary should be provided. The worker should not wear any ring, watches and carry keys or other materials which are good conductors of electricity. 



(13)
All scaffolds, ladders and other safety devices mentioned or described herein shall be maintained in safe conditions and no scaffold, ladder or equipment shall be altered or removed while it is in use. Adequate washing facilities should be provided at or near places of work.

(14) 
These safety provisions should be brought to the notice of all concerned by display on a notice board at a prominent place at work spot. The person responsible for the compliance of the safety code shall be named therein by the Contractor. 

(15) 
To ensure effective enforcement of the rules and regulations relating to safety precautions, the arrangements made by the Contractor shall be open to inspection by the Labour Officer or Engineer-in-Charge of the Authority or their representative. 

(16) 
Notwithstanding the above Clause (1) to (15) there are nothing in these to exempt the Contractor from the operating of any other Act or rule in force in the Republic of India.

MODEL RULES FOR THE PROTECTION OF HEALTH AND SANITARY ARRANGEMENTS FOR WORKERS EMPLOYED BY DDA OR ITS CONTRACTORS 

1.  
Application 

These rules shall apply to all building and construction works in-charge of Delhi Development Authority.

2. 
Definitions 

“Work place” means a place where at an average fifty or more workers are ordinarily employed in connection with construction work. 

“Large work place” means a place where at an average 500 or more workers are ordinarily employed in connection with construction work. 

3. 
First Aid 
(a) 
At every work place there shall be provided and maintained, so as to be easily accessible during working hours, first aid appliances including an adequate supply of sterilized dressing cotton wool. The appliances shall be kept in good order and in large work place, they shall be placed under the charge of a responsible person who shall be readily available during working hours. 

(b) 
At large work place where hospital facilities are not available within easy distance from the work, First Aid posts shall be established and run by a trained Compounder. 
(c) 
Where large work places are at remote from regular hospitals, an indoor ward shall be provided with one bed for every 250 employees.
(d) 
Where large work places are situated in cities, towns or in their suburbs and no beds are considered necessary owning to the proximity of city or town hospitals, suitable transport shall be provided to facilitate removal of urgent cases to the hospitals at other work places.  Some conveyance facilities, such as a car, shall be kept readily available to take injured person or persons suddenly serious to the nearest hospital. 

4. 
Drinking Water 


CONDITION NO.4 OF MODEL RULES

The contractor shall supply only potable water in the labour camp sample of water shall be drawn from the source of water supply in the labour camps every months and got tested from the MCD lab by the contractor.  Wherever drinking water is supplied to the labour camps through tankers.  Samples shall be drwn from the tankers and got tested.  Water storage tanks chlorine tablets shall be added from time to time as per requirement so that potability of water remain intact No extra payment shall be made on this account.

(a) In every work place, there shall be provided and maintained at suitable place, which is easily accessible to labour, a sufficient supply of cold water fit for drinking. 

(b) Where drinking water is obtained from an intermittent public water supply, each work place shall be provided with storage where drinking water shall be stored. 

(c) Every water supply or storage shall be at distance of not less than 15 m from any latrine, drain or other source of pollution. Where water has to be drawn from an existing well which is within such proximity of latrine, drain or any other source of pollution, the well shall be properly chlorinated before water is drawn from it for drinking. All such wells shall be entirely closed in and be provided with a trap-door which shall be dust and waterproof. 

(d) A reliable pump shall be fitted to each covered well. The trap-door shall be kept locked and opened only for cleaning or inspection which shall be done at least once a month. 

5.  Washing and Bathing place: 
(i) Adequate washing and bathing places shall be provided separately for men and women. 

(ii) Such facilities shall be conveniently accessible and places shall be kept clean, hygienic and in dried condition 

6. Scale of accommodation in Latrines and urinals

(i)
Latrines and urinals shall be provided within the premises of every work, on the 



following scale: 















No. of seats 
(a) Where the number of persons does not exceed 50.  
2
(b) Where the number of persons exceeds 50, but does not
3


exceed 100. 
(c) For every additional 100 persons 
3 per 100


In particular cases the Executive Engineer shall have the powers to vary scale where necessary.

7.
Latrines and urinal for women: 

If women are employed, separate latrine and urinals, screened those for men and marked in the vernacular in conspicuous letter “For women only” shall be provided on the scale laid in rule 6.  Those for men shall be similarly marked “For men only”.  A poster showing the figure of a man and a women shall also be exhibited at the entrance of latrines, for each sex.  There shall be adequate supply of water close to theurinals and latrines.
8.
Latrines and urinals 

Except in work places provided with water flushed latrines, connected with a water borne sewage system, all latrines shall be provided with receptacles on dry earth system which shall be cleaned at least four times daily and at least twice during working hours and kept in a strictly sanitary condition. The receptacles shall be tarred inside and outside at least once a year. 

9.
Construction of latrines 

The inside well shall be constructed of masonry of some suitable heat-resisting, non-absorbent materials and shall be cement washed inside and outside at least once a year. The dates of cement washing shall be maintained for this purpose and kept available for inspection. Latrine will not be of  standard lower than borehole system and should have thatched roof. 

10,
Disposal of Excreta: 

Unless otherwise arranged for by the Local Sanitary Authority, arrangements for proper disposal of excreta by incineration at the work place shall be made by means of a suitable incinerator approved by the Assistance Director of Public Health or the Municipal Medical Officer of Health as the case may be in whose jurisdiction the work place is situated. Alternatively excreta may be disposed off by putting a layer of night soil at the bottom of pucca tank prepared for the purpose and covering it with a 6” layer of waste or refuse and then covering with a layer of earth for a fortnight (when it will turn into manure). 

11.
Provision of shelter during rest: 

At every work place there shall be provided free of cost two suitable sheds, one for meals and the other for rest separately for the use of men and women. The height of each of the shelter shall not be less than 11 feet (3.35 m) from the floor level to the lowest part of the roof. The sheds should be of thatched roof and mud flooring will be provided with dwarf wall around not less than ½ feet (76cm.) Sheds should be kept clean and the space provided shall be on the basis at least 5 square feet (0.46 Sqm per) head. 

12,
Crèches:
(a) At every work place, where 50 or more women workers are ordinarily employed, there shall be provide two huts for the use of children under the age of six years belonging to such women. One hut should be used for infant’s games and play and other as their bed room. The hut shall not be constructed on a lower standard than the following: 

(i) Thatched roof 

(ii) Mud floor. 

(iii)Planks spread over the mud floor and covered with matting. 

The huts shall be provided with suitable and sufficient opening for light and ventilation. There shall be adequate provision of sweeper to keep the places clean. There shall be two dais in attendance. Sanitary utensils shall be provided to the satisfaction of the Health Officer of the area concerned. The use of the hut shall be restricted to children, their attendants and mother of the children. 
(b) Where the number of women workers is more than 25 but less than 50, the Contractor shall provide at least one hut and one Dai to look after the children of women workers. 
(c) The size of crèche shall vary according to the number of women workers. 

(d) 
The crèche shall be properly maintained and necessary equipment like toys etc. shall be 
provided.



13.
Canteen 

A cooked food canteen on a moderate scale shall be provided for the benefit of workers whenever it is considered expedient of the Contracts. 
14.
The above rules shall be incorporated in the contract and in the notice inviting tenders shall form intergral part of the contracts.
CONTRACTOR’S LABOUR REGULATIONS

SHORT TITLE


These regulation, may be called the “DDA Contractor’s Labour Regulations”.

1.
DEFINITION


In these regulations, unless otherwise expressed or indicated, the following words and expression shall have the meaning hereby assigned to them respectively i.e.. 
(i). “Labour” means workers employed by DDA or its Contractor directly or indirectly through sub-contractor or other persons or by an agent on his behalf, on a payment not exceeding Rs.400/- per month and will not include supervisory staff like Overseak etc. and will not be less than minimum rates of wages fixed by the latest Delhi Govt. and plus upto date variable dearness allowance on applicable for minimum wages/ on the basis of cost vide modification by Delhi Administration time to time for the class of employee engaged on the same type of work circulated vide number of the time of tender. 
(ii).  “Fair Wages” means wages, whether for time or piece work fixed and notified at the time of inviting tenders under the provision of the minimum wages act from time to time to be not less than minimum rates of wages fixed by the Govt. of N.C.T. Delhi vide Notification  issued  from time to time.  

(iii). “Contractor” shall include every person whether a sub-contractor or head man agent employing labour on the work taken on Contract. 

(iv). “Wages” shall have the same meaning as defined in the payment of wages act and includes time and piece rate wages. 

2
(a)
Normally working hours of an employee should not exceed 8 hours a day and in case of a child 4½ hours a day. Working day shall be so arranged that inclusive of intervals for rest, it shall not spread over more than 12 hours on any day
. 



(b) 
When an adult worker is made to work for more than 9 hours on any day or for more than 48 hours in any week, he shall be given overtime for the extra hours put in by him at double the ordinary rate of wages and children shall not be made to work extra.

(c)
Every worker shall be given a weekly holiday normally on Sunday in accordance with the provision of the minimum wages (Central) Rules 1950 as amended from time to time irrespective of whether such worker is governed by the minimum wages act 1948. 

3. 
Display of notice regarding wages etc.The contractor shall : 

(a) Before he commences his work on Contract, display and correctly maintain and continue to display and correctly maintain in a clear and legible condition in  conspicuous place on the work, notice in English and in the local Indian Language spoken by the majority of the workers giving the minimum rate wages which have been certified by the Executive Engineer, the Chief Engineer or Regional Labour commissioner as fair wages and the hours of work which such wages are earned and the actual wages being paid. (and other relevant information) 

(b) Send a copy of such note to the certifying officer as EE/CE and required Labour commissioner 

4. 
Payment of Wages

(i) Wages due to every worker shall be paid to him directly or through other person authorized on this behalf. 
(ii) All wages shall be paid in current coin or in currency or in both. 
(iii) Arrears claimed after 3 months after the completion of the work shall not be entertained. 

5. 
Fixation of wage periods


The contractor shall fix the wage periods in respect of which wages shall be payable 

(i) No wage period shall exceed one month. 

(ii) The wages of every worker employed on the Contract shall be paid


(a)
in case of establishment in which wage period is one week, within three days from the end of the wage period and 


(b) 
in the case of other establishments before the expiry of 7th day or 10th day from the end of the wage period according to the number of workers employed in such establishment does not exceed 1000.


(iii) 
Where the employment of any worker is terminated by or on behalf of the Contractor, the wages earned by him shall be paid before the expiry of the day succeeding the one on which his/her employment is terminated.


(iv) 
All payment of wages shall be made on a working day except when the 
work is completed before the expiry of the wage period in which case final payment shall be made 48hours of the last working day at work site  and during the working time.  

Note: - The term “Working day” means a day on which the work for which the labour employed is in progress. 

6.  Wage book and wage Slip etc.

(i) The Contractor shall maintain a wage book of each worker in such a form as may be convenient, at the place of work but the same shall include the following particulars

(a) Name of the worker. 
(b) Rate of daily or monthly wages. 

(c) Nature of work on which employed. 

(d) Total number of days worked during each wage period. 

(e) Dates and period for which worked overtime. 

(f) Gross wages payable for the wage period. 

(g) All deduction made from the wage with an indication in each case of the ground for which the deduction is made. 

(h) Wage actually paid for each wage period.
(ii) Signature or thumb impression of the worker. 

(iii) The Contractor shall also issue a wage slip containing the aforesaid particulars to each worker, employed by him on the work at least a day prior to the day of disbursement of wages. 
(iv) The Contractor shall issue an Employment Card in the prescribed form III to each worker on the day of work or entry into his employment. If the worker has already any such card from the previous employer, the contractor shall merely endorse that employment card with relevant entries. On termination of employment, the employment card shall again be endorsed by the Contractor and returned to the worker. 

(v) “The Contractor shall issue an Attendance cum Wage Card as per Form IV enclosed to each worker on the day of work on entry into his employment”

7. 
Register of Unpaid wages: 


The Contractor shall maintain a Register of unpaid wages in such form as may be convenient at the place of work but the same shall include the following particulars: 
(a) Full particulars of the labourers whose wages have not been paid. 

(b) Reference number of the muster roll and wage register. 

(c) Rate of wages. 

(d) Wage period. 

(e) Total amount not paid, 

(f) Reason for not making payment. 

(g) How the amount of unpaid wages was utilized. 




(h) Acquaintance with date

8. 
Register of Accidents 


The Contractor shall maintain a register of accidents in such form as may be convenient at the work place but the same include the following particulars: 
(a) Full particulars of the labourers who met with accident. 

(b) Rate of wages. 

(c) Sex

(d) Age

(e) Nature of accident and cause of accident. 

(f) Time and date of accident.

(g) Date & time when admitted in hospital 

(h) Date of discharge from the hospital 

(i) Period of treatment and result of treatment. 

(j) Percentage of loss of earning capacity and disability as assessed by Medical Officer.

(k) Claim required to be paid under Workmen’s Compensation Act. 

(l) Date of payment with details of the person to whom the same was paid. 

(m) Amount paid. 

(n) Authority by which the compensation was assessed. 

(o) Remarks. 

9.
 Fines and deductions which may be made from Wages

The wages of a worker shall be paid to him without any deductions of any kind except the following. 

(a)
Fines. (List of acts and Omission for which fine can be imposed)


(i)
Willful subordination or disobedience, whether alone or in combination with another. 


(ii)
Theft, fraud, dishonesty in connection with Contractor’s business or property of the D.D.A.


(iii)
Taking or giving bribes or any illegal gratification. 


(iv)
Habitual late attendance 


(v)
Drunkenness’, fighting, riotous or indecent behavior. 


(vi)
Smoking near or around the area where combustible or other materials are stacked.


(vii)
Habitual negligence. 


(viii)
Habitual indiscipline. 


(ix)
Causing damage to work in progress or to property of the DDA or the Contractor. 


(x)
Sleeping on duty. 


(xi)
Malingering or slowing down work. 


(xii)
Giving false information regarding name, age, father’s name etc. 


(xiii)
Habitual loss of wages cards supplied by the employers. 


(xiv)
Unauthorized use of employer’s property or manufacturing, or making 
of unauthorized articles at the work place. 


(xv)
Bad workmanship in constructions and maintenance by skilled workers 
which is not approved by the Department and for which Contractors  
are compelled to undertake rectification. 


(xvi)
Making false complaints and/or misleading statements. 


(xvii)
Engaging in trade with in the premises of the establishment. 

(xviii)
Any unauthorized divulgence of business affairs of the employers 


(xix)
Collection or canvassing for the collection of any money within the premises of any establishment unless authorized by the employers. 


(xx)
Holding Meeting inside the premises without previous sanction of the employer.


(xxi)    Threatening or intimidating any workman or employee during the working hours within the premises.

(b)
Deduction for absence from the duty, i.e. from the place or places, where by the terms of his employment, he is required to work. The amount of deduction shall be in proportion to the period for which he/she was absent.

 (c)
Deduction for damage or loss of goods expressly entrusted to the employed person, for custody, or for loss of money or any other deduction which he is required to account, where such damages or loss is directly attributable to his neglect or default.

(d)
Deduction for recovery of advances or for adjustment of over payment of wages, advances granted shall be entered in a register. 

(e)
(i) 
Any other deduction, which the Central Government may from time to  time allow.


(ii) 
No fine should be imposed on any worker save in respect of such acts and omissions on his part as have been approved by the Chief Labour Commissioner.


(iii) 
No fine shall be imposed on a worker and no deduction for damage or loss shall be made from his wages until worker has been given an 
opportunity for showing cause against such fines or deductions.


(iv) 
The total amount of fine which may be imposed in any one wage period on a worker shall not exceed an amount of three paise in a rupee of the total wages, payable to him in respect of that period.


 (v) 
No fine imposed on any worker shall be recovered from him by installment or after the expiry of sixty days from the day on which it was imposed.


(vi) 
Every fine shall be deemed to have been imposed on the day of the Act or  omission in respect of which it is imposed. 





10
Register of fines, etc.

(i)
The Contractor shall maintain a register of fines and a register of deduction for damage or loss in form Nos. 1 and 2 respectively which should be kept at the place of work.

(ii) 
The Contractor shall maintain,  both in  English and the local Indian Language, a list approved by the Chief Commissioner, clearly stating the Act of Omission for which penalty, or fine can be imposed on a workman and display it in a good condition in a conspicuous place on the work. 


11
Preservation of Registers.


The wage book, the wage slips, the register of unpaid wages, the registers of accidents, the registers of fines, reduction required to be maintained under these regulations shall be preserved for 12 months after the date of last entry made in the end and shall be made available for inspection by the Engineer-in-Charge, or Labour Welfare Officer or any other officer, authorized by Ministry of Urban affairs & Employment Government of India in this behalf.

12 
Power of Labour Welfare Officer to make investigations or Enquiry 


The Labour Welfare Officer or any other person authorized by the Central Government on their behalf shall have power to make enquiries with a view to ascertain and enforce due and proper observance of the fair wage clauses and provisions of these regulations. He shall investigate into any complaint regarding the default made by the Contractor or Sub-Contractor in regard to such provisions.

13
Report of Labour Welfare Officer 


The Labour Welfare Officer or any other person authorized as aforesaid shall submit a report of his investigation or enquiries to the Executive Engineer concerned indicating the extent, if any to which the default has been committed with a note that necessary deduction from the Contractor’s bill be made and the wages and other dues be paid to the labourers concerned. In case an appeal is made by the Contractor under clause 14 of these regulations actual payment of labourers will be made by the Executive Engineer after the Regional Labour Commissioner has given his decision on such appeal.


a)
The Executive Engineer shall arrange payment to the labourers concerned within 45 days from the receipt of the report from the Labour Welfare Officer or the Regional Labour Commissioner as the case may be.

14. 
Appeal against decision of Labour Welfare Officer. 


Any person aggrieved by the decision and recommendations of the Labour Welfare Officer or other person so authorized may appeal against such decision to the Regional Labour Commissioner within 30 days from the date of decision, forwarding simultaneously a copy of his appeal to the Executive Engineer concerned but subject to such appeal, the decision of the Officer shall be final and binding upon the Contractor.

15. 
Prohibition regarding representation

(i)
A workman shall be entitled to be represented in any investigation or enquiry under these regulations by:

(a)
An officer of the Registered Trade Union of which he is a member.

(b)
An officer of federation of Trade Unions to which the trade referred to in clause (a) is affiliated. 

(c)
Where the employer is not a member of any registered trade union, by an officer of a Registered Trade Unions, connected with the Industry in which the worker is employed or any other workman employed in the Industry in which the worker  is employed. 


(ii)
An employer shall be entitled to be represented in any investigation or enquiry under 
these regulations by:
(a) 
An officer of an association of employers of which he is a member. 
(b)
An officer of  federation of associations of employers to which association referred to in clause (a) is affiliated.

(c)
Where the employer is not a member of any association of employers by an officer of Association of employer connected with the industry in which the employer is engaged or other employer, engaged in the Industry in which the employer is engaged. 


(iii)
No party shall be entitled to be represented by a legal practitioner in any investigation or Enquiry under these regulations. 

16.
Inspections of books and slip 


The Contractor shall allow inspection of the wages books and the wage slips, the register of unpaid wages, the register of accidents, and the register of fines and deduction to any of his workers, or to his agent at a convenient time and place after due notice is received from the Labour Welfare Officer or any person authorized by the Central Govt. on his behalf.

17.
Submission of Returns: 


The Contractor shall submit periodical returns as may be specified from the time to time.

18.
Amendments: 


The Central Government may from time to time add to or amend the regulations and or any questions as to the application/interpretation or effect of those regulations. Decision of the Chief Labour Commissioner or Deputy Labour Commissioner, the Government of the India or any persons authorized by the Central Government on that behalf shall be final. 


Annexture to Additional condition 34(i) showing quantities of meaterials of aras of road roller of surfacing to be considered for working out the minimum period for which hire charge are to be recovered. 

	S.No.
	Materials of surfacing
	Quantities

	1.
	Consolidation of earth sub-grade
	1860 Sqm.

	2.
	Consolidation of sub base with 90mm to 45mm graded stone metal.
	42 Cum.

	3
	Consolidation of wearing coat of stone ballast 7.5 cm. to 11.5 cm. thick.
	30 Cum.

	4
	Consolidation of wearing coat of brick ballast 10 cm. thick.
	60 Cum.

	5
	Spreading and consolidation of red Bajri 6mm.
	1860  Cum.

	6
	Painting one coat using stone aggregate 13.2mm nominal size 

(a) 
@ 1.65 cum. per 100 Sqm. and paving bitumen A-90 or S-90 @ 2.25 
Kg. per Sqm. or 

(b)
@ 1.5 cum. per 100 Sqm. bitumen emulsion or road tar @ 1.95 Kg. 
per Sqm.
	930 Sqm.

	7
	Painting two coats using:

(a)
For first stone aggregate 13.2mm. Nominal size.

(i)
@ 1.5 cum. per 100 Sqm. with paving bitumen A-90 or S-90 @ 2 kg./Sqm.

(ii)
@ 1.35 cm. per 100 Sqm. with paving bitumen emulsion @ 2kg/Sqm. or

(iii)
@ 1.5 cm. per 100 Sqm. with tar @ 2.25 Kg./Sqm.
	600 Sqm.

	
	(b)
For 2nd coat, stone aggregate 11.2mm nominal size 1.0 cum per 100 Sqm. with

(i)
One kg. of paving bitumen A-90 or S-90 or bitumen emulsion per Sqm. of

(ii)
1.25 Kg. of bitumen emulsion per Sqm.
	1670 Sqm.

	8
	Repainting with stone aggregate 11.2mm nominal size 0.9 cum. per 100 Sqm. with 

(a) 
1.10 Kg. of paving bitumen A-90 or S-90 or bitumen emulsion per Sqm. or 

(b)
1.22 Kg. of bitumen emulsion per Sqm.
	1670 Sqm.

	9
	2-cm. premix carpet surfacing using 2.4 cum. of stone aggregate 11.2mm. Nominal size per 100 Sqm. and binding including tack-coat the binder being paving bitumen S-90 or hot cut back bitumen or bitumen emulsion @ 96 Kg. / cum. of agg. in specified quantities.
	930 Sqm.

	10
	2.5 cm thick premix carpet surfacing using 3 cm. of stone aggregate 11.2mm nominal size per 100 Sqm. and binder including tack-coat the binder being paving bitumen S-90 or not cut back bitumen emulsion in specified quantities.
	930 Sqm.

	11
	4 cm. thick concrete surfacing using stone aggregate 3.8 cum. (69% 20mm nominal size and 40% 12.5mm nominal size) per 100 Sqm. and coarse sand 1.90 cum. per 100 Sqm. and hot cut back bitumen over a tack coat of hot cut back bitumen.
	370 Sqm.

	12
	5 cm. thick bitumen concrete surfacing using stone aggregate 4.8 cum. (60% 40mm nominal size and 40% 20mm nominal size) per 100 Sqm. and coarse sand 2.4 cum. per 100 Sqm. and hot cut back bitumen over a tack coat of hot cut back bitumen.
	370 Sqm.

	13
	6mm thick bitumen concrete surfacing using stone aggregate 5.8 cum. (60% 40mm nominal size and 40% 25mm nominal size) per 100 Sqm. and coarse sand 2.9 cum. per 100 Sqm. and hot cut back bitumen over a tack coat of hot cut back bitumen @ 50 Kg. per cum of aggregate.
	280 Sqm.

	14
	7.5 cum. bitumen concrete surfacing using stone aggregate, 7.3 cum. (60% 50mm nominal size and 40% 40mm nominal size), per 100 Sqm. and hot cut back bitumen over a tack-coat of hot cut back bitumen, and coarse sand @ 3.6 cum. per 100 Sqm.
	230 Sqm.

	15
	2.5 cum. bitumastic sheet using stone aggregate 1.65 cum. (60% 13.2 mm nominal size, 40% 11.2mm nominal size) per 100 Sqm. and coarse sand 1.65 cum. per 100 Sqm. and hot cut bitumen over a tack-coat of hot cut back bitumen.
	230 Sqm.

	16
	4 cm. bitumastic sheet using stone aggregate 2.6 cum. (60% 13.2mm nominal size 40% 11.2mm nominal size) per 100 Sqm. coarse sand 2.6 cum. per 100 Sqm. and hot cut back bitumen over a tack coat of hot bitumen.
	560 Sqm.

	17
	Laying full grouted surface using stone aggregate 40mm nominal size 6.10 cum. per 100 Sqm. with binder, binding with 40mm nominal size 1.83 cum. pr 100 Sqm. and seal coat of binder and stone grit 11.2mm nominal size 1.07 cum. /100 Sqm. the binder being hot bitumen or tar, as specified.
	460 Sqm.

	18
	Laying full grouted surface using stone aggregate 50mm nominal size 9.14 cum. per 100 Sqm. with binder,  binding with 40mm nominal size 1.83 cum. per 100 Sqm. and seal coat of /binder and stone grit 11.2 mm nominal size 1.07 cum/100 Sqm. the binder being hot bitumen or tar.
	370 Sqm.

	19
	4cm. thick premix macadam surfacing using stone aggregate 25mm nominal size 4.57 cum. per 100 Sqm and bitumen binding with stone aggregate 13.2 mm nominal size 1.52 cum. per 100 Sqm. and seal coat of hot bitumen stone aggregate 11.2 mm nominal size. 1.07 cum. per 100 Sqm.
	560 Sqm.

	20
	5 cm. thick premix macadam surfacing with stone aggregate 25mm nominal size 6.10 cum per 100 Sqm. and hot bitumen binding with stone aggregate 13.2 nominal size 1.52 cum. per 100 Sqm. and seal coat of hot bitumen and stone aggregate 11.2mm nominal size 1.07 cum. /100 Sqm.
	460 Sqm.

	21.
	Seal coat to premix and with paving bitumen S-90 using 128 kg of bitumen per. cum of sand and 0.75 cubic m. sand per hundred Sqm. of road surface.
	1860 Sqm.

	22.
	Consolidation of granular sub base course with power vibratory roller.
	133 cum.

	023.
	Consolidation of CC 1:4:8 base course with power vibratory roller.
	133 cum.


SPECIFITION AND CONDITIONS

GENERAL :

1.
The contractor must get acquainted with the proposed site for the works and study specifications and conditions carefully before tendering. The work shall be executed as per programme approved by the Engineer-in-charge.  If part of site is not available for any reason or there is some unavoidable delay in supply of materials stipulated by the Department, the programme of construction shall be modified accordingly and the contractor shall have no claim for any extras or compensation on this account.

2.
Periphery of works areas shall be the area shown in the layout plan of the scheme :

Specification : 

3.1
Specification to be followed for execution of work shall be :

3.1.1.
The entire work shall be done as per CPWD specification 1996 vol.1 to VI upto date correction slip, most specification and Revised CPWD specification 2002 for cmenet, concrete, RCC and cement mortar or General Specifications for Electrical works (part-I Int. 2005) and (Part-II Ext. 1994) with uptodate C.S. till date of opening of tender. 


However in ase of any discrepancy in the description of any item as given in the schedule of quantities appended with the tender and the specification relating to the relevant item as per CPWD specifications srelations 1996 vol.I to VI and CPWD specification 2002 for cement, concrete, RCC and cement mortar or General Specifications for Electrical works (Part-I Int. 2005) and (part-II Ex. 1994) with upto date C.S.  The former shall prevail the speciicaions for any items are not available in the CPWD specifications referred above, relevant B.I.S. specifications shall be followed in case BIS specification are also not available, the decision of the Engineer-in-charge shall be final, whenver any reference to any inian standard specificatiooccurs in the documents relating to the contract the same shall be inclusive of all the amendments issued there to or revisions sthereof if any, upto the dte of receipt of tenders. 

3.1.2.
Samples of all building materials doors and windows fittings sanitary wares and other articles required for execution of works shall be got approved from Engineer-in-charge Article manufactured by firms of repute and approved by the Engineer-in-charge shall only be used.  Articles classified as first quality by the manufacture shall be used unless otherwise specified. 


Prefernece shall be given to those articles which bear I.S.I. Certification mark.  In case articles bearing I.S.I. Certification mark are not available, the quality of samples brought by the contractor shall bejudged by the standard laid in the relevant I.S.I. Specifications all material and articles brought by the contractor to the site for use shall confirm to the samples approved which shall be preserved til the completion of the work.

3.1.3.
The work will be carried out in the manner complying in all respects with the requirement of relevant by laws of the local body under the Jurisdiction of which the work is to be executed or as directed by the Engineer-in-charge and nothing extra will be paid on this account. 

3.1.4
The contractor shall have a performance tests for the enire installations as per standards/ specifications before the work is finally accepted and nothing whatsoever shall be payable to the contractor without such test. 

3.1.5
The junior Engineer should maintain the Register for cement paint and other registers as require by the Engineer-in-charge and these should be signed by the contractor or his autorised agent and the Junior Engineer-in-charge of the work.

3.1.6.
The contractor shall leave such recesses, holes, openings etc. as may be required for the electric and sanitary works by providing PVC scrubs at appropriate level and directions and nothing extra shall be paid on the work.

3.1.7.
The work of electrification, horticulture and other internal and external servies may be carried out simultaneously by other agencies with the work being tendered for against the enclosed contract documents.  The contractor shall afford necessary facilities for the same.

3.1.7A.  No claim in the matter shall be entertained and nothing extra over the agreement rates shall be paid for the same for fixing, laying/buying in the works pipes, cables conduits clamps boxes or hooks for fan clamps etc.

3.1.8
The contractor shall make his own arrangement for temporary electric connection if required and make necessary payment for it direct to the department concerned.

3.1.9
The contractor shall be required to do the work of development before taking upto building work, as per the direction of the Engineer-in-charge.

3.2
Specific provisions in the wording of items in the schedule of quantities shall have precedence over 3.1.1 and 3.1.2.

3.3
The bricks brought by the contractor including those classified as first class in the local market shall be classified shown in the permit (where there is a permit system) under which the contractor might obtain the material.

3.4(a)
Material bearing B.I.S. Marks shall be given first preference for incorporation in the work.  Whenever ISI marked materials are available the same only shall be used.  In case where articles of different makes and designs bearing BIS mark are available in the market the decision of the Engineer-in-charge abut a particular make and design to be used in the work shall be final and binding.   In case where articles with B.I.S. mark are not available in the market, the quality shall have to conform to relevant B.I.S. specification.

3.4(b)
Materials for which B.I.S. has licensed use of B.I.S. certification mark only materials bearing B.I.S. certiition mark only material bearing ISI certification mark are available the decision of the Engineer-in-charge about the design to be used in the work shall be final and binding on the contractor where articles with B.I.S. certification mark are not available the quantity shall confirm to the relevant CPWD specification/ISI specification or as approved by the Engineer-in-charge.

3.5
Immediately after the award of works, the contractor shall produe samples of all materils be used and incorporated in the works for approval samples shall used in the works.

3.6
The structgural and architectural drawings shall, at all times, be properly correlated for executing any work Architecture requirement shall be fully satisfied where specific mention is made of Architects Design, Architects approval etc.  Samples shall be prepared for approval before starting the work on any item specified by the Engineer-in-charge.

3.7
For all precast concrete work on an unyielding platform with smooth finished surface shall be made.  The member shall have to be cash in approved rigid moulds.  Use of bricks loose plank sand battens and similar non-rigid side of moulds shall not be permitted.  Vibrators must be used for compaction of concrete.  All facts of the members must come out smooth.  Curing shall be either under water or by covering with wet gunny bags for minimum 14 days.  For all types of cement work with Hopper mixed shall be used in the work.


(a)
For all type of cement work, Hopper mixture shall beused in the work.

3.8
The hinges of door shutters shall be welded to angle iron frames for full length and eyes and hooks shall be provided to such frames as per requirement.  Nothing extra shall be paid for this work or for providing wooden padding for fixing th fitting to shutters to suit angle iron frames rates for steel windows shall be fully deemed to exclude the cost of providing M.S. stays and windows fasteners of approved type each.  The rate of M.S. Grill shall cover all grill work provided.  No distinction shall be made between plain and ornamental grills for payment.  The grill should be welded along the full length of connected upto door and windows m.s.frame.

3.10
Rates for flooring item shall be inclusive of providing sunk flooring in bath room and kitchen.  However rounding the junction as provided in agreement item shall be paid for.

3.11
For various fitting in internal services, the dimensions given in the following table shall be maintained.


Item




Height   above
Distance   from





           
Floor level (mm)
face of wall (mm)

Bath Room


Bib Cock



  800



200


Shower Rose


2100



500


Stop Cock for Shower Rose.
1100





W.C.


Bib Cock



 250



100

Other fittings


Wash basin front Edge
             800


Mirror: Bottom

           1260


Top




1800


Glass Shelf



1050


Towel Rail



-


Kitchen Sink



  800


Kitchen



  500



200

3.12.
Welding wherever required in the structure like grill railing and truss shall be done for full lengh ttuck welding is not allowed.
3.13.
Unless otherwise specified rates quoted by the contractor shall hold for work at all heights and depths.  The contractor shall not be paid on any thing extra for maintaing in good cordition all the work executed till completion of the entire work; nor on account of damage to the works caused by rains or other natural phenomenon during the execution of works. 

3.14
The G.I. fitting shall be of same specification as G.I.B.Clas pipe.


(a)
The G.I. fittings shall be of same specification of G.I.B. Class pipe.


(b)
Course sand (badarpur ) will be used after washing in case sislt contents is beyond permissible limit.


©
Short pipe nipple lused in work should be of same grade and specification as prescribed for G.I.Pipe. 


(d)
Full wlding of steel section of grills along the contract area with frames but hings to be welded with frames. 

3.15
Collection and stacking of mateials shall include all leads. The rates quoted by the contractor shall hold good irrespectrive of the source from which the materials are brought so long as they conform to the specification.  Clousre of aprticuars quarry will not entitled to any revisions in rates. 

3.16 The contractor shall be responsible for which and ward of shutters and materials issued to him/ handed over to him by the deparment and nothing shall bepaid extra to him for this.

3.17
Centring and shuttering require for R.C.C. slab, beam and column etc. for more than single height shall be done by the contractor as per approved drawings issued by the Engineer-in-charge.  Nothing extra beyond and Agrement rate shall paid for the same.  Rates are applicable for centring * shuttering done for all heights. 

3.17(a)
The rates to be quoted by the agency for stone lading and other exterior items shall include the cost of centring and shuttering scaffolding for execution of work andnothing extra shall be payable on this account.
3.18 The M.S. Flats clamps 6mm thick for bolting arrangement are be provide and welded as per site condition. The rate of angle iron door/windows frames is inludive of the cost of such clamp.  The door and windows fittings like hinges hooks and eyes are be welded to the M.S.Frames as required and nothing extra will be paid on this account and no deduction for not providing the eyes, hooks, bolts and sliding bolts etc. due to provisions of such camps shall be made. 

3.19 The flush door shutter shall be with B.i.S. specification mark and shall be obtained from suppliers on the approval list of C.P.W.D./DDA Coarse sand will be wsshed before used. 

3.20 The panel door shutters will be provided by the contractor themselves from the manufacturers only who will be in the approved list of DDA.

All times to be used for manufacture of doors, windows and ventilators shall be kiln seasoned to the required specified standards and approved kiln and the contractor shall produce a satisfactory proof of the name in writing the engineer in charge whose decision shall be final and binding. 

4.1 
The contractor shall carry out the work of sewer lines in close co-ordination with works of the services in the area. The contractor shall have no financial or other claims arising out of lack of co-ordination. 

4.2 
No payment shall be made for the excavation for RCC pipelines for the portions covered by excavation for construction of manholes. 

4.3 
Earth excavated from trenches shall be stacked at a distance from the top edge of excavation, equal to depth of the trench below ground level or equal to 1.5 m whichever is greater. 

4.4 
S.F.R.C. Covers should be engraved with date of manufacturing, name of manufacture and ISI mark and D.D.A. 

Work Under Sub-Soil Water. 

4.4.1 
The sub soil water level shall be determined and recorded at each manhole position before any de-watering is done and when there is at least of 25 cm depth of water in the trench. The average of the two levels will be taken as sub-soil water level for the length between the two manholes. 

4.4.2 
The depth below sub soil water level shall be measured to invert level of the pipe or the bottom of the concrete for relevant item. 

4.4.3 
Nothing extra shall be paid for the work under sub soil water level in case of manhole for all depth. 

4.5 
The contractor shall carry out disc test on all sewer lines and satisfy the Engineer-In-Charge that the line are absolutely clear. Any obstruction shall be removed by the contractor without any claim for extras. Decision of the Engineer-In-Charge with regards to disc test and cleaning of the lines shall be final. 
4.6
The contractor will not be required to carry out testing of joints in the R.C.C. pipes laid below sub soil water level.  In such case C.C. 1:2:4 shall be provided all round joint of such pipes for length of 225 mm on either side of joints and nothing extra shall be paid.
5.
Services 

The contractor shall employ licensed plumbers for water supply and sanitary installation work and shall satisfy requirements including disc and other test, of the Municipal Corporation of Delhi in respect of the same. The contractor shall make his own arrangement for supply of Electricity and water required for the works. 

5.1
Cutting of holes in walls, floors, chhajjas, RC.C, slabs etc. The tendered rate shall include the cost of cutting holes wherever required making good the same nothing extra shall be paid for this.  

5.2
Wherever necessary the S.C.I. Pipes and G.1. Pipes shall be fixed in R.C.C. columns, beams etc. with scrub plugs and nothing extra shall' be paid for it. 

5.3
The contractor shall be responsible for the protection of all sanitary water supply fittings and fixtures against pilferage and breakage during the period of installation until the completion of the work. 

5.4
G.I. Pipes as stipulated in the schedule of materials can be issued in the inches or it's equivalent metric size as considered fit by store division and the issue rates as recoverable from the contractor will remain the same. 
 

5.5
The contractor will not paid extra on this account and nothing will be deducted for using metric size of G I. pipes used from central stores Division and the item will be paid as per agreement rate for the same item.

5.6
The rates of base ties is included in the item of M.S door/ pressed door frame and nothing extra shall be paid. 

6.
Appliances 

The contractor shall at no extra cost, provide at site appliances such as weighing scale, graduated cylinder, standard sieves, slumps cones, C.I .. or M.S. test tube moulds, caliper, tapes etc. for site testing of materials and work. 

7.
Bricks 

The contractor will make his own arrangement for the entire quantity of bricks required for the work. Quality of brick shall be judged as per specifications and brickwork is to be done with F.P.S. Bricks.

8.
Labour Tents
The contractor shall put the tents for labour as per the conditions of contract, only in the area indicated on the plan and demarcated on the ground by the Engineer-In-Charge. The final bill shall not be paid unless all the tents are cleared form the site. 

9. 
Shops

Restaurants, Teashops or kiosks shall not be allowed to put up by the contractor in the works area in the labour, area. Temporary kiosk(s) put up by the Engineer-In-Charge shall be taken by the contractor on lease which is to be determined on the date of completion or termination of contract whichever is earlier and the rate of Rs.30.00 per kiosk per month shall be recovered from the contractor from the bill paid. On date of completion of the work or termination of contract whichever is earlier, the kiosk(s) shall be vacated by the contractor and a vacant possession shall be given over to the Engineer-In-Charge failing which penalty shall be levied on the contractor at the rate of Rs.150.00 per day of delay involved. 

10.
Drawings 

The drawing referred to in the tender documents are available for inspection of intending tenders in the office of the Executive Engineer. Tenderers shall inspect the same and acquit themselves with work to be executed. Tenderers shall be desired to have these drawings, which shall be included as part of the agreement with the tenderer whose tender is finally accepted. The contractor shall have no claim with reference to these drawings in respect of any of the rates after acceptance of the tender. 

11.
Testing of Materials
For the tests conducted in DDA labs the testing charges will notbe borne the agency however when tests are conduced from Lab other than DDA the testing charges shall be borne by the agency in case they fail otherwise they will be borne by DDA.  The packing, transportation, cost of material will be borne by the agency/contractor any testing charge of field tests done at site will be borne by the agency.  Water testing charges if any shall be borne by the contractor.  This supersedes all other conditions regading testing of materials. 

12. 
Safety Codes.


Safety pertaining to construction works, such as excavation, trenching, blasting, demolition, provision of scaffolds, ladder, working platforms, gangways, mixing of asphaltic materials, electric and gas welding, use of hoisting and contraction machinery shall be governed by the relevant provision of C.P.W.D. safety codes (agreement form) or as directed by the Engineer-In-Charge. Contractors shall provide corrugated sheeting duly painted with red and white 'Strips around area where any digging work or another work for laying pipes, cables etc. which is to be Carried out on the roads. Contractor will install warning lights in order to give proper warning to the vehicle and pedestrians at night. 

12. (a) The excavated earth shall be dumped at a safe place as per the direction of the Engineer-In-Charge for which he will not claim any thing extra on this account. . 

13.
Additional Conditions 

G.I. pipes of various size as specified if stipulated will be issued by the department from D.D.A stores only for item of water supply and sanitary installation. For other item involving the use of G.I. pipes and M.S. pipes of various size' such as hand rails. Rain water pipes, spouts & flush pipe etc. The contractor shall make his own arrangement and no extra claim on this account will be enlisted  by the Department.  Short pipe nipples provided by the contractor in G.I. pipe lines shall be of G.I.pipe. 
. 

14.
Fire Hydrant shall conform to IS909-1975: 

15. 
The contactor shall be required 'to submit the detailed programme for completion of work within the stipulated period in the form of a bar chat, covering all major activities to the Engineer-In-Charge with in 15 days from the date of start of work. Any modification suggested by the Engineer-In-Charge shall .be incorporated in the, Bar Chart. It will be ensured by the contractor that the time schedule laid in the aforesaid Bar Chart is adhered to. In case of any slippage, the time lost, will have to be made good by the contractor by speeding up the activities. In such cases he shall be bound to follow the revised programme decided by the Engineer -In-Charge. 

16.
The rate of all item of work shall be clearly specified otherwise include the cost of all material labour etc. involves in execution of the items. 
17. 
The surface having finished rough sponge and with the uniform texture the sample of such plaster should be prepared by the contractor and got approved by the Engineer-in-Charge before undertaking mass work. 

18. 
The contractor shall be required to use only mechanical mixer (s) with fitting hopper (s) for mixing cement concrete required for R.C.C. works/ cement concrete works. 

Design Mix


a)
All R.C. work shall be as per approved design mix.  All the provision of IS 456-2000 shall be followed.


b)
The contractor shall install automatic batching plant of adequate capacity at site of work.

c)
Only steel string shall be used as per provisions under para 5.2 & 15 sub-paras of CPWD specification 1996.


d)
The Cement consumption for the design mix M-25 shall be as per CPWD, Delhi Schedule ofrates 2002 subject to minimum of 410 Kg. per cub.m. and as per IS code 456-2000.  In case the actual use of quantity of cement being less than as specified in CPWD, Delhi Schedule of Rate 2002, then appropriate recovery will be effected.

19. 
The material will be issued to the contractor at the place of delivery as mentioned in the schedule of materials. If these are delivered at any other site difference due to cartage will be adjusted accordingly. The contractor shall have to cart at his cost materials to the site of work as soon as these are issued. The material will be issued between the working hours and as per rules of D.D.A. godowns as framed from time to time. 

20.
The contractor shall bear all incidental charge for cartage, storage and safe custody of materials. 

21. 
All materials obtained from D.DA stores or otherwise shall be got checked by the Engineer-in-Charge of the works on receipt of the same at site before use. 

22. 
No payment will be made to the contractors for damage caused by the rains and other natural calamities during the execution of works and no such claims on this account will be entertained. 

23. 
The water will be tested with regard to it's suitability for use in RC.C. work and nothing extra shall be paid on this account. 

24. 
The contractor will submit to the Engineer-in-charge PERT chart within fifteen days from the date of start of the work for completing the same within the stipulated period. The contractor shall follow the PERT chart strictly and no deviation whatsoever shall be allowed therefrom. If the contractor fails to submit the PERT chart, the Engineer -In-Charge shall get it prepared at the risk and cost of the contractor. 

25. 
The scaffolding for doing the brick works for all external walls shall be done from outside. The supports shall be sound and strong, tied together with the horizontal pieces. The holes for horizontal scaffolding pole shall be provided only in the header course. The holes in the masonary work for supporting the scaffolding shall be filled and made good before plastering The contractor shall responsible for providing and maintaining sufficiently strong scaffolding so as withstand all loads likely to come upon it. Nothing extra is payable on this account. 
Due care shall be taken by the contractor to ensure of brick mansonary walls in plumbs. The outer face of the building shall be kept as true face. 

26. 
The contractor shall complete one sample house in all respects within 90 days from the start of the work.  On complete block of houses selected by Engineer-in-charge shall be completed within 180 days of the start of the work as directed by the Engineer -In-Charge.

27. 
The item of External plastering shall be taken after getting the approval of the Engineer-In-Charge. The item of external finishing if got executed from another agency may need a. close co-ordination between the items of external plastering and finishing for which the contractor shall have to work in close liaison with second agency as per direction of Engineer-In-Charge. 

The contractor shall be responsible for any activity, authorized or unauthorized going on with in the site area handed over to him by the department for construction, maintenance or for any other purpose. The contractor shall also be responsible for informing the Engineer-in-Charge in writing wherever his supervision is essential. Further this shall not be ground for seeking time extension in completion of the work and/or for claiming any loss and/or damage by the contractor all as the causes prolongation of completion of work. 

26. 
Levy of taxes. 

(i) 
Tendered rates are inclusive of all taxes and levies payable under the respective statutes. However pursuant to the constitution act, 1982, if any, further tax or levy is imposed by statute after date of receipt of tenders and the contractor there upon necessarily and properly pays such taxes /levies, the contractor shall be reimbursed the amount so paid provided such payment, if any, is not in the opinion of superintending Engineer (whose decision shall be final and binding) attribute to delay in execution of work under the control of the contractor. 

(ii) 
The contractor shall keep necessary books of accounts and other document .for the purpose of his condition as may be necessary and shall allow inspection of the same by a duly authorized representative of Govt and further he shall furnish such other information/ documents as the Engineer-in-Charge may require. 

(iii). 
The contractor shall within a period of 30 days of imposition of any further tax or levy, pursuant to the constitution Act. , 1982 give written notice there of to the Engineer in-charge that the same is given pursuant to this condition together with all necessary information relating thereto. 

27. 
Steel section/steel window shall be obtained from the approved manufactures. 
28.
Sand Cast Iron Pipes and A.C. Pipes.


Only ISI marked sand cast iron pipes and fittings A.C. pipes and accessories shall be allowed to be used in the work.
Design Mix


a)
All R.C. work shall be as per approved design mix.  All the provision of IS 456-2000 shall be followed.


b)
The contractor shall install automatic batching plant of adequate capacity at site of work.


c)
Only steel string shall be used as per provisions under para 5.2 & 15 sub-paras of CPWD specification 1996.


d)
The Cement consumption for the design mix M-25 shall be as per CPWD, Delhi Schedule ofrates 2002 subject to minimum of 410 Kg. per cub.m. and as per IS code 456-2000.  In case the actual use of quantity of cement being less than as specified in CPWD, Delhi Schedule of Rate 2002, then appropriate recovery will be effected.

SPECIAL CONDITION
Water Storage Tanks: 

(i) 
The H.D.P.E. water storage tanks should be F.DA (food Drug addition) approved and tested by C.B.R.I Roorkee and Public Health engineering labouratory. If necessary The Engineer-In-Charge will be at liberty to get the tanks tested for the various tests laid down by test house approved by the Engineer-In -charge to ensure their strength and suitability for strong portable water, The testing and other incidental charges shall, however be borne by the contractor and contractor shall also provide the guarantee covered by the manufacturer and same shall duly endorsed to the D.DA with manufacturer's guarantee for all the above materials. 
(ii) 
Barricading of excavated trenches on both sides of the trench to the height of 1.60 meters with galvanized steel plain sheet of 1.00 mm. thick (class-1) fixed on 100 mm. dia sal Ballies 3m. apart with nails etc. will be done by contractor as a safety measure and nothing extra will be paid for. He will also provide red strips on sheets with aluminous paint 75 mm wide alternatively on outside of sheet vertically and no extra payment will be made on this account. 
(iii) 
Any permission, if required from police authorities or other departments for closing or cutting of the road will be obtained by the contractor at his own. He will have no claim for any financial loss or extension of time on this account. 

(iv) 
The agreement item provides for white glazed tiles, coloured tiles, however be used as per the direction of Engineer-In-Charge if these tiles are available at the rate of white glazed tiles. In such case no extra, payment shall be admissible. 

(v) 
The rates of all item of work shall be, unless already specified otherwise, included cost of all labour and material involved in the execution of item. 

ADDITIONAL CONDITIONS
1. 
The contractor shall give a performance test of the entire installations as per standard specification before the work is finally accepted and nothing extra whatsoever, shall be payable to the contractor for the test. 

2.
Mild Steel and cold twisted deformed bars shall be payable to the contractor for thetest where stipulated will be issued ion lengths shapes and sizes available in the stores.  No claim of extra payment etc. on this account shall be entertained.
3. 
Any cement slurry added over base surface for continuation of concreting for better bond is deemed to have been included in the item (unless otherwise specified) and nothing extra shall be payable for extra cement consumption on this account. 

4. 
In case there is any discrepancy in frequency of testing as given in the list of mandatory tests and that in individual sub-heads of work as per C.P.W.D. specification 1996,/2002 Vol-1 to VI, with up to date correction slips (higher of two frequencies of the testing shall be followed) and nothing extra shall be payable to the contractor on this account. 
. 
5.
Weep holes and expansion joints whenever required in S.W.Drains may be provided at suitable intervals as per specification.  Nothing extra shall be paid on this account. 
GENERAL RULES ADDITIONAL CONDITIONS AND SPECIFICATRIONS
The following shall be read in conjunction with and constructed in reference to and in context of the General Rules, Specifications of Tender Documents and the condition here in contained and the requirement to be fulfilled without any extra charges and the contractor shall take all these into account while quoting the rates. 

5.(a) 
The field staff shall keep the record of initial levels and final levels of all low-lying areas. 

(b) 
The field staff shall ensure that the quantity of excavated earth disposed off by mechanical transport is dumped in the areas certified by the Engineer-In-Charge as low laying area shown on the enclosed layout. 

GENERAL
1.
Application of Specifications 

These specifications form part of the contract and shall be read in conjunction with other documents forming the contract, via the General Conditions of Contract, tender form, schedule of quantities and drawings. 

2.
Works included 

The rates for all items cover the cost of all materials, Labour, tools, machinery, plant, pumps, explosives, scaffolding staging, shores, props, bamboo, ropes, templates, page and all appliances and operations whatsoever necessary for efficient and proper execution of the work, in accordance with the specifications. 

3.
Executions of works 

The contractor is responsible for the correct execution of the work in accordance with the drawings provided to him He is also responsible for all mistakes due to working to wrong levels or centre lines, when levels, centre lines and bench mark of reference have been once intimated to him in writing by the Engineer-In-Charge It is his responsibility to record, project and maintain the said marks and to work to the same, and complaints shall afterwards to admitted for excess work done as a consequence of such levels not having been kept up and maintained by the contractor. 

4 
In case the contractor requires any clarification regarding specifications, conditions, drawing etc. The Engineer-In- Charge shall be contacted.

5.
Access to Site
The contractor is to include in his rates the cost of forming access to the site with all temporary roads and gangways required for the works. 

6.
Access for Inspection 

The contractor is to provide, at all times during the progress of the works and the maintenance period, proper means of access, with ladders, gangways etc. and other necessary attendant to move and adopt as directed for the inspection or measurements of the works by the Engineer-in-Charge or his authorized representative. 

7.
Specialized work 

The following specialized works shall be carried out by specialist persons or manufacturers with the written approval of the Engineer-in-Charge. 

(i) 
Stone & marble works 


(ii) 
Steel doors, windows and rolling shutters. 

(iii) Terrazzo tile flooring/mosaic flooring/ glazed tiles and ceramic tiles/ exposed 

aggregate finished plaster. 


(iv) 
Flush doors/fire doors. 


(v) 
Painting & polishing. 

(vi) Water proofing treatment of roof, terraces of balconies, sunken portions of toilets in all floor, water tank etc. 

8. 
Where the contractor is required to provide materials of certain sizes or weights which may have gone out of market due to change over to metric standards, substitutes conforming to the nearest equivalents on the higher side, as approved by the Engineer-in-Charge, shall be used. No claim of extra payment shall be entertained on this account. 

Instruments and equipment 

9. 
The contractor shall make the following available readily and in good working condition at site to ensure proper quality of work. Theodolite, Dumpy level with staff, steel tapes, stop watch, platform type weighing machine of 200Kgs.capacity, steel balance with weights, spring balance, slump cone with tamping rod, 15 cm. cube moulds, 24 Nos. Plumb Bob, spirit level, Vernier/Micrometer, Calibrated cylinder, Hammers, thermometer and standard compression testing machine for concrete cubes. 

10.
The layout, alignment and the orientation of the different members of the structural works should be carried out after thoroughly checking the drawing and obtaining clarification, if any from the Engineer-In-Charge. The setting out work should be carried out by the precision surveying instruments and got approved from the Engineer-In-Charge. The contractor shall arrange the necessary equipment and instruments. 

11.
Provision of Grooves 

The Engineer-In-Charge shall require (where he deems so necessary) to provide grooves of approved pattern between various surface such as timber/ plaster, exposed aggregate/ plaster/concrete/exposed concrete /brick work, ceiling /walls, skirting/plaster between various concreting operations of same or different members (particularly in the exposed concrete work) or as required etc. Such grooves shall be provided without extra charges and the contractor's rate for various items are deemed to include the cost of all labour, tools and materials required for making such grooves. 

12. 
Large sized details shall take precedence over small sized drawings. The contractor shall verify all dimension at site. 

13. 
Storage of materials 

The contractors shall store all materials in proper manner so as to avoid contamination and deterioration. The places at site where materials are to be stored shall be subject to the approval of the Engineer-in-Charge. The place where the materials are stored by the contractor be required by the Engineer-in-Charge for any other purpose, the contractor shall make arrangements to clear space within such time as may be instructed by the Engineer-in-Charge. 

14.
Permanent bench marks 

Where directed by the Engineer-IN-Charge, the contractor shall provide permanent bench marks. Likewise, any other levels or line or points specifically required by the Engineer-IN-Charge shall be built -in. The contractor shall carefully protect and preserve such important mark during execution of work. 

15.
Testing of materials 

The tests shall be carried out by the contractor at his own cost in laboratories approved by the Engineer-in-​Charge and as often as he may consider them necessary. Initially the cost shall be born by the contractor and shall be reimbursed to contractor in case test result confirms to required standards. Engineer-In-Charge may ask the contractor to install testing equipments at site for such test, which he may like to get tested at site himself. The Contractor shall ensure and certify the calibration of the equipment so installed and shall maintain the same in working order through out the period of construction. The contractor shall also provide necessary trained staff for carrying out such test and using such equipment. All tests shall be carried out under the supervision of the Engineer-in-Charge. 

16. 
The levels, measurements and other information concerning the existing site as shown in drawing or as described are supposed to be correct but the contractor shall verify them for himself, as no extra claim whatsoever shall be entertained on account of any change in such matters or on account of the description turning out to be different from what was expected. 

17. 
The rate of different items are for all heights, depths and widths unless otherwise specified in the items of schedule of Quantities attached. 

18.
Bailing out water 

The rate shall include cost bailing ·out water, rainwater, as well as sub soil water, and keeping the working place dry and -nothing extra on this account shall be paid. 

19.
Royalty 

Royalty for earth, boulders, metal, sand etc. shall be borne by the contractor and nothing extra on this account shall be paid to him. 

20. 
Safety Measures. 

The contractor shall provide necessary barriers, warming signals and other safety measures while cutting roads or laying pipe lines etc. or when ever otherwise necessary, so as to avoid accidents. He shall also indemnify the employer against claims for compensation arising out of negligence in this respect. These provisions are in addition to the safety measures already mentioned in the 
PWD-8 

21. 
All soil, filth or other matter of an offensive / obnoxious nature, taken out of any trench, sewer, drains, cesspool or other place, shall not be deposited on ether surface, but shall at once be carted away by the contractor to some pit or place provided to him as approved by the Engineer-IN-Charge. 

22. 
Water for construction purposes 

The water to be used for construction shall have to satisfy the requirement as per the Indian Standard codes. As soon as the Contractor has decided or located source of water, he shall be required to send samples of water for testing to laboratory approved by the Engineer -In-charge. Water shall be allowed for use for construction purposes, only if it satisfies the requirements of the Indian standard codes. In case, the water is found unsuitable for construction purposes, the contractor shall have to arrange water from alternative source. The samples for water have to be repeated at least once in every three months or earlier. 

23. 
Approval of samples of materials. 

Attention of the contractor is again drawn specifically to condition 3.5.of specification And Conditions" in the printed tender documents regarding approval of samples of materials to be used in work. Before placing a bulk order for any materials bringing any materials to site, the contractor shall have to bring a sample first and get it approved from the Engineer-in-Charge. Any material brought to site in contravention of this condition shall be rejected forth with and no payment will be made.

24. 
BAR CHART/CPM CHART 

Within 10/15 days from the date of award of work, the contractor shall have to submit a bar Chart/PERT chart /CPM chart to the Engineer-In-Charge indicating how contractor proposes to complete the work within the stipulated time as per the contract. The BAR CHART/CPM chart should clearly indicate the various constructions as well as various finishing items in the proper sequence of construction. Once this programme of construction has been submitted by the contractor and approved by the Engineer-in-Charge, the contractor shall have to abide by it and shall have to employ labour and bring materials consistent with the progress indicated in the chart. 


25. 
Inspection of works.

The work during the progress can also be inspected by the Chief technical Examiner/Technical Examiner from the Central Vigilance Commission or by the officer of the quality Control / Vigilance cell of the Delhi Development Authority on behalf of Engineer-in-Charge. 

26. 
Form work for exposed concrete 

Whenever directed by the Engineer-In-Charge with a view to obtain exposed face concrete by itself formwork shall have to be provided by the contractor in specific pattern as required and instructed. A sample of the exposed face finish shall be made by the contractor and the same shall be got approved before work is started. Due care shall taken while removing the form work. The time allowed for such shuttering shall be as decision of Engineer-in-Charge On removal of form work, the surface shall be rubbed with carborandum stone, so as to give a smooth finish and to match the surrounding surface. No patching up with cement plaster or otherwise shall be allowed. If however, any honey combs, broken edges, or ugly off sets, etc. are found, the contractor shall have to re-do the work without any extra charges. The material used for shuttering for exposed concrete shall be only timber with freshly sawn surface or as approved by the Engineer-In-Charge. 


27.
T.M.T. bars & MS round bars for steel reinforcement shall be issued only for reinforced cement concrete works related to Building portion including site development, landscaping water supply & sanitary installation and drainage works to be delivered to DDA.

28.
SCI pipes G.I. pipes and (Class L.A.) pipes shall be issued only for water supply, sewerage and drainage works to be delivered to D.D.A.
29.
WATER PROOFING

All areas where water proofing is to be done the waer proofing shall be got done through firm specialized in wter proofing work.

Building works of schedule of quantities pertaining to the building works shall be guaranteed against seepage/leakage for a period of ten years.  The contractor shall have to execute a performance bond in the prescribed proforma enclosed on page No.84 of tender documents water proofing compound of approved. 

30. 
The proportion of water proofing compound of approval mark to be used in cement shall be 2% by weight i.e. 1 kg. of chemical approval quality and manufacture shall be mixed with 100 kg. of cement or in the proportion recommended by the manufactures.  

31. 
Co-ordination with other Agencies 

The work of internal/external installation, lifts fire fighting installations etc. shall be carried out by the Department through other agencies with whom proper work co~ ordination as per direction of the Engineer-in-Charge shall be carried out. 

32. 
Steel work 

In item of steel door frames (pressed steel or T-iron frames) the rate includes cost of base tie or threshold and nothing extra is to be paid for the same. 

Rate for Similar items in different Section. 

33. 
For the convenience of execution and payment the schedule of quantities is divided into different section viz, (A) Building work (B) Site Development and Land Scaping works and (C) Sanitary Installation, water Supply and Drainage Works. 

Some item of work are repeated in different section. The lowest rate quoted by the contractor for such item of work in any section/ subhead of schedule of quantities shall be considered as the quoted rate for the item in all the' different section/ subhead for payment. 

(B)
Sanitary Installation water supply and drainage works. 

1. 
The contractor shall be responsible for getting the necessary test certificates from the concerned branch of Municipal Corporation and also to get connection for the drainage and water supply from the concerned branch of Municipal Corporation. 

2.
The work shall be done by licensed plumeber of Municipal Corporation and they must produce the copy of license as and when required before execution of work. 

3.
Holes and chases for concealed piping 

The cost of cutting holes, making chases and making good the same for concealed pipes and providing pipes for laying the internal sewer to gradient etc shall be included in the various item of work and nothing extra shall be paid on this account. 

4.
Damage to existing work. 

Any damage done by the contractor to any existing work during the course of execution of his work shall be made good by his own cost. 
 

5.
Prior Approval of Samples 


The samples of sanitary fitting, pipes and its fitting etc. shall be deposited with the Engineer-in-Charge (Which will be returned to the contractor at time of the completion of the work) and got approved by him before using in the work. Any, material rejected by the Engineer-in-Charge shall be removed from the site of work. 

6.
The work shall be executed as per the programme drawn or approved by the Engineer-in-Charge and it shall be also arranged as to have full co-ordination with the building work. Neither claim for idle labour shall entertained nor any claim on account of the delay in completion of the building work shall be entertained. 

7.
Testing of lines.
All pipeline laid by the contractor shall be tested as required under the specification to the entire satisfaction of the Engineer-In-Charge. The work shall not be treated as completed unless the lines are so tested. 

8.
All ferrule connections for water supply as well as meter connections shall be arranged by the contractor and payment of fees thereof if any shall also be made by him. The D.D.A. shall, however reimburse to the contractor such payments of fees paid to Government/ Municipal Corporation on presentation of bills.

9.
Watch and ward of fitting 

The contractor shall be responsible for the watch and ward of all fitting until the work is fully completed and handed over to the D.DA No claim on this account will be entertained. 

10.
The levels, measurement and other information concerning the existences of site as shown on the drawing or as described are supposed to be correct but the contractor shall verify them for himself and no extra claim, whatsoever, shall be entertained on account of any discrepancy or admission in such matters or on account of the description turning out to be different from what was expected. 
 

11.
Co-ordination with other works 
The work shall be done in conformity with the plans and within the requirements of the general Architectural, Air-Conditioning, Electrical and Structural Plans. This work shall be properly coordinated with the work of the other trades. Hangers and sleeves, structural opening shall be furnished in time for their installations as other work proceeds. 

12.
(a) The plumbing drawings are diagrammatic, but shall be followed as closely as actual construction and work permits. 

(b) The Architectural drawing shall be co-related with the plumbing drawings to all dimensions and shall be followed. 

13.a. 
The recommended positions of the fittings, fixtures control value, tanks etc. as shown on the drawing will be adhered to as far as possible. 

13.b. 
Should there be any discrepancy due to incomplete description / ambiguity or omission in the drawings and other documents, whether original or supplementary, forming the contract, either found on completion or during currency of the installation work, the contractor shall immediately, on discovering the same, draw the attention of the Engineer-In-Charge decision shall be final and binding on the contractor. 

14.
Completion Drawings 

The contractor shall submit one complete set of original and further two copies of additional drawings to the Engineer-In-Charge after completion of the work. The drawings must give with the following information. 

1)
Run of all pipes and diameter on all floors and vertical stacks. 

2)
Location and sizes of all control valves access panels and other equipments. 

3)
I.L of all manholes including I.L. at out falls. 

No completion certificate will be issued until the drawings as aforesaid are submitted by the contractor. 

15.
Testing of works materials 

The contractor shall preferably arrange the equipments and testing instruments in testing room. 

(a)
All testing shall be done as and when directed before the work is accepted. 

(b)
Upon notification that the work has been completed, the contractor shall make arrangements under the direction and in the presence of the Engineer-In-Charge or his representative, for inspection and test as shall be considered necessary to determine whether or not the full requirements of the specifications have been with. Any further test, if considered necessary, shall be carried out by the contractor at his own expense. 

(c) 
Contractor shall provide all testing equipment, labour and operating services required for these tests. 

(d) 
The above test shall be carried out by the contractor without any extra charge. 

(e) 
The contractor shall also provide all equipment, instrument, Labour, and such other allied assistance required by the Engineer-In-Charge for measurement of the work, materials etc. 

16. 
Any material supplied by the D.D.A, if damaged in any way during cartage or execution of work or otherwise, shall be made by the contractor at his own cost. 

17.
Recessed fittings 

Wherever recessed fitting are required to be provided, the contractor shall be responsible for keeping necessary recess in the building before and failing which he will have to make chases and recesses and make good the same with general finish at his own cost for which nothing extra shall be paid by the D.DA 

18. 
The contractor shall obtain for himself, on his responsibility and at his own expenses, all the Information which may be necessary for the purpose of making the tender before entering into a contract and must examine and study the specifications drawing, the design of the Sanitary Installation and also inspect the site the surroundings of the work and plan of the buildings. 

19.
Maintenance of Installations 

During the progress of the work, completed portions of the building may be occupied and put to by the D.DA but the contractor shall remain fully responsible for maintenance of the installations till the entire work covered by the contract is satisfactorily shall also covered the DDA with the manufacture guarantee for all the above materials.
20.
It is obligatory on the part of the contractor to remoe/shift the labour immediately after the work has been compled and the final payment shallbe released only thereafter.  No claim in installation of contractor’s bill shall be entertained on account of above.

21.
(a)
Separate godowns shall be provided for OPC & PPC storage.

(b) 
No PPC should be used in R.C.C. frame structure specially in the exposed portion like chhajjas, balconies, open terraces, top, roofs, extended beams, open stairs cases and slab beams in toilets; 

(c) 
Separate account should be maintained in cement register for receipt/ issue of OPC quantities of cement. 

(d) 
In the register of cement concrete cubes testing record type of cement must be specified. 

(e) 
The contractor shall be responsible for any activity authorized or unauthorized going on with in the site area handed over to him by department for construction development maintenance or for any other purpose. The contractor shall also be responsible for informing the Engineer-In Charge in writing wherever their supervision is essential further this not be ground for seeking time extension in completion of the work and/ or for claiming any loss and/ or damage by the contractor if at all this clause propagation completion of work. 
It is obligatory on the part of the contractor to remove/shift the labour immediately after the work has been completed and the final paypment shall be relesed only there after no claim in finalization of contractors bill shall be enetertained on account.
1.
ADJUSTMENT OF TAX CONSEQUENT UPON AMENDMENT TO CONSTITUTION. 

(i) 
Tendered rates are inclusive of all taxes and levies payable under the respective statutes However purusnat to the constitution (Forty sixth amendment) Act 1982 if any further tax or levy is imposed by stgatute after the date of receipt of tender and the concrete shall be reimbursed the amount so paid provided such payment of any is attributable to delay in execution of work within the control of the contractor.

(ii)
The contractor shall keep necessary books of account and other documents for the purpose of this condition as may be necessary and shall allowed inspection of the same by a duly authorized representative of Govt. and further shall furnish such other information documents as the Engineer-In Charge may require. 

(iii)
The contractor shall within a period of 30 days of imposition of any further tax or levy pursuant to the constitution Forty six amendment Act 1982 given a written notice together will all necessary information relating thereto.

EXTRA ADDITIONAL CONDITIONS 

1. Coarse Snad (bardarur) will be used after washing in case the silt contents is beyond permissible limit.

2. Short pipe nipple used in work should be of same grade and specification as prescribed for G.I. Pipe.

3. Full welding of steel section of grills along the contract area and with frames but hings to be welded with frames.
4. In case of any embiguity in the unit and nomenclature of any item in the agreement, unit/ nomenclature in the DSR applicable will be final.

Signature of Contractor

Name of work : Peripheral Development of integrated freight complex (IFC) at Narela including Bulk Services.

SH   :  Construction of boundary wall along Railway Line from 100mt. R/W Road to Railway Freight Terminal and raising of boundary wall along Village Bhoregarh to Alipur Road.

	S.No.
	Description of Item
	Qty.
	Unit
	Rate in Unit
	Place of delivery

	1.
	Ordinary Portland Cement
	381.0
	M.T.
	5175.00/MT
	Any DDA Store at Delhi, New Delhi

	2.
	Twisted  Deformed bars
	Nil
	M.T.
	Nil
	- do -

	3.
	M.S. Round Bars
	Nil
	M.T.
	Nil
	- do -

	4.
	Hoolock wood Panelled braced & battened and/or wire gauged shutters.
	Nil
	Sqm
	Nil
	To be supplied of cost Sqn at site of work

	5.
	S.C.I. Pipes

(a)
100 mm dia
	Nil
	Meter
	Nil
	Any DDA Store at Delhi, New Delhi

	
	(b)
75 mm dia
	Nil
	Meter
	Nil
	- do -

	
	(c)
50 mm dia
	Nil
	Meter
	Nil
	- do -

	6.
	G.I. Pipes

(a)
15 mm dia
	Nil
	Meter
	Nil
	- do -

	
	(b)
20 mm dia
	Nil
	Meter
	Nil
	- do -

	
	(c)
25 mm dia
	Nil
	Meter
	Nil
	- do -

	
	(d)
32 mm dia
	Nil
	Meter
	Nil
	- do -

	
	(e)
40 mm dia
	Nil
	Meter
	Nil
	- do -

	7.
	C.I. Pipe Class I.A.
	Nil
	Meter
	Nil
	- do -

	8
	Fluch Door shutters non-decorative 30/35 mm thick single and or double leaf.
	Nil
	Sqm
	Nil
	To be supplied of cost Sqn at site of work

	9.
	White Glazed Tiles 108* 108mm.
	Nil
	Nos.
	Nil
	Any DDA Store at Delhi, New Delhi

	10.
	Bitumen
	Nil
	MT.
	Nil
	- do -


Conditions

1.
The materials shall be issued to the contractor at the place of delivery mentioned against each item shown as above. Nothing shall be paid for cartage of the same to different sites as required and as directed by the Engineer-in-Charge.
2.
The issue rates mentioned in schedule of materials to be issued are inclusive of 2% storage charges.
3.
The penal rate recovery for the materials procured from store shall be double to the issue rate.
[image: image1.jpg]CUYPLCAL SKETCIH FOR CEMENT G;bDO‘«JL&'

. AL ORC, SHEET
R ALY KNI OF
ViEA HHIER PROOF

3 Lw B LOOE
il CARING i
. 3
“a
| '\u—.;
: I.L =i S icics
U LAY 2

et e UUdBOL
EARI

. - Cl n \‘_
s N
. Cv T X :
v ‘_.l',’"l s e,
N R :
' Lrant R - &
L . g 3 : -
} % @'/EE A7) C L(

P e






ANNEXTURE TO CLAUSE 34 (a) & (b)

	S.No.


	Description of plant & Machinery
	Hire Charges P.Day
	Place of issue

	
	
	
	


PERFORMA FOR PERFORMANCE BOND

 The agreement made this………………...day of……………..two Thousand……………………….and ............................... between Son of……………One part.) and the Chairman Delhi Development Authority Hereinafter called the Delhi Development Authority of the other part.) WHEREAS. This agreement is supplementary to a contract hereinafter called the Contractor dated………..and made between the GUARANTOR OF THIS ONE part and the Delhi Development Authority of the other part whereby the other whereby the contractor inter alia undertook to a contract (hereinafter called the Contractor) dated…………………………………….and made between the Guarantor of this one part and the Delhi Development Authority of the other part whereby the contractor interlaid undertook to render the buildings and structed in the said contract received completely water and leak -proof. AND WHEREAS THE guarantor agreed to give a guaranteed to the effect that the said structure will remain waterproofing treatment now THE GUARANTOR hereby guarantee that water proofing treatment given by him will render the structure completely leak proofing and the minimum life of such water proofing treatment shall be ten years to be reckoned from the date after the maintenance period prescribed in the contract. Provided that the guarantor will not be responsible for leakage caused by earthquake or structural defects or misuse of roof or alteration and for such purpose. 

(a) 
Misuse of rule shall means any operation which will damage water proofing Treatment like chopping of fire wood and things of the same nature which might Caused damage to roof. 

(b) 
Alteration shall mean construction of an additional story or a part of the roof or construction adjoining to existing roof where by water proofing treatment is removal in part. 

(c) The decision of the Engineer-In-Charge calling upon him rectify the defects failing which the work shall be got done by the department by some other contractor at the GUARANTOR risk and cost. The decision of the Engineer-in-Charge as to the cost payable by the guarantor shall be final and bindin. That if Guarantor fails execute the water proofing or commits breach there under then the Guarantor will immediately the Principle and his successors against all loss damage cost expense or otherwise which may be incurred by him by reason of any default on the part of the GUARANTOR in performance and observance of this supplementary agreement As to the amount of loss and/or damage and/or cost incurred by the Delhi Development Authority the decision of the Engineer-in-Charge will be final and binding on the parties. 

In witness where of these present have been executed by the obligor…………………………….and by……………………………………..and for and on behalf of the Delhi Development Authority on the month and year first above written. 

Signed Sealed and Delivered by OBLIGOR in the presence of 

1.
…………………………………………………………

2. 
…………………………………………………………

SIGNED FOR AND ON BEHALF OF THE DELHI DEVELOPMENT AUTHORITY BY…………………………………………………………………………in the presence of 

1. …………………………………………………………………………………………

2. …………………………………………………………………………………………

Annexure 

FROM OF PERFORMANCE SECURITY 

BANK GUARNTEE BOND

1. In consideration of the Lt. Governor of Delhi (hereinafter called "the DDA" having agreed under the terms and conditions of agreement no …………dated……………………………made between………………………………. and…………………………………………………………… (hereinafter called the said contractor(s)…………For the work………..………….(herein after called, the said agreement) having agreed to production of a irrecoverable Bank guarantee                      for…………………….. (Rupees………………………………only) as security/Guarantee from the contractor (s) for compliance of his obligations in accordance with the terms & conditions in the said agreement, we ..................................... (hereinafter referred to as "the Bank") (Indicate the name of the bank) here undertake to pay to the DDA an amount not exceeding Rs .………………………. (Rupees…………………………………………only) on demand by the DDA 

2. We ………………………
do hereby undertake to pay the amounts due and payable under this guarantee (Indicate the name of the Bank) 

Without any demure, merely on a demand from the DDA stating that the amount claimed is required to met the recovery due or likely to be due from the said contractor (s). Any such demand made on the Bank shall be conclusive as regards the amount due and payable by the Bank under this Guarantee. However, our liability under this guarantee shall be restricted to an amount not exceeding Rs…………………………………………..…………………only. 

3. We………………….. the said bank further undertake to pay to the DDA any money so demanded not withstanding any· disputed of disputes raised by the contractor (s) in any suit or proceeding pending before any court or Tribunal relating thereto out liability under this present being absolute and unequivocal. 

The payment so made by us under this bond shall be a valid discharge of our liability for payment there under and the contractor (s) shall have no claim against us for making such payment. 

4.  We…………………….. further agree that the guarantee herein contained shall remain in full force (indicate the name of the bank) and effect during the period that would be taken for the performance of the said agreement and that it shall continue to be enforceable till all the dues of the DDA under or by virtue of the said agreement have been fully paid and its claim satisfied or discharged or till Engineer-In-Charge on behalf of the DDA certified that the terms and conditions of the said agreement have been fully and properly carried out by the said contractor (s) and accordingly discharge this guarantee. 

5. We………………………………………further agree with the DDA that the DDA shall have (Indicate the name of the bank) the fullest liberty without our contest and without effecting in any manner our obligations hereunder to vary any of the terms and conditions of the said agreement or to extent time of performance by the said contractor (s) from time to time postpone for any time or from time to time any of the power exercisable by the DDA against the said contractors. And to for bear or enforce any of the terms & condition relating to the said agreement and we shall not be relieved from our liability of such variation, or extension being granted to the said contractor or for any forbearance, act of commission on the part .of the DDA or any indulgence by the DDA to the said contractor (s) or by any such matter or thing whatsoever which under the law relating to sureties would, but for this provisions, have effect of so relieving us. 

6. This guarantee will not be discharged due to the change in the constitution of the Bank or the Contractor (s). 

7. We…………………………..lastly undertake not to revoke this guarantee except with the (indicate the same of the Bank) Previous consent of the DDA in writing 

8. This guarantee shall be valid up to………………………………………………….unless extended on demand by DDA Not with standing anything mentioned above, our liability against this guarantee is restricted to Rs……………………………………………….only) and unless a claim in writing is lodged with us within six months of the date expiry or the extended date of expiry of this guarantee all our liabilities under this guarantee shall stand discharged. Dated the……………………...day of …………………….............................. for ..................................…………………(indicate the name of bank) 

Annexure-II

TABLE OF MILESTONE (S)

	Sr. No.
	Description of Milestone

(Physial)
	Time allowed in days

(from date of start)
	Amount to be withheld in case of nonachivement of milestone

	1.
	
	
	

	2
	--------------
	BLANK
	------------------------------

	3
	
	
	

	4.
	
	
	


OR
	S.No.
	Financial Progress
	Time Allowed in Months (From Date of Start)
	Amount to be withheld in case of non achievement of Milestone.

	1.
	1/8th  (of the whole work)
	1/4th (of the whole work.
	In the event of not achieving the necessary progress as assessed from the running payment, 1% of the Tendered Value of work will be withheld for failure of each Milestone.

	2.
	3/8th (of the whole work
	½ (of the whole work)
	- do -

	3.
	3/4th (of the whole work
	3/4th of the whole work
	- do -

	4.
	Full
	Full
	- do -


CLAUSE OF WORKS AGREMEENT FOR

SETTLEMENT OF DISPUTES & ARBITRATION

Except where otherwise provided in the contract all question and disputes relating to the meaning of the specification, designs, drawings and instructions herein before mentioned and as to the quality of workmanship or materials used on the work or as to any other question, claim, right, matter or thing whatsoever in any way arising out of or relating to the contract, design, drawings, specifications, estimates, instructions, orders of these conditions or otherwise concerning the works or the execution or failure to executes the same whether arising during the progress of work or after the cancellation, termination, completion or abandonment thereof shall be dealt with as mentioned hereinafter.

i)
If the Contractor considers any work demanded of him to be outside the requirements of the contract, or disputes any drawings, record or decision given in writing by the Engineer-in-charge or any matter in connection with or arising out the Contract or Carrying out of the work, to be unacceptable he shall promptly within 15 days request the Superintending Engineer in writing for written instruction or decision. Thereupon, the Superintending Engineer shall give his written instructions or decision within a period of one month from the receipt of the contractor’s letter.

If the Superintending Engineer fails to give his instructions or decisions in writing within the aforesaid period or if the Contractor is dissatisfied with the instructions or decision of the Superintending Engineer, the Contractor may, within 15 days of the receipt of Superintending Engineer’s decision appeal to the Chief Engineer who shall afford an opportunity to the Contractor to be heard, if the matter so desires and to offer evidence in support of his appeal. The Chief Engineer shall give his decision within 30 days of receipt of Contractor’s appeal If the contractor is dissatisfied with this decision the contractor shall within a peiod of 30 days from receipt of the decision, give notice to the Engineer Member, DDA for appointment of arbitrator failing which the said decision be final, binding and conclusive and not referable to adjudication by the arbitrator.
ii)
Except where the decision has become final, binding and conclusive in terms of Sub para (i) above, disputes or difference shall be referred for adjudication through arbitration by a Sole Arbitrator, who shall be a technical person having knowledge and experience of a trade, appointed by the Engineer Member, DDA. It will be no objection to any such appointment that the arbitrator so appointed is a DDA employee that he had to deal with the matter to which the contract relates and that in the course of his duties as DDA employee, he has expressed his views in all or any of the matters in dispute of difference. If the arbitrator so appointed is unable or unwilling to act or resigns his appointments or vacates his office due to any reason whatsoever, another sole arbitrator shall be appointed in the manner aforesaid. Such person shall be entitled to  proceed with the reference from the stage at which it was left by his predecessor.

It is a term of this contract that the Party invoking arbitration shll give a list of ispute with amounts laimed in respect of each such dispute alongwith the notice for appointmentof the arbitrator and giving the reference to the rejection by the Chief-Engineer of the appeal.


It is also a term of this contract that no person other than a  person appointed by the Engineer Member, DDA as aforesaid, should act as arbitrator and, if for any reason that is not possible, the matter shall not be referred to the arbitration at all. It is also a term of this contract that if the contractor does not make any demand for appointment of arbitrator in respect of any claims in writing as aforesaid within 120 days of receiving the intimation from the Engineer-in-charge that the final bill is ready for the payment, the claim of the contractor shall be deemed to have been waived and absolutely barred and the Delhi Development Authority shall be discharged and released of all liabilities under the contract in respect of these claims.


The arbitration shall be conducted in accordance with the provisions of the Arbitration and Conciliation Act 1996 (26 of 1996) or any statutory modifications or reenactment thereof and the rules made there under and for the time being in force shall apply to the arbitration proceeding under this clause. 


It is also term of this Contract that the arbitrator shall adjudicate on only such disputed as are referred to him by the appointing authority and give separate award against each dispute and claim referred to him and in all cases where the total amount of the claims by any party exceeds Rs.1,00,000/- the arbitrator shall give reasons for the award.


It is also a term of the Contract that if any fees are payable to the arbitrator these shall be paid equally by both the parties.


It is also a term of the Contract that the arbitrator shall be deemed to have entered on the reference on the date of issues notice to both the parties calling them to submit their statement of claims and couter statement of claims. The venue of the arbitration shall be Delhi. The fees, if any, of the arbitrator shall, if required to be paid before the award is made and published, be paid half and half by each of the parties. The cost of the reference and of the award (including the fees, if any, of the arbitrator) shall be in the discretion of the arbitrator who may direct to any by whom and in what manner, such costs or any part thereof shall be paid and fix or settle the amount of costs to be so paid.


The decision of the Superintending Engineer regarding the quantum of reduction as well as justification theeof in respect of rates for sub standard work which may be decided to be accepted will be final and would not be open to arbitration.
SCHEDULE OF QUANTITIES
Name of work
:
Peripheral Development of Integrated Frieght Complex (IFC) at Narela including Bulk Services
SH
:
Construction of boundary wall along Railway Line from 100 mt. R/W road to Railway Freight Terminal and raising of boundary wall along village Bhoregarh to Alipur Road.
	S. No.
	Description of Item
	Qty.
	Unit
	Rate
	Amount Rs.)

	1.
	Earth  work in excavation by mechanical means (Hydraulic Excavator)/ manual means over area excluding 30 cm. in depth 1.5 Mt. in width as well as 10 sqm on plan including disposal of excavated earth lead upto 50 mt. and lift upto 1.5 mtr. disposal earth to be leveled and neatly dressed.

a)  All kinds of soil.
	1854.00 Cum.
	Cum
	
	

	2.
	Filling available excavated earth (excluding rock) in tranches, plinth, sides of foundations etc. in layers not exceeding 20cm. in depth, consolidating each deposited layer by ramming and watering, lead upto 50 metre and lift upto 1.5 m.
	318.00 Cum
	Cum
	
	

	3.
	Providing and laying in position cement concrete of specified grade excluding the cost of centering and shuttering -  All works upto plinth level:

a) 1:5:10 ( 1 cement: 5 fine sand: 10 graded stone aggregate  40 mm nominal size)
	265.00 Cum.
	Cum
	
	

	
	    b)  1:2:4 ( 1 cement: 2 coarse sand: 4 graded stone aggregate 20 mm nominal size)
	99.00 cum
	Cum
	
	

	4.
	Centering and shuttering including strutting and propping etc. and removal of form work for foundation, footing basis for columns.
	499.00 Sq.m.
	Sq.m.
	
	

	5,
	Random rubble masonary with hard stone in foundation and plinth including leveling up with cement concrete 1:6:12 (1 cement : 6 coarse sand : 12 graded stone aggregate 20mm nominal size) at plinth level with cement mortar 1:6 (1 cement : 6 coarse sand)
	3608.00 cum.
	Cum
	
	

	6.
	Brick work with F.P.S. bricks of class designation 75 in foundation and plinth in cement mortar 1:6 (1 Cement: 6 Coarse Sand).
	33.00 Cum.
	Cum.
	
	

	7.
	Pointing on stone work with cement mortar 1:3 ( 1 cement : 3 fine sand)
(a)  Raised and cut pointing.
	4236.00 sqm
	Sqm
	
	

	8.3
	(b)  Flush / Ruled Pointing
	4236.00 sqm
	Sqm
	
	


Stipulated Material :  Cement : 381 MT @ Rs.5175/- per MT.


A.E. (P)





EE(P)/CC-11



S.E./CC-11/DDA


















